## Battery Bonus, All Islands
All Islands
Date | Units installed | MW (committed capacity) | MW (PV capacity) | MW Capacity (PV & Committed) | Incentives Paid | Units verified or In-progress | MW Verified or In-Progress | Units Rejected | Confirmed Units in Pipeline | Confirmed MW in Pipeline
2021-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
2021-08-01 | 0 | 0 | 0 | 0 | 0 | 31 | 0.16 | 25 | 31 | 0.16
2021-09-01 | 0 | 0 | 0 | 0 | 0 | 149 | 0.77 | 24 | 149 | 0.77
2021-10-01 | 0 | 0 | 0 | 0 | 0 | 280 | 1.5 | 35 | 280 | 1.5
2021-11-01 | 0 | 0 | 0 | 0 | 0 | 462 | 2.71 | 27 | 462 | 2.71
2021-12-01 | 28 | 0.14 | 0.069 | 0.209 | 118150 | 566 | 3.33 | 41 | 594 | 3.539
2022-01-01 | 62 | 0.308 | 0.173 | 0.481 | 261800 | 664 | 3.949 | 39 | 726 | 4.43
2022-02-01 | 114 | 0.591 | 0.602 | 1.193 | 502554 | 653 | 3.918 | 63 | 767 | 5.111
2022-03-01 | 178 | 0.89 | 0.8 | 1.69 | 756815 | 709 | 4.23 | 57 | 887 | 5.92
2022-04-01 | 235 | 1.19 | 0.99 | 2.18 | 1014263 | 758 | 4.54 | 70 | 993 | 6.72
2022-05-01 | 303 | 1.64 | 1.24 | 2.88 | 1395029 | 863 | 5.14 | 48 | 1166 | 8.02
2022-06-01 | 390 | 2.19 | 1.52 | 3.71 | 1864535 | 885 | 5.31 | 33 | 1275 | 9.02
2022-07-01 | 464 | 2.69 | 1.76 | 4.45 | 2277550 | 956 | 5.72 | 58 | 1420 | 10.17
2022-08-01 | 586 | 3.48 | 1.93 | 5.41 | 2960814 | 1098 | 6.64 | 62 | 1684 | 12.05
2022-09-01 | 651 | 3.89 | 2.15 | 6.04 | 3304214 | 1187 | 7.45 | 60 | 1838 | 13.49
2022-10-01 | 686 | 4.08 | 2.27 | 6.35 | 3468009 | 1361 | 7.1 | 63 | 2047 | 13.45
2022-11-01 | 822 | 4.92 | 2.65 | 7.57 | 4185426 | 1526 | 9.81 | 51 | 2348 | 17.38
2022-12-01 | 942 | 5.79 | 3.3 | 9.09 | 4925374 | 1617 | 10.55 | 53 | 2559 | 19.64
2023-01-01 | 1040 | 6.365 | 3.6654 | 10.0304 | 5413693 | 1786 | 11.92 | 88 | 2826 | 21.9504
2023-02-01 | 1156 | 7.08 | 4.1254 | 11.2054 | 6017856 | 1955 | 13.57 | 77 | 3111 | 24.7754
2023-03-01 | 1270 | 7.73 | 4.5 | 12.23 | 6572178 | 2223 | 15.83 | 90 | 3493 | 28.06
2023-04-01 | 1572 | 9.57 | 5.38 | 14.95 | 8136532 | 2262 | 16.52 | 81 | 3834 | 31.47
2023-05-01 | 1767 | 11 | 6.11 | 17.11 | 9348071 | 2393 | 17.27 | 58 | 4160 | 34.38
2023-06-01 | 1945 | 12.2 | 6.71 | 18.91 | 10367501 | 2487 | 18.22 | 34 | 4432 | 37.13
2023-07-01 | 2005 | 12.64 | 6.95 | 19.59 | 10746023 | 2643 | 19.28 | 46 | 4648 | 38.87
2023-08-01 | 2259 | 14.42 | 7.68 | 22.1 | 12262993 | 2663 | 19.4 | 77 | 4922 | 41.5
2023-09-01 | 2492 | 16.03 | 8.33 | 24.36 | 13624565 | 2832 | 20.41 | 69 | 5324 | 44.77
2023-10-01 | 2647 | 17.27 | 8.74 | 26.01 | 14680503 | 3158 | 22.39 | 67 | 5805 | 48.4
2023-11-01 | 2923 | 18.99 | 9.59 | 28.58 | 16146940 | 3381 | 26.29 | 56 | 6304 | 54.87
2023-12-01 | 3226 | 20.77 | 10.37 | 31.14 | 17652231 | 3389 | 26.59 | 37 | 6615 | 57.73
2024-01-01 | 3441 | 23.15 | 10.86 | 34.01 | 19017705 | 3683 | 28.81 | 83 | 7124 | 62.82
2024-02-01 | 3906 | 25.59 | 12.15 | 37.74 | 21744462 | 3499 | 28.86 | 22 | 7405 | 66.6
2024-03-01 | 4204 | 27.44 | 13 | 40.44 | 23318611 | 3266 | 27.3 | 20 | 7470 | 67.74
2024-04-01 | 4480 | 29.33 | 13.73 | 43.06 | 24927644 | 3032 | 25.72 | 7 | 7512 | 68.78
2024-05-01 | 4963 | 32.45 | 15.39 | 47.84 | 27579610 | 2622 | 23.84 | 13 | 7585 | 71.68
2024-06-01 | 5045 | 33.03 | 16 | 49.03 | 28076112 | 2575 | 23.49 | 3 | 7620 | 72.52
2024-07-01 | 5218 | 34.24 | 16.19 | 50.43 | 29103524 | 2444 | 22.55 | 0 | 7662 | 72.98

## Battery Bonus Maui
Maui
Date | Cumulative Installed |  |  |  | Cumulative Incentives Issued | Pending (in Progress & Verified) |  | Confirmed Units in Pipeline | Confirmed MW in Pipeline | Rejections
| Units | MW (committed capacity) | MW (PV capacity) | Committed PV & Battery | $ | Units | MW | Units | MW | Units
2021-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
2022-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
2022-08-01 | 0 | 0 | 0 | 0 | 0 | 10 | 0.11 | 10 | 0.11 | 4
2022-09-01 | 0 | 0 | 0 | 0 | 0 | 25 | 0.41 | 25 | 0.41 | 14
2022-10-01 | 0 | 0 | 0 | 0 | 0 | 75 | 0.7 | 75 | 0.7 | 7
2022-11-01 | 0 | 0 | 0 | 0 | 0 | 118 | 1.01 | 118 | 1.01 | 7
2022-12-01 | 0 | 0 | 0 | 0 | 0 | 153 | 1.25 | 153 | 1.25 | 4
2023-01-01 | 3 | 0.015 | 0.0054 | 0.0204 | 12750 | 189 | 1.48 | 192 | 1.5004 | 38
2023-02-01 | 4 | 0.02 | 0.0054 | 0.0254 | 17000 | 251 | 1.97 | 255 | 1.9954 | 20
2023-03-01 | 8 | 0.08 | 0.01 | 0.09 | 70678 | 344 | 2.69 | 352 | 2.78 | 21
2023-04-01 | 22 | 0.17 | 0.04 | 0.21 | 145818 | 390 | 3.09 | 412 | 3.3 | 24
2023-05-23 | 42 | 0.32 | 0.09 | 0.41 | 272213 | 421 | 3.31 | 463 | 3.72 | 15
2023-06-01 | 73 | 0.53 | 0.19 | 0.72 | 451818 | 432 | 3.41 | 505 | 4.13 | 7
2023-07-01 | 81 | 0.58 | 0.21 | 0.79 | 491598 | 462 | 3.61 | 543 | 4.4 | 9
2023-08-01 | 128 | 0.95 | 0.29 | 1.24 | 811104 | 482 | 3.7 | 610 | 4.94 | 24
2023-09-01 | 153 | 1.12 | 0.31 | 1.43 | 952799 | 505 | 3.85 | 658 | 5.28 | 13
2023-10-01 | 170 | 1.24 | 0.34 | 1.58 | 1057179 | 599 | 4.51 | 769 | 6.09 | 25
2023-11-01 | 199 | 1.47 | 0.41 | 1.88 | 1251251 | 642 | 4.67 | 841 | 6.55 | 26
2023-12-01 | 258 | 1.82 | 0.5 | 2.32 | 1545598 | 632 | 4.67 | 890 | 6.99 | 3
2024-01-01 | 308 | 2.97 | 0.58 | 3.55 | 1866796 | 662 | 4.84 | 970 | 8.39 | 6
2024-02-01 | 411 | 2.96 | 0.74 | 3.7 | 2512566 | 643 | 4.66 | 1054 | 8.36 | 6
2024-03-01 | 481 | 3.44 | 0.86 | 4.3 | 2920668 | 631 | 4.51 | 1112 | 8.81 | 9
2024-04-01 | 526 | 3.74 | 0.95 | 4.69 | 3177419 | 633 | 4.52 | 1159 | 9.21 | 4
2024-05-01 | 607 | 4.28 | 1.16 | 5.44 | 3637796 | 635 | 5.29 | 1242 | 10.73 | 12
2024-06-01 | 625 | 4.46 | 1.55 | 6.01 | 3789861 | 668 | 5.44 | 1293 | 11.45 | 3
2024-07-01 | 665 | 4.73 | 1.32 | 6.05 | 4017576 | 681 | 5.54 | 1346 | 11.59 | 0

## Battery Bonus O'ahu
O'ahu
Date | Cumulative Installed |  |  |  | Cumulative Incentives Issued | Pending (in Progress & Verified) |  | Confirmed Units in Pipeline | Confirmed MW in Pipeline | Rejections
| Units | MW (committed capacity) | MW (PV capacity) | Committed PV & Battery | $ | Units | MW | Units | MW | Units
2021-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
2021-08-01 | 0 | 0 | 0 | 0 | 0 | 31 | 0.16 | 31 | 0.16 | 25
2021-09-01 | 0 | 0 | 0 | 0 | 0 | 149 | 0.77 | 149 | 0.77 | 24
2021-10-01 | 0 | 0 | 0 | 0 | 0 | 280 | 1.5 | 280 | 1.5 | 35
2021-11-01 | 0 | 0 | 0 | 0 | 0 | 462 | 2.71 | 462 | 2.71 | 27
2021-12-01 | 28 | 0.14 | 0.069 | 0.209 | 118150 | 566 | 3.33 | 594 | 3.539 | 41
2022-01-01 | 62 | 0.308 | 0.173 | 0.481 | 261800 | 664 | 3.949 | 726 | 4.43 | 39
2022-02-01 | 114 | 0.591 | 0.602 | 1.193 | 502554 | 653 | 3.918 | 767 | 5.111 | 63
2022-03-01 | 178 | 0.89 | 0.8 | 1.69 | 756815 | 709 | 4.23 | 887 | 5.92 | 57
2022-04-01 | 235 | 1.19 | 0.99 | 2.18 | 1014263 | 758 | 4.54 | 993 | 6.72 | 70
2022-05-01 | 303 | 1.64 | 1.24 | 2.88 | 1395029 | 863 | 5.14 | 1166 | 8.02 | 48
2022-06-01 | 390 | 2.19 | 1.52 | 3.71 | 1864535 | 885 | 5.31 | 1275 | 9.02 | 31
2022-07-01 | 464 | 2.69 | 1.76 | 4.45 | 2277550 | 956 | 5.72 | 1420 | 10.17 | 57
2022-08-01 | 586 | 3.48 | 1.93 | 5.41 | 2960814 | 1088 | 6.53 | 1674 | 11.94 | 58
2022-09-01 | 651 | 3.89 | 2.15 | 6.04 | 3304214 | 1162 | 7.04 | 1813 | 13.08 | 46
2022-10-01 | 686 | 4.08 | 2.27 | 6.35 | 3468009 | 1286 | 6.4 | 1972 | 12.75 | 56
2022-11-01 | 822 | 4.92 | 2.65 | 7.57 | 4185426 | 1408 | 8.8 | 2230 | 16.37 | 44
2022-12-01 | 942 | 5.79 | 3.3 | 9.09 | 4925374 | 1464 | 9.3 | 2406 | 18.39 | 49
2023-01-01 | 1037 | 6.35 | 3.66 | 10.01 | 5400943 | 1597 | 10.44 | 2634 | 20.45 | 50
2023-02-01 | 1152 | 7.06 | 4.12 | 11.18 | 6000856 | 1704 | 11.6 | 2856 | 22.78 | 57
2023-03-01 | 1262 | 7.65 | 4.49 | 12.14 | 6501500 | 1879 | 13.14 | 3141 | 25.28 | 69
2023-04-01 | 1550 | 9.4 | 5.34 | 14.74 | 7990714 | 1872 | 13.43 | 3422 | 28.17 | 57
2023-05-23 | 1725 | 10.68 | 6.02 | 16.7 | 9075858 | 1972 | 13.96 | 3697 | 30.66 | 43
2023-06-23 | 1872 | 11.67 | 6.52 | 18.19 | 9915683 | 2055 | 14.81 | 3927 | 33 | 27
2023-07-01 | 1924 | 12.06 | 6.74 | 18.8 | 10254425 | 2181 | 15.67 | 4105 | 34.47 | 37
2023-08-01 | 2131 | 13.47 | 7.39 | 20.86 | 11451889 | 2181 | 15.7 | 4312 | 36.56 | 53
2023-09-01 | 2339 | 14.91 | 8.02 | 22.93 | 12671766 | 2327 | 16.56 | 4666 | 39.49 | 56
2023-10-01 | 2477 | 16.03 | 8.4 | 24.43 | 13623324 | 2559 | 17.88 | 5036 | 42.31 | 42
2023-11-01 | 2724 | 17.52 | 9.18 | 26.7 | 14895689 | 2739 | 21.62 | 5463 | 48.32 | 30
2023-12-01 | 2968 | 18.95 | 9.87 | 28.82 | 16106633 | 2757 | 21.92 | 5725 | 50.74 | 34
2024-01-01 | 3133 | 20.18 | 10.28 | 30.46 | 17150909 | 3021 | 23.97 | 6154 | 54.43 | 77
2024-02-01 | 3495 | 22.63 | 11.41 | 34.04 | 19231896 | 2856 | 24.2 | 6351 | 58.24 | 16
2024-03-01 | 3723 | 24 | 12.14 | 36.14 | 20397943 | 2635 | 22.79 | 6358 | 58.93 | 11
2024-04-01 | 3954 | 25.59 | 12.78 | 38.37 | 21750225 | 2399 | 21.2 | 6353 | 59.57 | 3
2024-05-01 | 4356 | 28.17 | 14.23 | 42.4 | 23941814 | 1987 | 18.55 | 6343 | 60.95 | 1
2024-06-01 | 4420 | 28.57 | 14.45 | 43.02 | 24286251 | 1907 | 18.05 | 6327 | 61.07 | 0
2024-07-01 | 4553 | 29.51 | 14.87 | 44.38 | 25085948 | 1763 | 17.01 | 6316 | 61.39 | 0

## Sheet1 (hidden)
Project | Guaranteed Commercial Operations Date
AES Kuihelani Solar (Stage 1) | GCOD 10-27-23
AES Waikoloa Solar | 12/26/22 COD (slipped from 11/3/2022)
Barber's Point Solar | Original GCOD 12-29-23 COD 5-2-24
Hale Kuawehi Solar | COD 5/5/23 (slipped from 4/28/23 and 12/2/22)
Ho‘ohana Solar 1 (Stage 1) | GCOD 8-31-23 Estimated COD 12-15-23
Kahana Solar (Stage 2) | Original GCOD: 12-29-23 Anticipated COD 4-17-24
Kamaole Solar (Stage 2) | Original GCOD 07-25-23 Anticipated COD 10-29-24
Kapolei Energy Storage (KES) (Stage 2) | New GCOD 12-30-22 Estimated COD 3-10-23
Keahole Battery Energy Storage | 1-23-24 (slipped from 12-28-23 and 11-28-23)
KHLS Phase 1 | GCOD 12-17-22 COD Aug-23
Kūpono Solar | GCOD 4-9-24
Mahi Solar (Stage 2) | Original GCOD 12-31-23 New Proposed GCOD 3-31-24 (GCOD in recent PPA under review by PUC)
Mililani I Solar (Stage 1) | New GCOD 7-31-22 Estimated COD 7-29-22
Mountain View Solar (Stage 2) | GCOD 5-17-23 Estimated COD 6-6-23
Paeahu Solar Stage 1 (docket suspended) | Suspension lifted 5-11-22 GCOD 4-28-23 COD 9-8-23
Palailai Solar 1 - Phase 1 | New GCOD 1-27-23 COD March 2023
Pulehu Solar (Stage 2) | COD now listed as 10-31-24 Proposed new GCOD 12-31-23 Original GCOD was 4-28-23
Waena Battery Energy Storage System (Awaiting Commission Approval) | 5-28-24 (slipped from 4-26-24, 3-29-24 and 2-29-24 and 1-29-24)
Waiawa Phase 2 Solar (Stage 2) | GCOD 10-30-23
Waiawa Solar (Stage 1) | New GCOD 9-30-22 Estimated COD 11-14-22 (COVID-19 lockdown in Shanghai, China delaying delivery of battery enclosures; could impact COD)
West O‘ahu Solar (Stage 1) | GCOD 9-7-22 Estimated COD 1-20-23 (Extended due to Force Majeure)

## Discretionary Permits Remain (hidden)
Discretionary Permit Outstanding
Project | Developer | State | City and County | Notes
West O‘ahu Solar | AES |  | N/A | not really a discretionary permit, but approval still needed
Mountain View Solar Stage 2 | AES | PUC overhead line review, IRS target 11-15 6e SHPD compliance | CUPminor, Zoning waiver (DPP) | status update states "if applicable" for zoning waiver- it is applicable
Waiawa Phase 2 Solar (Stage 2) | AES | 6e compliance, LUC ammendment | CUPm, Zoning waiver (DPP) | status update states "if applicable" for zoning waiver - it is applicable
Mahi Solar | Longroad Energy |  | CUPminor, Zoning Waiver (DPP)

## TF Project Permit Details (hidden)
Project | Permitting, Approving, or Accepting Agency | Permit or Approval | Discretionary or Ministerial | Application Date or Status | Issuance Status | Permit or Approval Issuance or Target (ETA) Date | Last Updated (HSEO ref)
AES West O‘ahu | AES West O‘ahu Solar (Stage 1) | [5 empty] | 2021-09-24
AES West O‘ahu | PUC | Overhead Line Review | Discretionary | Approved | Approved 3-18-21 | Approved 3-18-21
AES West O‘ahu | DLNR-SHPD | HRS 6E Compliance | Discretionary | Approved | Approved | 2021-01-04
AES West O‘ahu | DPP, OEQC | HRS 343 Compliance (Environmental Assessment) | Discretionary | Approved | Approved | FEA accepted and filed on 7-8-20
AES West O‘ahu | DOH-CWB | NPDES | Ministerial | Approved | Approved | 2021-03-31
AES West O‘ahu | AES West O‘ahu Solar | Special Use Permit | Discretionary | Approved | Approved | Complete 5-13-21, Final approval 6-10-21
AES West O‘ahu | DPP | Conditional Use Permit - Minor | Discretionary | Permit Application Filing milestone was met in August 2020 | Land Use Commission rescheduled hearing from May 26-27 to June 9; impacted ability to move forward with CUP (Minor). Working with DPP to accelerate DPP permits | 2021-08-12
AES West O‘ahu | DLNR - Land Court | Secure Land Rights | Ministerial | Estimate sending easement to land court mid August to early September |  | 2021-10-01
AES West O‘ahu | DOH-IRHB | Noise Permit | Ministerial | Permit Application Filing milestone was met in August 2020 |  | ETA Q3-Q4 2021
AES West O‘ahu | DPP | Grading, Grubbing, and Stockpiling Permit | Ministerial | Permit Application Filing milestone was met in August 2020 | Land Use Commission delayed hearing June 9 (approved); impacted ability to move forward with CUP (Minor). Working with DPP to accelerate DPP permits. | ETA Q4 2021
AES West O‘ahu | DPP | Building and Electrical Permit | Ministerial | Permit Application Filing milestone was met in August 2020 | Land Use Commission rescheduled hearing from May 26-27 to June 9; impacted ability to move forward with CUP (Minor). Working with DPP to accelerate DPP permits | ETA Q4 2021
Kupehau | Kupehau Solar (Stage 2) | [5 empty] | 2021-07-27
Mililani I | Mililani I Solar (Stage 1) | [5 empty] | 2021-07-29
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2021-03-04
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2020-01-23
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2020-01-23
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2017-07-06
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2017-07-06
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2014-10-03
Mililani I | DPP | Zoning Waiver | Ministerial | submitted | Approved | 2014-07-29
Mililani I | DPP | Conditional Use Permit - Minor | Discretionary | submitted | Approved | 2014-07-29
Mililani I | DPP | Conditional Use Permit - Minor (Joint Development) | Discretionary | submitted | Approved | 2010-05-07
Mililani I | DOH-CWB | NPDES | Ministerial | submitted | Approved | 2021-01-19
Mililani I | FAA | FAA Determination of No Hazard | Ministerial | submitted | Completed | Summer-Fall 2019
Mililani I | USACOE | Section 404 Clean Water Act - Nationwide Permit Program | Ministerial | submitted | Completed | Summer-Fall 2019
Mililani I | USFWS, DLNR-DOFAW | Biological Resource Consultation | Ministerial | submitted | Completed | Summer-Fall 2019
Mililani I | DPP | Grading and Grubbing Permit | Ministerial | Submitted Nov 2020 | Approved | 2021-03-12
Mililani I | DPP | Building Permit (PV Project) | Ministerial | Submitted Nov 2020 | Approved | 2021-03-12
Mililani I | DOH-CWB | Section 401 Water Quality Certification | Ministerial | Not Required | Not Required | N-A
Mililani I | USFWS | Section 7-10 Endangered Species Act Consultation | Ministerial | Not Required | Not Required | N-A
Mililani I | DPP | Building Permit (HECO Substation) | Ministerial | N-A | N-A | N-A
Mililani I | DPP | Building Permit (Project Substation) | Ministerial | Received courtesy inspection approval, anticipate full approval by end of July | Courtesy inspection approval received, Pending full approval (anticipated end of July) | 2021-07-30
Waiawa | Waiawa Solar (Stage 1) | [5 empty] | 2021-07-28
Waiawa | USACOE | Section 404 Clean Water Act - Nationwide Permit Program | Ministerial | Not Required | Not Required | N-A
Waiawa | USFWS | Section 7-10 Endangered Species Act Consultation | Ministerial | Not Required | Not Required | N-A
Waiawa | FAA | FAA Determination of No Hazard | Ministerial |  | Completed | Summer-Fall 2019
Waiawa | USFWS, DLNR-DOFAW | Biological Resource Consultation | Ministerial |  | Completed | Summer-Fall 2019
Waiawa | DOH-CWB | Section 401 Water Quality Certification | Ministerial | Not Required | Not Required | N-A
Waiawa | PUC | Overhead Line Review | Discretionary | Approved | Approved | March, 2021
Waiawa | DOH-CWB | NPDES- Construction | Ministerial | Approved | Approved | 2021-01-19
Waiawa | LUC | Motion to Amend for Urban Land Use | Discretionary | Approved | Approved | 2020-02-11
Waiawa | DPP | Zoning Waiver(s) | Discretionary | Approved Approved | Approved Approved | August 13, 2020 March 15, 2021
Waiawa | DPP | Conditional Use Permit - Minor | Discretionary | Approved | Approved | 2021-04-01
Waiawa | DPP | Conditional Use Permit - Minor Modification | Discretionary | Approved | Approved | 2021-03-15
Waiawa | DPP | Grading and Grubbing Permit | Ministerial | Approved | Approved | 2021-04-06
Waiawa | DPP | Building Permit (PV-BESS Project) | Ministerial | Approved | Q2 2021 | 2021-04-19
Waiawa | DPP | Building Permit (Project Substation) | Ministerial | Approved | Q2 2021 | Q2 2021
Waiawa | DOT | Highway Permit | Ministerial | Submitted | Pending | Q2 2021
Waiawa | DPP | Building Permit (Overhead Line) | Ministerial | Target Submission Q2 2021 | Pending | 2021-10-01
AES Mountain View | AES Mountain View Solar (Stage 2) | [5 empty] | 2021-07-28
AES Mountain View | PUC | Overhead Line Review | Discretionary |  | In progress
AES Mountain View | DLNR-SHPD | HRS 6E Compliance | Discretionary |  |  | ETA Q4 2021-Q1 2021
AES Mountain View | DPP | Conditional Use Permit - Minor | Discretionary |  |  | ETA Q4 2021-Q1 2022
AES Mountain View | DPP | Zoning Waiver (if applicable) | Ministerial |  |  | ETA Q4 2021-Q1 2022
AES Mountain View | DOH-CWB | NPDES | Ministerial |  |  | ETA Q1 2022-Q2 2022
AES Mountain View | DOH-IRHB | Noise Permit | Ministerial |  |  | ETA Q4 2021-Q1 2022
AES Mountain View | DPP | Grading, Grubbing, and Stockpiling Permit | Ministerial |  |  | ETA Q1-Q2 2022
AES Mountain View | DPP | Building and Electrical Permit | Ministerial |  |  | ETA Q1-Q2 2022
Ho‘ohana | Ho‘ohana Solar (Stage 1) | [5 empty] | 2021-07-28
Ho‘ohana | DPP | Conditional Use Permit - Minor | Discretionary |  | Approved | 2015-01-01
Ho‘ohana | DLNR-SHPD | HRS 6E Compliance | Discretionary |  | AIS accepted 2-19-15 | AIS accepted 2-19-15
Ho‘ohana | DPP | Grading (Initial Road Construction) | Ministerial |  | Approved | 2019-12-01
Ho‘ohana | DPP | Conditional Use Permit - Minor Modification | Discretionary |  | Approved | 2019-10-18
Ho‘ohana | DPP | Conditional Use Permit - Minor Modification | Discretionary |  | Approved | 2019-10-19
Ho‘ohana | DOH-CWB | NPDES (Initial Road Construction) | Ministerial |  | Approved | 2019-12-01
Ho‘ohana | DPP | Zoning Waiver | Ministerial |  | Approved | 2021-08-01
Ho‘ohana | DPP | Conditional Use Permit - Minor Modification | Discretionary |  | Approved | 2021-08-01
Ho‘ohana | DPP, LUC | Special Use Permit - Amendment- Restatement of State Land Use Boundary Amendment | Discretionary |  | Approved - Decision and Order pending | 2020-10-08
Ho‘ohana | DOT | Road Crossing Agreement | Ministerial |  | Not Applicable
Ho‘ohana | DPP | Building Permit (HECO Switchyard) | Ministerial | Not required per DPP guidance; requesting confirmatory letter from DPP |  | N-A
Ho‘ohana | PUC | 46kV Line Relocation Approval | Discretionary |  | In Progress
Ho‘ohana | DPP | Grading (Solar and Battery Project) | Ministerial | Target submission July 2021 |  | ETA October 2021
Ho‘ohana | DPP | Grading (Project Substation) | Ministerial | Submitted 5-12-2021 |  | ETA October 2021
Ho‘ohana | DPP | Grading (HECO Switchyard) | Ministerial | Initial submission 5-12-2021; some design work refinement continuing |  | ETA October 2021
Ho‘ohana | DOH-CWB | NPDES - Form C (Solar and Battery Project) | Ministerial | Initial submission 3-22-2021; some design work refinement continuing |  | ETA October 2021
Ho‘ohana | DOH-CWB | NPDES - Form C (Project Substation) | Ministerial | Initial submission 5-12-2021; some design work refinement continuing |  | ETA October 2021
Ho‘ohana | DPP | Building Permit (Solar and Battery Project) | Ministerial | Submit June 2021. Project design in progress |  | ETA November 2021
Ho‘ohana | DPP | Building Permit (Project Substation) | Ministerial | Submission 5-12-2021 |  | ETA November 2021
Waiawa | Waiawa Phase 2 Solar | [5 empty] | 2021-07-28
Waiawa | PUC | Overhead Line Review | Discretionary
Waiawa | DOH-US Navy | Zone of Influence Approval (if applicable) | Ministerial |  |  | ETA Q2-Q3 2021
Waiawa | DLNR-SHPD | HRS 6E Compliance | Ministerial | HRS 6E compliance to START 12-18-20 | HRS 6E compliance to targeted to END 4-9-21 | ETA Q2-Q3 2021
Waiawa | LUC | LUC Amendment to Decision and Order |  |  |  | ETA Q3-Q4 2021
Waiawa | DPP | Conditional Use Permit - Minor |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DPP | Conditional Use Permit - Minor (Joint Development) |  |  |  | ETA Q3 2021-Q4 2021
Waiawa | DPP | Conditional Use Permit - Minor Modification |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DPP | Zoning Waiver (if applicable) |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DOH-CWB | NPDES - Form C |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DOH-IRHB | Noise Permit |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DPP | Grading, Grubbing, and Stockpiling Permit |  |  |  | ETA Q1-Q2 2022
Waiawa | DPP | Building and Electrical Permit |  |  |  | ETA Q1-Q2 2022
| Mahi Solar | [5 empty] | 2021-09-10
Mahi | DOT | Permit to Cross Public Highway |  |  | Not Required
Mahi | PUC | Approval of PPA |  | Approved - 12-31-2020 | Approved | 2020-12-31
Mahi | PUC | Overhead Line Review |  | Application filed 4-6-21; stipulated procedural schedule filed on 6-21-21 | In Progress
Mahi | DPP, LUC | Special Use Permit |  | Application submitted on 12-15-2020; Revised and resubmitted March 2021. | Approved | 2021-09-09
Mahi | DLNR-SHPD | HRS 6E Compliance (Plan Approval, Archeological Assessment) |  | SHPD accepted the AIS with the proposed mitigation and monitoring measures. Significant traditional historic properties and wahi pana have been identified in the vicinity, including Pohakea Trail, ali‘i battle sites, a heiau atop Pu‘u Ku‘ua, and Honouliuli National Historic Site, among others. None of these significant historic properties were identified as extending into the Mahi Solar project area. However, two plantation-related sites abut or extend into the project area: the Waiāhole Ditch (Site 50-80-09-2268) and remnants of the Oʻahu Sugar Company Irrigation Infrastructure (Site 50-80-12-7346). The AIS report (Rechtman, September 2021) meets the requirements of HAR 13-276-5. It is accepted. Please submit one hard copy of the AIS, labeled Final, along with a text-searchable pdf copy of the AIS and a copy of this letter to the SHPD Kapolei office, attention Library. Please upload a text-searchable pdf copy of the Final AIS to HICRIS Project No. 2021PR00380 using the Project Supplement option, and a copy to Lehua.K.Soares@hawaii.gov. SHPD hereby notifies the DPP that SUP permit issuance process may continue with the understanding that an AMP meeting the requirements of HAR §13-279-4 prior to project initiation shall be submitted for SHPD review and acceptance prior to project initiation. | Determination received | 2021-09-08
Mahi | DPP | Zoning Waiver |  | Target submission August 2021 (after SUP Approval) |  | ETA 10-27-2021
Mahi | DPP | Conditional Use Permit - Minor for Utility Installation, Type B |  | Target submission August 2021 (after SUP Approval) |  | ETA 10-27-2021
Mahi | DPP | Conditional Use Permit - Minor Joint Development |  |  |  | 2021-02-18
Mahi | DPP | Building Permits |  | Target submission October 2021 |  | ETA February 2022
Mahi | DPP | Grading, Grubbing, Stockpiling Permit |  | Target submission October 2021 |  | ETA February 2022
Mahi | DOH-CWB | NPDES - Form C |  |  |  | ETA February 2022
Mahi | DOH-IRHB | Noise Permit |  |  |  | ETA December 2021
kes | Kapolei Energy Storage (Stage 2) | [5 empty] | 2021-07-29
kes | DPP | Conditional Use Permit - Minor |  | Approved - 10-29-2019 | Approved | Approved 10-28-20
kes | PUC | Overhead Line Review |  | Submitted 4-6-2021 | In progress
kes | DPP | Drainage Plan Approval
kes | DPP | Grading, Grubbing, Stockpiling Permit |  | Anticipated to file the application on 10-12-2021 to third party reviewer |  | Update: ETA 2-9-22, slipped from ETA 12-28-2021 (expected)
kes | DPP | Building and Electrical Permit |  | Anticipated to file the application on 11-12-2021 to third party reviewer |  | Update: 3-12-22, slipped from ETA 1-28-2022 (expected)
kes | DOH- CWB | NPDES - Form C |  | Anticipated to file the application to third party reviewer on 10-12-21 |  | Update: ETA 2-9-22, slipped from ETA 12-28-2021 (expected)
kes | DLNR-SHPD | HRS 6E Compliance |  | no longer on docket update (may need to follow-up).
kes | PUC | Overhead Line Review |  | Notice of approval sent on Sept. 15 2021 | Approved | Approved 09/15/2021
Barbers Point Solar (PPA Not Yet Approved by PUC)
| DHHL | HRS 343 EA |  |  | In progress, pre-assessment consultation
| DOT-HWY | Permit to Perform Work Upon State Highway
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I changed this, since some of these are not "permitting" agencies, but are aproving entities - I think it is a difference worth distinguising to help stakeholders understand different roles.
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a column or way to indicate if a permit or approval is ministerial, discretionary, or unclear?
Note on C49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: do you know if this is the permit to perfom work, or is this for application for occupancy and use? both? I am guessing it is for work?
Note on E71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: do they have a confirmatory letter?

## Permit References and Timelines (hidden)
Jurisdiction | Permitting / Approving Agency | Permit or Approval | Resources |  | Type | Common Rank (1 most common - 5 less common) | Typical Timeline (days) | https://energy.hawaii.gov/renewable-energy-project-permitting-in-the-state-of-Hawai‘i
County | DPP | Conditional Use Permit - Minor | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/ReportsNotices/MonthlyBulletins.aspx | Discretionary | 1 | 45
County | DPP | Grading Permit | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/ReportsNotices/MonthlyBulletins.aspx | Ministerial | 1
County | DPP | Zoning Waiver | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/Calendar.aspx | Ministerial | 1 | 30-90 days | https://energy.hawaii.gov/wp-content/uploads/2015/07/Oahu-Waiver-Permit_March-2015.pdf
County | DPP | Grubbing Permit | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/ReportsNotices/MonthlyBulletins.aspx | Ministerial | 1
County | DPP | Building Permit Project | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/ReportsNotices/MonthlyBulletins.aspx | Ministerial | 1
State | DOH-CWB | NPDES (Initial Road Construction) | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 1
Steate | DOH-CWB | NPDES (Construction) | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 1
State | DOH-CWB | NPDES (Solar and Battery Project) | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 1
State | DOH-IRHB | Noise Permit | ask developer |  | Ministerial | 1
State | LUC (State) | Special Use Permit (Projects >15 acres, LUC makes final decision). | https://luc.hawaii.gov/ |  | Discretionary | 1
County | Planning Commission (County) | Special Use Permit (Projects >15 acres, LUC makes final decision). | https://www.honolulu.gov/dpppd/default.html |  | Discretionary
County | DPP | Trenching Permit | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx |  | Ministerial | 2
State | DOT-HWY | Permit Application to Perform Work Upon State Highways |  |  | Ministerial | 2 | 5-10 days
State | DOT-HWY | Application & Permit for the Occupancy & Use of State Highway Right-of-Way |  |  | Ministerial | 2 | 5-10 days
State | DOH-CWB | NPDES Dewatering | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 2
County | DPP | Conditional Use Permit - Major | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx |  | Discretionary | 3 | 90
Federal | USACOE | Section 404 Clean Water Act - Nationwide Permit Program |  |  | Ministerial | 3
State | DLNR - OCCL | Conservation District Use Permit | https://dlnr.hawaii.gov/occl/current-applications/ |  | Discretionary | 3
State | DBEDT - OP | CZMA Fed Consistency |  |  | Ministerial | 3
State | LUC | District Boundary Amendment | https://luc.hawaii.gov/calendar/ luc.hawaii.gov -> then hit pending dockets -> boundary amendments |  | Discretionary | 3 | 365
Federal | USACE | CWA Section 404 Permit - Individual |  |  | Discretionary | 4
State | DPP | SMA - major | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/Calendar.aspx | Discretionary | 5 | 180
Federal | USACE | Section 9 |  |  | Discretionary | 5
State | PUC | 46kV Line Relocation Approval |  |  | Discretionary - PUC | 1
State | SHPD | HRS 6E, Historic Preservation | https://dlnr.hawaii.gov/shpd/intake-and-determinations/ | see determinations reports | Discretionary | 1
Federal | USFWS | Section 7/10 Endangered Species Act Consultation |  |  | Ministerial | 2
Federal | FAA | FAA Determination of No Hazard |  |  | Ministerial | 2
State | Varies - Accepting Agency | HRS 343 EA | http://oeqc2.doh.hawaii.gov/_layouts/15/start.aspx#/Doc_Library/ |  | Discretionary | 3
State | DOH CWB | CWA Section 401 WQ Certification | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 3
State | DLNR - CWRM | Stream channel Alteration |  |  | Discretionary | 4
State / County | DLNR - CWRM | Stream Diversion |  |  | Discretionary | 4
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I changed this, since some of these are not "permitting" agencies, but are aproving entities - I think it is a difference worth distinguising to help stakeholders understand different roles.
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a column or way to indicate if a permit or approval is ministerial, discretionary, or unclear?

## TMKs (hidden)
Project * | Tax Map Key(s)
AES Mountain View Solar | 185003031; 185003032; 185019034
AES West Oahu Solar Plus Storage | 192002007
Hoohana Solar 1 | 194002052
Kapolei Energy Storage | 191014042
Mahi Solar | 192001001; 192004012; 192004006; 192004003; 192004010
Mililani I Solar | 194005090; 194005092; 194005096; 194005091
Waiawa Phase 2 Solar | 196004024; 196004025; 196004026; 196006036
Waiawa Solar Power | 196004024

## zzz_TF Master Schedule (hidden)
| 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-11-21 | 2021-11-21 | 2021-11-21 | 2021-11-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-02-22 | 2022-02-22 | 2022-02-22 | 2022-02-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-04-22 | 2022-04-22 | 2022-04-22 | 2022-04-22 | 2022-05-22 | 2022-05-22 | 2022-05-22 | 2022-05-22 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | Coal | 2022-09-01 | 2022-09-01 | 2022-09-01 | 2022-09-01 | 2022-10-22 | 2022-10-22 | 2022-10-22 | 2022-10-22 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2023-01-23 | 2023-02-23 | 2023-03-23 | 2023-04-23 | 2023-05-23 | 2023-06-23 | 2023-07-23 | 2023-08-23 | 2023-09-23 | 2023-10-23 | 2023-11-23 | 2023-12-23
AES West O‘ahu Solar (Stage 1) - 2019-0050 | [64 empty] | Plant | GCOD
Environmental Site Studies | DONE | [63 empty] | Shut
Engineering and Design | Engineering (Q3 2020 - Q3 2021); Engineering at 100% design phase | [63 empty] | Down
IRS System Impact Study | DONE
IRS Facility Study | DONE
IRS Amendment | DONE
Transmission Line Approval | DONE
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q3 2020 - Q4 2021) -- LUC hearing on SUP 6/9-6/10; CUP expected Q3 2021
Permitting: Construction (Ministerial) | Permitting (Q3 2020 - Q4 2021)
Procurement | Procurement (Q1 2021 - Q4 2021)
Construction | [20 empty] | Construction (Q4 2021 - Q2 2022)
Hawaiian Electric Work | Hawaiian Electric Work (Q4 2020 - Q2 2022) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [32 empty] | Testing and Commissioning (Q1 2022 - Q3 2022) -- Acceptance Test typically takes 30 business days
Energization | [32 empty] | Testing and Commissioning (Q1 2022 - Q3 2022) -- Energization is a one time event
Commissioning | [32 empty] | Testing and Commissioning (Q1 2022 - Q3 2022) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [32 empty] | Testing and Commissioning (Q1 2022 - Q3 2022) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [65 empty] | GCOD
Mililani I Solar (Stage 1) - 2018-0434 | [73 empty] | GCOD
Environmental Site Studies | DONE
Engineering and Design | Engineering (Q2 2020 - Q3 2021) -- HECO reviewed 90% design; Issued for Construction (IFC); 60% design for substation
IRS System Impact Study | DONE
IRS Facility Study | DONE
IRS Amendment | DONE
Transmission Line Approval | DONE
Permitting: Environmental and Land Use (Discretionary) | DONE
Permitting: Construction (Ministerial) | Permitting (Q4 2020 - Q2 2021) -- final Building Permit (substation) expected June 2021
Procurement | Procurement (Q3 2020 - Q3 2021)
Construction | Construction (Q1 2021 - Q1 2022) -- groundbreaking ceremony April 2021; construction expected May 2021
Hawaiian Electric Work | Hawaiian Electric Work (Q4 2020 - Q4 2021) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [32 empty] | Testing and Commissioning (Q1 2022 - Q4 2022) -- Acceptance Test typically takes 30 business days
Energization | [32 empty] | Testing and Commissioning (Q1 2022 - Q4 2022) -- Energization is a one time event
Commissioning | [32 empty] | Testing and Commissioning (Q1 2022 - Q4 2022) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [32 empty] | Testing and Commissioning (Q1 2022 - Q4 2022) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [57 empty] | Potential GCOD 7/31/22 | [15 empty] | GCOD
Waiawa Solar (Stage 1) - 2018-0435 | [77 empty] | GCOD
Environmental Site Studies | DONE
Engineering and Design | Engineering (Q4 2020 - Q3 2021) -- HECO reviewed 90% substation design; 60% gen-tie design; 90% design under development
IRS System Impact Study | DONE
IRS Facility Study | DONE
IRS Amendment | DONE
Transmission Line Approval | DONE
Permitting: Environmental and Land Use (Discretionary) | DONE
Permitting: Construction (Ministerial) | Permitting (Q4 2020 - Q3 2021) -- substation Building Permit expected July 2021; 46kV OH line Building Permit expected October 2021
Procurement | Procurement (Q3 2020 - 4 2021)
Construction | Construction (Q1 2021 - Q2 2022) -- groundbreaking ceremony April 2021; construction expected May 2021
Hawaiian Electric Work | Hawaiian Electric Work (Q4 2020 - Q4 2021) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [44 empty] | Testing and Commissioning (Q2 2022 - Q4 2022) -- Acceptance Test typically takes 30 business days
Energization | [44 empty] | Testing and Commissioning (Q2 2022 - Q4 2022) -- Energization is a one time event
Commissioning | [44 empty] | Testing and Commissioning (Q2 2022 - Q4 2022) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [44 empty] | Testing and Commissioning (Q2 2022 - Q4 2022) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [63 empty] | Potential GCOD 8/31/22 | [13 empty] | GCOD
Kapolei Energy Storage (Stage 2) - 2020-0136 | [69 empty] | New GCOD - early battery delivery | [10 empty] | New GCOD - NO early battery delivery
Environmental Site Studies
Engineering and Design | Early Engineering Letter Agreement executed; HE reviewed 30% design
IRS System Impact Study | DONE
IRS Facility Study | Revised FS completed May 2021, however, revisions are likely due to KES's new proposed schedule
IRS Amendment | IRS Amendment process scheduled from late May to July 2021
Transmission Line Approval | Application for 138kV OH line filed 4/6/21
Permitting: Environmental and Land Use (Discretionary) | DONE -- KES plans to secure land rights by June 2021
Permitting: Construction (Ministerial) | [16 empty] | Construction Permitting (9/15/21 - 1/7/22)
Procurement | Procurement (3/16/21 - 6/10/22)
Construction | Construction (October 2020 - July 2022)
Hawaiian Electric Work | Hawaiian Electric Work (September 2019 - July 2022)
Acceptance Test | [57 empty] | Acceptance Testing
Control System Acceptance Test | [65 empty] | CSAT
Commercial Operations | [52 empty] | Original GCOD | [16 empty] | New GCOD - early battery delivery | [10 empty] | New GCOD - NO early battery delivery
AES Mountain View Solar (Stage 2) - 2020-0139
Environmental Site Studies |  | Virtual Public Meeting on 5/19
Engineering and Design | Engineering (Q2 2021 - Q2 2022) -- to stay on schedule Early Engineering Agreement must be executed no later than June 2021; AES and HE are discussing Early Engineering (May 2021 Status Report)
IRS System Impact Study | Anticipated to be completed May 2021
IRS Facility Study | Exchanged comments May 2021
IRS Amendment | [8 empty] | Estimated filing of IRS Amendment for Stage 2 projects (2Q/3Q 2021)
Transmission Line Approval | [8 empty] | Estimated filing of OH Line Approval for Stage 2 projects (2Q/3Q 2021)
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q3 2021 - Q2 2022) -- HRS 6E compliance to be completed Q2/Q3 2021; Environmental and Land Use Permitting to be completed by Q1 2022 (May 2021 Status Update)
Permitting: Construction (Ministerial)
Procurement | [8 empty] | Procurement (Q3 2021 - Q2 2022)
Construction | [44 empty] | Construction (Q2 2022 - Q1 2023)
Hawaiian Electric Work - Remote Engineering | [8 empty] | Remote Engineering (Q3 2021 - Q1 2022)
Hawaiian Electric Work - Remote Procurement | [20 empty] | Remote Procurement (Q4 2021 - Q3 2022)
Hawaiian Electric Work - Remote Construction | [56 empty] | Remote Construction (Q3 2022)
Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q2 2023) -- Acceptance Test typically takes 30 business days
Energization | [81 empty] | Testing and Commissioning (Q1 2023 - Q2 2023) -- Energization is a one time event
Commissioning | [81 empty] | Testing and Commissioning (Q1 2023 - Q2 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q2 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [85 empty] | GCOD
Kupehau Solar (Stage 2) - 2020-0138
Environmental Site Studies
Engineering and Design | Engineering (Q2 2020 - Q3 2022) -- Early Engineering Agreement executed; HECO reviewed 30% design
IRS System Impact Study | Anticipated SIS completion date May 2021
IRS Facility Study | Preliminary FS under review by 174PG
IRS Amendment | Anticipated IRS Amendment completion date is confidential (HECO 3/15/21 IR Response)
Transmission Line Approval | To be included with Ho‘ohana Solar 1
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q1 2020 - Q2 2022) -- Environmental and Land Use Permit to be completed March 2022 (May 2021 Status Update)
Permitting: Construction (Ministerial) | Permitting (Q1 2020 - Q2 2022) -- Construction Permitting to be completed May 2022 (May 2021 Status Update)
Procurement | Procurement (Q2 2020 - Q3 2022)
Construction | [32 empty] | Construction (Q1 2022 - Q1 2023)
Hawaiian Electric Work | Hawaiian Electric Work (Q1 2021 - Q1 2023) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Acceptance Test typically takes 30 business days
Energization | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Energization is a one time event
Commissioning | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [87 empty] | New estimated GCOD (7/1/23)
Ho‘ohana Solar 1 (Stage 1) - 2018-0431
Environmental Site Studies | DONE
Engineering and Design | Engineering (Q2 2020 - Q1 2022) -- 60% switchyard design due to HECO 6/3/21; 90% switchyard design due to HECO 10/6/21
IRS System Impact Study | SIS re-study expected to be completed May 2021
IRS Facility Study | DONE
IRS Amendment | DONE
Transmission Line Approval | Application for 138kV Kahe-Hālawa OH line filed 2/26/21; application for 138kV Kahe-Waiau UG line to be filed June 2021; filing for 46kV Wai‘au-Mililani UG/OH line relocation to be filed June 2021
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q1 2020 -Q1 2022) -- CUP-M modification and Zoning Waiver to be submitted June 2021
Permitting: Construction (Ministerial) | Permitting (Q1 2020 -Q1 2022) -- final Building Permit (solar/battery) to be submitted June 2021
Procurement | Procurement (Q2 2021 - Q3 2022)
Construction | [32 empty] | Construction (Q1 2022 - Q1 2023)
Hawaiian Electric Work | Hawaiian Electric Work (Q2 2021 - Q4 2022) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Acceptance Test typically takes 30 business days
Energization | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Energization is a one time event
Commissioning | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [88 empty] | GCOD
Waiawa Phase 2 Solar (Stage 2) - 2020-0137
Environmental Site Studies
Engineering and Design |  |  |  |  | Engineering (Q1 2021 - Q2 2022) -- Engineering and Design must start June 2021 to stay on schedule; AES and HE are discussing Early Engineering; Waiawa Solar (stage 1 ) line runs through Waiawa Phase 2 site; potential delays to GCOD if Wahiawa substation work is not completed on-time (May 2021 Status Report)
IRS System Impact Study | DONE
IRS Facility Study | Final FS was sent to Waiawa on 6/1/2021. Preparing responses to Developer's questions provided on 6/11/2021
IRS Amendment | [8 empty] | Estimated filing of IRS Amendment for Stage 2 projects (2Q/3Q 2021)
Transmission Line Approval | [8 empty] | Estimated filing of OH Line Approval for Stage 2 projects (2Q/3Q 2021)
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q3 2020 - Q2 2022) -- HRS 6E compliance to be completed Q2/Q3 2021
Permitting: Construction (Ministerial)
Procurement | [32 empty] | Assumes Procurement starts after Environmental and Land Use Permitting is complete
Construction | [20 empty] | Construction (Q4 2021 - Q2 2023)
Hawaiian Electric Work - Remote Engineering | [12 empty] | Remote Engineering (Q3 2021 - Q3 2022)
Hawaiian Electric Work - Remote Procurement | [32 empty] | Remote Procurement (Q1 2022 - Q1 2023)
Hawaiian Electric Work - Remote Construction | [81 empty] | Remote Construction (Q1 2023 - Q2 2023)
Acceptance Test | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Acceptance Test typically takes 30 business days
Energization | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Energization is a one time event
Commissioning | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [90 empty] | GCOD
Mahi Solar (Stage 2) - 2020-0140
Environmental Site Studies
Engineering and Design | Engineering (Q2 2021 - Q2 2022) -- Early Engineering Agreement executed 4/15/21
IRS System Impact Study | DONE
IRS Facility Study | Preliminary FS issued to Longroad 2/10/21; review completed; final FS to be completed July 2021
IRS Amendment | [8 empty] | Estimated filing of IRS Amendment for Stage 2 projects (2Q/3Q 2021)
Transmission Line Approval | [8 empty] | Estimated filing of OH Line Approval for Stage 2 projects (2Q/3Q 2021)
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q2 2020 - Q1 2022) -- C&CH Planning Commission to hear SUP on 6/23/21; Longroad planning for SUP approval by August 2021
Permitting: Construction (Ministerial) | [19 empty] | Estimated Construction Permitting starts
Procurement |  |  |  |  | Procurement (Q2 2021 - Q4 2022)
Construction | [32 empty] | Construction (Q1 2022 - Q2 2023)
Hawaiian Electric Work - Remote Engineering | Remote Engineering (Q2 2021 - Q1 2022)
Hawaiian Electric Work - Remote Procurement | [20 empty] | Remote Procurement (Q4 2021 - Q3 2022)
Hawaiian Electric Work - Remote Construction | [56 empty] | Remote Construction (Q3 2022 - Q4 2022)
Acceptance Test | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Acceptance Test typically takes 30 business days
Energization | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Energization is a one time event
Commissioning | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [92 empty] | GCOD
Barbers Point Solar
Kupono Solar*
NEPA Compliance JBPHH

## Permit Details Demo (hidden)
Permitting Agency | Permit or Approval | Required Studies | Status of Required Studies | Permit Number | Application Date or Status | Issuance Status | Permit or Approval Issuance or Target (ETA) Date | Developer | Developer Contact | Project Website | Project Size (ac) + Storage (ac) | Location | Tax Map Key(s) | Project Size (Gross Area in Acres) | County Zoning | State Land Use District(s) (Soil Types) | PUC Docket | PUC Term (Years) | Project Guaranteed Commercial Operations Date
Kupehau Solar | [7 empty] | 174 Power Global |  | Kupehau Solar | 60MW + 240MWh | Kunia | (1)9-2-004:008 | 254 | AG-1 | Agricultural (D, E) | 2020-0138 | 20 | 2022-05-31
PUC | 46kV Line Relocation Approval |  |  |  | Not Required | Will interconnect w/ Ho‘ohana Solar
LUC | Special Use Permit |  |  |  | Not Applicable | Not Applicable
DPP | Grading (Initial Road Construction) |  |  |  | Not Applicable | Not Applicable
DPP | Conditional Use Permit - Minor Amendment |  |  |  | Not Applicable | Not Applicable
DOH-CWB | NPDES (Initial Road Construction) |  |  |  | Not Applicable | Not Applicable
DLNR-SHPD | HRS 6E Compliance | Environmental and Cultural Studies (Biologic Survey and Archeological Inventory Survey) | Target Completion Q1 2021 |  |  |  | ETA Q3 2021
DPP | Conditional Use Permit - Minor |  | Biologic Survey and AIS Pending |  | Target submission June 2021 | Biologic Survey and AIS Pending | ETA September 2021
DPP | Zoning Waiver |  |  |  | Target submission June 2021 |  | ETA September 2021
DPP | Grading (Project Substation) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Grading (HECO Switchyard) |  |  |  | Target submission May 2021 |  | ETA October 2021
DOH-CWB | NPDES (Project Substation) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Building Permit (Project Substation) |  |  |  | Target submission May 2021 |  | ETA November 2021
DPP | Building Permit (HECO Switchyard) |  |  |  | Target submission May 2021 |  | ETA November 2021
DOH-CWB | NPDES (Solar and Battery Project) |  |  |  | Target submission December 2021 |  | ETA March 2022
DPP | Building Permit (Solar and Battery Project) |  |  |  | Target submission December 2021 |  | ETA March 2022
DPP | Grading (Solar and Battery Project) |  |  |  | Target submission December 2021 |  | ETA March 2022
DOT | Road Crossing Agreement |  |  |  | Target submission December 2021 |  | ETA August 2022
AES West O‘ahu Solar | [7 empty] | AES |  | AES West Oahu | 12.5MW + 50MWh | Makakilo | (1)9-2-002:007 | 97 | AG-1 | Agricultural (B,D,E) | 2019-0050 | 25 | 2022-09-07
DLNR-CWRM | Stream Channel Alteration Permit |  |  |  | Not Required | Not Required
DLNR-SHPD | HRS 6E Compliance | Archeological Inventory Study | Submitted to SHPD 2/6/20 | 19-07 | Approved | Approved
DPP, OEQC | HRS 343 Compliance (Environmental Assessment) |  |  |  | Accepted | Accepted | FEA accepted and filed on 07-08-20
PUC | Overhead Line Review |  |  |  |  | Approved 03/18/21
|  | Biological Resource Consultation |  |  | Completed | Completed
|  | Cultural Impact Assessment |  |  | Completed | Completed
DPP, LUC | Special Use Permit |  |  | 2020/SUP-6 SP21-411 |  | Planning Commission approved on 3/17/21 | ETA Q2 2021 (LUC approval)
DOH-CWB | NPDES | [5 empty] | ETA Q2 2021
DPP | Conditional Use Permit - Minor | [5 empty] | ETA Q3 2021
DPP | Zoning Waiver (if applicable) | [5 empty] | ETA Q3 2021
DOH-IRHB | Noise Permit | [5 empty] | ETA Q3 2021
DPP | Grading, Grubbing, and Stockpiling Permit | [5 empty] | ETA Q4 2021
DPP | Building and Electrical Permit | [5 empty] | ETA Q4 2021
Mililani I Solar | [7 empty] | Clearway |  |  | 39MW + 156MWh | Mililani | (1)9-4-005:090 (1)9-4-005:092 (1)9-4-005:096 (1)9-4-005:091 | 144 | AG-1 | Agricultural | 2018-0434 | 20 | 2022-11-01
DPP | Conditional Use Permit - Minor (Modification) | 2021/MOD-8 |  |  |  | Approved | 2021-03-04
DPP | Conditional Use Permit - Minor (Modification) | 2019/MOD-108 |  |  |  | Approved | 2020-01-23
DPP | Conditional Use Permit - Minor (Modification) | 2019/MOD-107 |  |  |  | Approved | 2020-01-23
DPP | Conditional Use Permit - Minor (Modification) | 2017/MOD-46 |  |  |  | Approved | 2017-07-06
DPP | Conditional Use Permit - Minor (Modification) | 2017/MOD-42 |  |  |  | Approved | 2017-07-06
DPP | Conditional Use Permit - Minor (Modification) | 2014/MOD-95 |  |  |  | Approved | 2014-10-03
DPP | Zoning Waiver | 2014/W-14 |  |  |  | Approved | 2014-07-29
DPP | Conditional Use Permit - Minor | 2014/CUP-23 |  |  |  | Approved | 2014-07-29
DPP | Conditional Use Permit - Minor (Joint Development) | 2010/CUP-10, Joint Development |  |  |  | Approved | 2010-05-07
DOH-CWB | NPDES |  |  |  |  | Approved | 2021-01-19
FAA | FAA Determination of No Hazard |  |  |  |  | Completed | Summer/Fall 2019
USACOE | Section 404 Clean Water Act - Nationwide Permit Program |  |  |  |  | Completed | Summer/Fall 2019
USFWS, DLNR-DOFAW | Biological Resource Consultation |  |  |  |  | Completed | Summer/Fall 2019
DPP | Grading and Grubbing Permit |  |  |  | Submitted Nov 2020 | Approved | 2021-03-12
DPP | Building Permit (PV Project) |  |  |  | Submitted Nov 2020 | Approved | 2021-03-12
DOH-CWB | Section 401 Water Quality Certification |  |  |  | Not Required | Not Required | N/A
USFWS | Section 7/10 Endangered Species Act Consultation |  |  |  | Not Required | Not Required | N/A
DPP | Building Permit (HECO Substation) |  |  |  | N/A | N/A | N/A
DPP | Building Permit (Project Substation) |  |  |  | Submitted | Pending | 2021-06-24
Waiawa Solar | [7 empty] | Clearway |  |  | 36MW + 144MWh | Pearl City | (1)9-6-004:024 | 200 | AG-1 | Urban | 2018-0435 | 20 | 2022-12-01
DOH-CWB | Section 401 Water Quality Certification |  |  |  | Not Required | Not Required | N/A
PUC | Overhead Line Review |  |  |  | Approved | Approved | 2021-03-01
USACOE | Section 404 Clean Water Act - Nationwide Permit Program |  |  |  | Not Required | Not Required | N/A
USFWS | Section 7/10 Endangered Species Act Consultation |  |  |  | Not Required | Not Required | N/A
FAA | FAA Determination of No Hazard |  |  |  |  | Completed | Summer/Fall 2019
USFWS, DLNR-DOFAW | Biological Resource Consultation |  |  |  |  | Completed | Summer/Fall 2019
DOH-CWB | NPDES |  |  |  | Approved | Approved | 2021-01-19
LUC | Motion to Amend for Urban Land Use |  |  |  | Approved | Approved | 2020-02-11
DPP | Zoning Waiver(s) |  |  | 2020/W-31 2021/W-8(CK) | Approved Approved | Approved Approved | August 13, 2020 March 15, 2021
DPP | Conditional Use Permit - Minor |  |  | 2020/CUP-2 | Approved | Approved | 2021-04-01
DPP | Conditional Use Permit - Minor Modification |  |  | 2021/MOD-23 | Approved | Approved | 2021-03-15
DPP | Grading and Grubbing Permit |  |  |  | Submitted November 2020 | Approved | 2021-04-06
DOT | Highway Permit |  |  |  | Submitted | Pending | Q2 2021
DPP | Building Permit (PV/BESS Project) |  |  |  | Submitted December 2020 | Pending | Q2 2021
DPP | Building Permit (Overhead Line) |  |  |  | Target Submission Q2 2021 | Pending | 2021-10-01
DPP | Building Permit (Project Substation) |  |  |  | Submitted February 23, 2021 | Pending | Q2 2021
AES Mountain View Solar | [7 empty] | AES |  | Mountain View Solar | 7MW + 35MWh | Wai‘anae | (1)8-5-003:031 (1)8-5-003:032 (1)8-5-019:034 | 100 | AG-1 | Agricultural (C,E) | 2020-0139 | 25 | 2023-05-17
PUC | Overhead Line Review
DLNR-SHPD | HRS 6E Compliance | Environmental and Cultural Studies (Biologic Survey and Archeological Inventory Survey) |  |  |  |  | ETA Q2-Q3 2021
DPP | Conditional Use Permit - Minor |  | Biologic Survey and AIS Pending |  |  |  | ETA Q4 2021-Q1 2022
DPP | Zoning Waiver (if applicable) | [5 empty] | ETA Q4 2021-Q1 2022
DOH-CWB | NPDES | [5 empty] | ETA Q4 2021-Q1 2022
DOH-IRHB | Noise Permit | [5 empty] | ETA Q4 2021-Q1 2022
DPP | Grading, Grubbing, and Stockpiling Permit | [5 empty] | ETA Q1-Q2 2022
DPP | Building and Electrical Permit | [5 empty] | ETA Q1-Q2 2022
Ho‘ohana Solar | [7 empty] | 174 Power Global, Hanwha |  |  | 52MW + 218MWh | Kunia | (1)9-4-002:052 | 160 | AG-1 | Urban | 2018-0431 | 20 | 2023-08-31
DPP | Conditional Use Permit - Minor |  |  | 2014/CUP-76 |  | Approved | 2015-01-01
DPP | Zoning Waiver |  |  | 2014/W-67 |  | Approved | 2015
DLNR-SHPD | HRS 6E Compliance | Archeological Inventory Study | Accepted 2/19/15 | LOG#2014.03535 LOG#2014.04974 Doc#1502SL23 |  | AIS accepted 2/19/15 | AIS accepted 2/19/15
DPP | Grading (Initial Road Construction) |  |  |  |  | Approved | 2019-12-01
DPP | Conditional Use Permit - Minor Modification |  |  | 2019/MOD-94 |  | Approved | 2019-10-18
DPP | Conditional Use Permit - Minor Modification |  |  | 2019/MOD-84 |  | Approved | 2019-10-19
DOH-CWB | NPDES (Initial Road Construction) |  |  |  |  | Approved | 2019-12-01
DPP | Zoning Waiver |  |  | 2020/W-27 |  | Approved | 2020-08-01
DPP | Conditional Use Permit - Minor Modification |  |  | 2020/MOD-38 |  | Approved | 2020-08-01
DPP, LUC | Special Use Permit - Amendment |  |  |  |  | Approved - Decision and Order pending | 2020-10-08
DOT | Road Crossing Agreement |  |  |  |  | Not Applicable
PUC | 46kV Line Relocation Approval |  |  |  |  | In Progress
DPP | Grading (Solar and Battery Project) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Grading (Project Substation) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Grading (HECO Switchyard) |  |  |  | Target submission May 2021 |  | ETA October 2021
DOH-CWB | NPDES (Solar and Battery Project) |  |  |  | Target submission May 2021 |  | ETA October 2021
DOH-CWB | NPDES (Project Substation) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Building Permit (Solar and Battery Project) |  |  |  | Target submission May 2021 |  | ETA November 2021
DPP | Building Permit (Project Substation) |  |  |  | Target submission May 2021 |  | ETA November 2021
DPP | Building Permit (HECO Switchyard) |  |  |  | Target submission May 2021 |  | ETA November 2021
Waiawa Phase 2 Solar | [7 empty] | AES |  | Waiawa Phase 2 Solar | 30MW + 240MWh | Waiawa | (1)9-6-004:024 (1)9-6-004:025 (1)9-6-004:026 (1)9-6-006:036 | 387 | Multiple Zones | Urban | 2020-0137 | 20 | 2023-10-30
PUC | Overhead Line Review |  |  |  |  | In Progress
DOH-US Navy | Zone of Influence Approval (if applicable) | [5 empty] | ETA Q2-Q3 2021
DLNR-SHPD | HRS 6E Compliance | Environmental and Cultural Studies (Biologic Survey and Archeological Inventory Survey) | AIS accepted April 2015 |  | HRS 6E compliance to START 12/18/20 | HRS 6E compliance to targeted to END 4/9/21 | ETA Q2-Q3 2021
LUC | LUC Amendment to Decision and Order | [5 empty] | ETA Q3-Q4 2021
DPP | Conditional Use Permit - Minor |  | Biologic Survey and AIS pending |  |  |  | ETA Q4 2021-Q1 2022
DPP | Conditional Use Permit - Minor (Joint Development) | [5 empty] | ETA Q4 2021-Q1 2022
DPP | Conditional Use Permit - Minor Modification | [5 empty] | ETA Q4 2021-Q1 2022
DPP | Zoning Waiver (if applicable) | [5 empty] | ETA Q4 2021-Q1 2022
DOH-CWB | NPDES | [5 empty] | ETA Q4 2021-Q1 2022
DOH-IRHB | Noise Permit | [5 empty] | ETA Q4 2021-Q1 2022
DPP | Grading, Grubbing, and Stockpiling Permit | [5 empty] | ETA Q1-Q2 2022
DPP | Building and Electrical Permit | [5 empty] | ETA Q1-Q2 2022
Mahi Solar | [7 empty] | Longroad Energy |  | Mahi Solar | 120MW + 480MWh | Kunia | (1)9-2-001:020 (1)9-2-004:012 (1)9-2-004:006 (1)9-2-004:003 (1)9-2-004:010 | 627 | AG-1 | Agricultural (B,C,D,E) | 2020-0140 | 25 | 2023-12-31
DOT | Permit to Cross Public Highway |  |  |  |  | Not Required
PUC | Overhead Line Review |  |  |  |  | In Progress
DPP, LUC | Special Use Permit |  |  | 2020/SUP-7 | Application submitted on 12/15/2020 | Application now being circulated for agency comments (due May 10).
DLNR-SHPD | HRS 6E Compliance (Plan Approval, Archeological Assessment) | Environmental Studies to be Completed in 2021 | Archeological Assessment to be Submitted Q2 2021 |  | Target submission Q2 2021 |  | Need SHPD Concurrence Letter by June 2021 before Planning Commission meeting on SUP
DPP | Zoning Waiver |  |  |  | Target submission August 2021 (after SUP Approval) |  | ETA September 2022
DPP | Conditional Use Permit - Minor |  |  | 2020/CUP-48 | Target submission August 2021 (after SUP Approval) |  | ETA September 2022
DPP | Conditional Use Permit - Minor Joint Development | [5 empty] | 2021-02-18
DPP | Building Permits |  |  |  | Target submission October 2021 |  | ETA March 2022
DPP | Grading Permit |  |  |  | Target submission October 2021 |  | ETA March 2022
DOH-CWB | NPDES | [5 empty] | ETA December 2021
DOH-IRHB | Noise Permit | [5 empty] | ETA December 2021
Grey = Permit or Approval is Not Needed or has Been Approved or Completed
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a column or way to indicate if a permit or approval is ministerial, discretionary, or unclear?