## Details
Program Docket | Project Docket | PUC Approved Project | Project Type | Stage | Island | Nameplate Capacity (MW) | Storage Capacity (MWh) | Estimated Utility RPS Percent Contribution | Developer | Delay Notes | Project or Task Update | Project or Task Update | Guaranteed Commercial Operations Date
O'ahu Utility-Scale Projects
2021-0024 | 2018-0434 | Mililani I Solar | Solar | Stage 1 | O'ahu | 39 | 156 | 1.2 | Clearway Energy Group |  | All Construction and Testing Activities Complete - Project Achieved Commercial Operations 7-31-22 |  | COD 7-31-22 |  |  |  | done
| 2018-0435 | Waiawa Solar | Solar | Stage 1 | O'ahu | 36 | 144 | 1.2 | Clearway Energy Group LLC; Global Infrastructure Partners |  | PPA - Amendment Approved 10-6-21 Engineering/Design - Finalized Permits and Land Rights - Complete and Secured Procurement and Delivery - All items delivered | Construction - Complete Hawaiian Telecom Circuit - Completed Testing • Oct-22: Acceptance Testing commenced 10-17-22 and passed 10-18-22. • 11-17-22: CSAT commenced (moved up from Feb-23). In final stages of testing, goal to complete before 12-31-22 | New GCOD 9-30-22 Operational 1-11-23 | no movement since last month. If acceptance testing was pushed up, how could this impact current COD? |  | prior to 12-31-22 | done
| 2020-0136 | Kapolei Energy Storage (KES) | BESS | Stage 2 | O'ahu | 185 | 565 | 0.1 | Plus Power | Delay Notes • Achieved COD 12-18-2023 | PPA - Complete • ESPPA amendment approved April 29, 2021, D&O 37754 • Amendment approved July 19, 2023 • 2nd amendment approved July 19, 2023 Engineering/Design - Complete • Final designs for Storage Facility, Substation, and COIF complete; HECO provided comments. • All final drawings (issued for construction) provided to Hawaiian Electric 11-1-22. Permits - Complete • DPP Permits for BESS, Substation Closed as of 8-17-23 • Grading Permit closed 9/28/2023 Land Rights - Complete | Procurement and Delivery - Complete • Replacement transformer was fully installed and operational in time for the Seller’s Capacity/RTE test on 8/7/2023 • March 2022. AMI meter for station power is still pending. The design was approved by the DPP and Meter has been released. Meter was installed on 8/15/2023. Construction - Complete Testing - Ongoing • Acceptance Testing Completed: 4-26-23 • TBD: CSAT anticipated (delayed). Seller expects to start the official CSAT testing by 12/01/2023 and achieve COD by 12/18/2023 | New GCOD 12-30-22 Operational 12-18-23 | no movement in COD |  | delayed 18 days since last month, permitting and equipment delays Delays in obtaining the Gentile Courtesy inspection resulted in the Gentile pole installation crew being unavailable until the week of 1/9/2023 - pushing out the COD by 13 days. PP is working with Moss/HMS to mitigate this delay to the greatest extent possible. | done
| 2019-0050 | AES West O‘ahu Solar | Solar & BESS | Stage 1 | O'ahu | 12.5 | 50 | 0.4 | AES West O‘ahu Solar, LLC. | Delay Notes • Achieved COD 3-28-2024 | PPA - Amendment Conditionally Approved 5-6-22 Engineering/Design - Complete Permits - Complete Land Rights - Complete | Procurement and Delivery - Complete Construction - Complete Testing - Ongoing | New GCOD 1-20-23 COD Achieved 3-28-24 | no movement in COD |  | no change in COD since prior month | done
| 2022-0007 | Kūpono Solar | PV Solar & BESS | Stage 2 | O'ahu | 42 | 168 | 0.85 | Bright Canyon Energy and Ameresco | Delay Notes • Commercial Operations Date recorded as June 7, 2024 | PPA - Amendment Submitted Overhead Line Approval - Complete Engineering and Design - Complete Permits - Complete | Procurement - Complete Land Rights - Secured Construction - Ongoing Testing - Pending | COD Achieved: 6-7-24 | no movement in COD |  | done | done
| 2020-0139 | Mountain View Solar | Solar & BESS | Stage 2 | O'ahu | 7 | 35 | 0.3 | AES Mountain View Solar, LLC. | Delay Notes • Completion of Project final IFC design & engineering, which continues to be delayed. Seller resubmitted 100% design to Company on September 17, 2024 for review, Company is reviewing. • Delayed delivery of substation equipment to site because of delayed IFC drawings. Switchgear and substation enclosure equipment will arrive mid-October 2024. • Seller’s expanded inverter testing and commissioning activities and updated schedule reflective of PPA durations. | PPA - Amendment Approved • The PUC approved the 2nd Amendment to the PPA on October 30, 2023. Engineering/Design - Ongoing • Step Up Substation & COIF: Seller working to incorporate comments and resubmit to company by August 30, 2024. System Impact Study - Ongoing • GFL PSCAD restudy was completed on 8/16/24. The GFM PSCAD and PSSE model updates are in progress Permits - Complete • HFD conducted a site inspection on 2/22/2024. HFD had no further comments or requests. Seller awaits issuance of the permit, expected September 2024 • Seller anticipating to extend the grading permit to account for delays in construction.. | Land Rights - Complete • Following commissioning, Seller will have COIF surveyed by a surveyor licensed in Hawaii and replace the existing blanket easement with the surveyed COIF easement to remain in place for the life of the Project. Procurement and Delivery - Ongoing • Substation package 99% delivered (est. Oct 2024), all other deliveries complete. Construction - Ongoing • Generation Facility - BESS module installation is complete. • COIF Pending Engineering IFC Set completion Testing - Pending • 2-24-25: Acceptance test scheduled to start. • 5-5-25: CSAT scheduled to start. | GCOD 5-17-24 Estimated COD 6-12-2025 | shifted 2 days - 12/26 to 12/28 | HICRIS 2022PR00486 | minor 5 day delay since prior month. COD in January 2024 | done
| 2020-0137 | Waiawa Phase 2 Solar | Solar & BESS | Stage 2 | O'ahu | 30 | 240 | 1.2 | Waiawa Phase 2 Solar, LLC. (AES) | Delay Notes • Delay in completion of Project design and engineering. AES resubmitted 100% set on September 17, 2024. Company is reviewing the 100% set of drawings. • Continued delays in the completion of the engineering designs are further delaying the COD. • Delivery of the Project COIF CTs/PTs completed September 16, 2024 • Completion of construction and the subsequent start of facility commissioning are contingent on their arrival. • Contractor and Seller tighten schedule around Seller testing and commissioning activities to bring COD in from February 2025 to January 2025. | PPA - Amendment Approved by PUC 8-1-2023. Engineering/Design - 90% • COIF / Step Up Substation - SOIF Designs Seller targeting complete package submission on 8/29. System Impact Study - Ongoing • GFM and GFL PSCAD model checkouts are in progress. Company provided feedback on PSSE and AES intends to update. Permits - Complete • Submitted to DPP on July 12, 2022. Special Assignment Inspection approval received April 13, 2023. Seller estimating permit issuance in September 2024. | Land Rights - Ongoing • Company received redlined easement agreement from landowner on May 1st, 2024. Company is working with Seller and Landowner to finalize easements. Est. (October 2024) Procurement and Delivery - Ongoing • IC Equipment anticipated October 2024. Construction - Ongoing • Generation Facility: BESS module installation 99% complete. Expected completion date in October 2024. • SOIF: Expected completion date December 2024. All of the foundations are laid. GSUs delivered to pads. O&M Shed delivered to pad. • COIF - Civil Work Only. Access road graded. Construction will not begin until final drawings are agreed to. Testing - Pending • Acceptance testing: March 2025 • CSAT: May 2025 | GCOD 9-1-2024 COD 6-4-25 | shifted 2 weeks
| 4 | Ho‘ohana Solar 1 | Solar & BESS | Stage 1 | O'ahu | 52 | 208 | 1.4 | 174 Power Global; (Hanwha Energy Corporation; Forest City Sustainable Resources) | Delay Notes • Delay due to issues that 174PG is currently addressing in its IRS restudy. • Study confirmed there is a voltage sag violation when the collector feeders are energized, and that mitigation is required. • Seller has offered potential solution on 8/21/24; Company is currently reviewing proposed solution. | PPA Amendment - Complete • The Company and Seller executed a PPA amendment on February 13, 2023 and filed the amendment with the Commission on February 17, 2023. The amendment was approved on May 30, 2023. Engineering/Design - Complete Permits - Complete • Final Permit Received 4/2/2024, Amended Building Permit for Solar/ Battery under review by DPP. System Impact Study - Ongoing • System Impact Study must be completed and all model deficiencies addressed prior to commencing Acceptance Test and commissioning activities. • Seller offered potential solution on 8/21/24; Company is awaiting diagrams supporting proposed solution. Seller can proceed with acceptance testing and comissioning activities | Procurement and Delivery - Complete Land Rights - Complete Construction - Ongoing • Gen facility: racking at 100% installed and PV at 100% installed. • SOIF - 100% Complete, COIF in local testing. Testing - Pending • Acceptance Test scheduled for 10-14-24 to 10-18-24 • CSAT scheduled for Oct-Nov, 2024. | GCOD 10-31-24 Estimated COD 11-29-24 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
2017-0352 | TBD | Pu'uloa Energy | Internal Combustion Engines (Biofuel) | Stage 3 | O‘ahu | 99 | - |  | Ameresco | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2027
| TBD | Pu'uloa Solar | Solar & BESS | Stage 3 | O‘ahu | 6 | TBD |  | Ameresco | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2026
| TBD | Base Proposal | Combustion Turbine (Biofuel) | Stage 3 | O‘ahu | 208 | - |  | Kalaeloa Partners LP | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2033
| TBD | Waiau Repower | Combustion Turbine (Biofuel) | Stage 3 | O‘ahu | 253 | - |  | Hawaiian Electric | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2033
| TBD | Mahi Solar & Storage | Solar & BESS | Stage 3 | O‘ahu | 120 | TBD |  | Longroad Development | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2027
| TBD | Makana La | Solar & BESS | Stage 3 | O‘ahu | 80 | TBD |  | Renew Development Holdco | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2037
| TBD | Par Hawai‘i Renewable Combined Heat & Power | Combined heat & power (biofuel) | Stage 3 | O‘ahu | 33.9 | - |  | Par Hawai‘i Refining | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2027
Maui Utility-Scale Projects
2021-0024 | 2018-0436 | AES Kuihelani Solar | Solar & BESS | Stage 1 | Maui | 60 | 240 | 1.9 | AES | Delay Notes • Commercial Operations Date recorded as May 31, 2024) | Overhead Line - Approved PPA amendment - Complete Engineering and Design - Complete Permits - Complete Land Rights - Complete | Procurement - Complete Construction - Complete Testing - Complete | COD Achieved: 5-31-24 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
| 2020-0132 | Waena Battery Energy Storage System (Reapproved by PUC with Conditions) | BESS | Stage 2 | Maui | 40 | 160 | 0.2 | Hawaiian Electric Company, Capital Improvement Project | Delay Notes • Letter sent to Commission to update pricing on May 20, 2024 • Decision and Order no. 40457 issued on December 22, 2023 approving project with conditions. Motion for Clarification letter sent on January 2, 2024 regarding conditions. • Order No. 40536 issued on January 22, 2024 granting Amendment to Attachment K, K‐1, and L of the Amended application and an extension, in part, for updated pricing from 90 days to 150 days. • RFP to be issued for updated pricing requested to be due on May 20, 2024 | Notes on Project Pause - Hawaiian Electric Self Build Project - Currently, the only work that is being done are activities related to the System Impact Study, Facility Study and responding to PUC information requests. Due to the pandemic-related global supply chain issues we were notified by our battery manufacturer that costs of the battery modules were to increase by 21% for the Waena BESS project. Global transportation has also become an issue which may mean delays for the project. All these concerns were provided to the PUC in the letter dated 12/3/21 |  | GCOD 11-30-2026 Estimated COD 11-30-2026 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
| 2018-0433 | Paeahu Solar | Solar & BESS | Stage 1 | Maui | 15 | 60 | 0.5 | Innergex Renewable Energy | Delay Notes • Project delays for re-approval process of CUP/H2 Permits led to mediation meetings, with a hearing concluding January 9, 2023. The Hearings Officer final report, along with the re-approval of the CUP/PH2 • Permit is currently delayed, pending updates from hearing officer. • Project requires PUC approval of the Overhead Line to proceed with project financing. • Projected has been delayed by FM Events requiring: Alternative Sourced PV BESS Inverter & potential delays due to BESS equipment supply shipping. • On September 29, 2023 & October 16, Company sent notice of missed construction financing milestones and assessment of daily delay damages. Company requested a new unit Price & GCOD. • Parties have met and are working diligently towards a new unit price and schedule. | Overhead Line Approval - Ongoing • On July 22, 2022, the Consumer Advocate filed a response to the Company’s July 8 Response to Order 38446, explaining it does not object to addressing Issue 3 of the proceeding at this time. • 5-23-22 Innergex provided letter to MECO, provided reasoning not all information is available to update the Interconnection Requirements Study (IRS). OH line approval should not be delayed pending execution of updated IRS Amendment. • Seller is anxiously awaiting a procedural schedule PPA amendments - Ongoing • If PUC Approval order Date Occurs 180 days after execution, the seller and HECO are entitled to an extension of the GCOD. • Paeahu PPA – PUC issued D&O No. 37340 on October 5, 2020 and 37553 on January 14, 2021 approving the project and denying a subsequent motion for reconsideration filed by Pono Power Coalition (“PPC”), respectively. • PPC filed a timely appeal to the Hawaii Supreme Court (“HSC”) related to the Paeahu PPA and procedural steps were completed throughout 2021. The HSC issued its Opinion of the Court on March 2, 2022 stating the PUC lawfully approved the PPA and affirmed the Approval Order and the Recon Order. The HSC entered judgment on April 1, 2022. • The Paeahu PPA notes if the PUC Approval Order Date occurs more than 180 days after the Execution date, the Seller and Company will be entitled to an extension of the Guaranteed Project Milestone Date. Parties agree that July 1, 2022 is the Effective Date of the PPA. Land Rights - ongoing Easement update required for overhead line extension, pending IFC of Seller transmission line, estimated Q4 2023 | Permits (Critical Path) - Ongoing • Noise permit was extended on July 18, 2022, and valid until July 13, 2023. • County Special Use Permit (CUP) - Approved 5-25-21, appealed by Pono Power Coalition, mediation was 5-3-22 to 5-27-22. A settlement was not reached and will proceed to a contested case, evidentiary hearing to commence 11-28-22. • Approvals at county level would not be granted until after the re-approval of the CUP/PH2 permit. The Hearing Officer final report is delayed and expected by end of Q3 2023. Engineering and Design - Ongoing • May-22: MECO pricing update identified the cost has more than doubled since May-2020 • 90% design complete step-up substation, generation facility, SOIF transmission line. Procurement -TBD • The Seller provided the Company with a BESS and PV inverter solution for the Hale Kuawehi Project on July 15, 2022. The Seller noted that the Paeahu solution will be very similar. The Seller anticipates design updates and preliminary system model updates. An interconnection restudy may be required. Construction - TBD Testing - TBD | Project Terminated | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
2017-0352 | TBD | Kuihelani Phase 2 Solar | Solar & BESS | Stage 3 | Maui | 40 | TBD |  | AES Corp. | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2027
| TBD | Puu Hao Solar | Solar & BESS | Stage 3 | Maui | 20 | TBD |  | AES Corp | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2027
| TBD | Kaheawa Wind 1 | Wind | Stage 3 | Maui | 30 | - |  | Terraform US | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2026
| TBD | Pūlehu Solar & Storage | Solar & BESS | Stage 3 | Maui | 20 | TBD |  | Longroad Energy | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2027
| TBD | Ukiu Energy | Internal Combustion (biofuel) | Stage 3 | Maui | 40 | TBD |  | Ameresco, Inc. | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2027
| 2021-0026 | Kamaole Solar | Solar & BESS | Stage 2 | Maui | 40 | 160 | 1.4 | Kamaole Solar LLC (Potential Renewables) | PPA Declared Null & Void March 2023 Due to Rising Costs | PPA Status • PPPA Declared Null and VOID Overhead Line Approval - Engineering and Design • Q3-22: remote work scheduled to start • 30% design complete for step up substation, 10% for COIF and COIF Transmission Line Land Rights Easement for COIF anticipated May 2023. | Permits • Nov-22: Anticipated approval date of SHPD approval letter. Archeological Inventory Survey ongoing, sites were larger than anticipated, impacting anticipated approval date and SUP and County permitting timelines (HRS) • Jun-22 : Estimated issue date of noise permit • Jan-23: Estimated approval date of EA exemption (HDOT, Maui County) • Jun-23: anticipated approval date of County Special Use Permit (slipped from Jan-23), as well as building permit • Jul-23: anticipated approval date of grading and grubbing and electrical permits Land Rights • May-23: estimated receipt of COIF/SOIF easement, impacted by delay in substation engineering Procurement and Delivery • All equipment dates pending resolutions to supply chain volatility • Orders placed for most equipment Sep-Nov-22, estimated arrival dates Q1-Q3 2023. Construction • Q2-23: generation facility and SOIF construction scheduled to start • Q3-23: COIF transmission line construction scheduled to start Testing • Sep-24: Acceptance test • Dec-24: CSAT | GCOD 8-31-23 Estimated COD 10-31-24 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
| Sum All Maui Projects |  |  |  | Maui | 245 | 380 | 2.1
Hawai'i Utility-Scale Projects
2021-0024 | 2018-0432 | Hale Kuawehi Solar | Solar & BESS | Stage 2 | Hawai'i | 30 | 120 | 0.8 | Innergex Renewable Energy Inc. | Delay Notes: • On February 9, 2024, Seller represented the Project is facing compounding delays due to workforce shortages, engineering redesigns and updates which required amendments to County permits. • Work is proceeding accordingly. | PPA Amendment - Complete Engineering & Design - Ongoing • All designs are complete, however typical and minor constructability updates may be required and are anticipated to be captured in final documentation. System Impact Study - Complete • On September 4, 2024, the Company identified issues, including the project’s response time in certain cases, discovered during the analysis of the supplemental report. The Company requested the Seller to review and resolve these matters. Permits - Tentatively Complete • All permits required to construct and operate the facility are in hand, Seller continues to work with the County to update designs as required. • The permit update, incorporating new details in the design package, will be resubmitted for County review by the end of September 2024. | Procurement and Delivery - Complete • All major procurement items have been received. The contractor has also indicated some materials have been noted as missing, possibly due to long term storage and handling. The Seller is working with the contractor to minimize procurement delays. Construction - Ongoing • Overall Project construction is 89% complete. • Overall Project commissioning is 10% complete. Testing - Pending / Delayed • Acceptance Testing estimated Start: November, 2024 • CSAT is expected to start February 26, 2025 | GCOD 10-11-24 COD 3-25-2025 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
| 2020-0127 | Keahole | BESS | Stage 2 | Hawai'i | 12 | 12 | N/A | Hawaiian Electric Company, Capital Improvement Project | Delay Notes • No change in status, but project schedule is still being impacted by: • Pending decision by the Commission on the amended application (submitted May 5, 2023) • Work is on hold and schedule to be re‐evaluated pending a PUC Approval Order for the Project | • Work is on hold and schedule to be re‐evaluated pending a PUC Approval Order for the Project | Decision and Order 39066 approved new Procedural schedule which ends in August 2023. Updated dates are based on the new procedural schedule. Amended application submitted to the Commission on May 5, 2023. | GCOD: 12-30-25 COD: 12-30-25
2017-0352 | TBD | Keamuku Solar | Solar & BESS | Solar & BESS | Hawai‘i | 86 | TBD |  | AES Corp. | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2030
| TBD | Puako Solar | Solar & BESS | Solar & BESS | Hawai‘i | 60 | TBD |  | Clearway Energy Group | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2028
| TBD | Kaiwiki Solar | Solar & BESS | Solar & BESS | Hawai‘i | 55 | TBD |  | Clearway Energy Group | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2028
| TBD | Hamakua Firm Energy | Combined Cycle (Biofuel) & BESS | Combined Cycle (Biofuel) & BESS | Hawai‘i | 60 | TBD |  | Pacific Current | Notes: RFP Awarded by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  |  | Estimated Completion: 2030
| Sum All Hawai'i Projects |  |  |  | Hawai'i | 42 | 132 | 0.8
Kaua'i Utility-Scale Projects
2020-0218 | 2020-0218 | West Kaua'I Energy Project | Solar, BESS, & Pumped Hydro | N/A | Kaua'i | 35 | 250+ | 22.7 | KIUC, AES | PPA Agreement Awaiting Commission Approval
| Sum All Kaua'i Projects |  |  |  |  | 35 | 0 | 22.7
Community-Based Renewable Energy (CBRE) - Shared Solar
2015-0389 | 2015-0389 | Palailai Solar 1 - Phase 1 |  | CBRE Phase 1 | O'ahu | 3 | 0 |  |  | Delay Notes: • COD Achieved October 10, 2023 | Engineering & Design - Complete Permits Complete Procurement - Complete | Construction - Complete Testing- Complete • Acceptance Test: Completed 8-24-23 • CSAT Test: Oct-23 CBRE Contract - Complete | New GCOD 1-27-23 *to be 7-28-23 Achieved: COD October 2023 | no movement since last month
| 2015-0389 | Ka Lae (solar) - formerly 'HLCBRE‐0003 Arion South Point' | Solar & BESS | CBRE Phase 1 | Hawai'i | 0.75 | 0 |  |  | Delay Notes: • Achieved COD on April1, 2024 | PPA • N/A Land rights Permits - Complete • All required permits for construction have been received from the Dept. of Public Works. Engineering/Design - Complete • Inverter change from Delta to Chint Power Systems inverters is required. Company confirmed Sellers's PCSAD model passed the check out on 01/16/24. | Procurement and Delivery - Complete Construction -Complete Testing | GCOD: 3-29-23 Achieved COD: 4-1-2024 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
| 2015-0389 | Kawela Plantation | Solar & BESS | CBRE Phase 1 | Moloka'i | 0.25 | 0 |  |  | Delay Notes: • Achieved COD on April1, 2024 | PPA - N/A Engineering/Design - Complete • Complete Overhead Line Approval - N/A | Permits - Complete Procurement and Delivery - Complete Construction - Complete Testing | GCOD: 10-19-2023 Achieved COD: 4-1-2024 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
| 2015-0389 | KHLS - Phase 1 |  | CBRE Phase 1 | O'ahu | 1.72 | 0 |  |  | Delay Notes: • Seller and Company executed a Letter Agreement to reinstate the KHLS CBRE Phase 1 project effective 03/26/2024. Commercial Operations deadline for the project is May 1, 2025 • Substantial Progress was not achieved by the Seller on 9/15/2023, and subsequently the project was terminated effective 09/17/2023 as noted in Termination Notice sent on 10/20/23. • Seller provided updated draft schedule on July 10th 2024 that has COD tracking later than Letter Agreement COD May 1st 2025, potentially to 4th Quarter 2025. Seller and Company working to verify schedule and determine drivers for COD change. Company provided additional comments on schedule on 7/26/24 for Seller review. | Engineering/Design • The 60% REV2 design review was completed by Company on 4/30/2024. The Seller is estimating to submit the 90% Design by Late August for Gen Facility, COIF, & Step-up Substation Permits • All permits approved. • The Building Permit for the facility was issued on 04/10/2024. Trenching Permit related to Facility Line Extension has been issued by DPP on 8/8/24. Land Rights • Seller is coordinating easements with HDOT, the City and County of Honolulu, and DHHL on the MV overhead route to the POI • Initial Survey Exhibit and Description completed on 7/28/24. Revised Description provided by Seller 8/21/24. Awaiting further review and comments on License Agreement by DHHL. | Procurement • All equipment received. • Company is working with Seller to finalize outstanding RFIs regarding remaining Company Owned Interconnection Facilities items that have not yet been procured. Construction • Substantial Progress Milestone confirmed to have been achieved on 03/01/2024. • Module installation completed, and Generating Facility wiring ongoing. Inverter installation completed. • Seller and Company are currently looking at impact revised schedule will have to construction related timelines. Company provided additional comments on schedule on 7/26/24 for Seller review. Testing • Acceptance Test Anticipated Q3 2025 • CSAT Test Anticipated Q4 2025 | GCOD 3-17-23 COD Q4 2025 | one month slip since last month

## Calendar
PUC Docket Number and Link | PUC Approved Project | Developer | Technology | Stage | Island | Nameplate Capacity (MW) | Estimated Utility RPS Percent Contribution | 2021-07-21 | 2021-09-21 | 2021-10-21 | 2021-11-21 | 2021-12-21 | 2021-01-22 | 2021-02-22 | 2021-03-22 | 2021-04-22 | 2021-05-22 | 2021-06-22 | July 2022 | Aug 2022 | Coal Plant Retirement 9-1-2022 | Storage Capacity (MWh) | Up to Oct, 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | June 2023 | July 2023 | August 2023 | Sept 2023 | Oct 2023 | Nov 2023 | 2023 | 2024 | 2024 (if delayed) | Jan 2025 | Feb 2025 | Mar 2025 | April 2025 | May 2025 | June 2025 | July 2025 | Aug 2025 | Sept 2025 | Oct 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Q3 / Q4 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034
2021-0024 | O'ahu Utility-Scale Projects
2018-0434 | Mililani I Solar (Stage 1) | Clearway Energy Group LLC; Global Infrastructure Partners |  |  |  | 39 | 1.2 | [11 empty] | Accelerated GCOD 7-31-22 PROJECT ENERGIZED!
2018-0435 | Waiawa Phase 1 Solar | Clearway Energy Group LLC; Global Infrastructure Partners |  | Stage 1 | O'ahu | 36 | 1.2 | [6 empty] | • Equipment delivery ongoing |  | • Shanghai shutdown impacting delivery of BESS components |  | Telecom poles building permit: Approved 6-28-22 |  |  |  | 0 | Accelerated GCOD 9-30-22 |  | Original COD 12-1-23 |  | Operational 1-11-23
2020-0136 | Kapolei Energy Storage (KES) | Plus Power | BESS | Stage 2 | O'ahu | 185 | 0.1 | [7 empty] | Mar-22: Grading permits received Site mobilization started |  | May-22 Building permits expected (DPP & AES) - Delayed |  |  |  |  | 565 |  |  |  | GCOD 12-30-22 | [11 empty] | Online December 2023
2019-0050 | AES West O‘ahu Solar | AES West O‘ahu Solar, LLC. | Solar & BESS | Stage 1 | O'ahu | 12.5 | 0.4 | [7 empty] | •Mar- 22: Noise Permit Received | • Apr-22: Grading Permit approved | • May-22: Building and Electrical Permit (DPP & AES) • May-22: Construction anticipated to start |  |  |  |  | 50 |  |  |  |  | New GCOD 1-20-23 | [11 empty] | COD Achieved Operations 3-28-24
2022-0007 | Kūpono Solar | Bright Canyon Energy and Ameresco | Solar & BESS | Stage 2 | O'ahu | 42 | 0.85 | [14 empty] | 168 | [16 empty] | GCOD 5-13-24 | COD Achieved Operations 6-7-24
2020-0139 | Mountain View Solar | AES Mountain View Solar, LLC. | Solar & BESS | Stage 2 | O'ahu | 7 | 0.3 | [14 empty] | 35 | [8 empty] | GCOD 5-17-23 | [7 empty] | GCOD 5-17-24 | [14 empty] | COD 6-12-25
2020-0137 | Waiawa Phase 2 Solar | Waiawa Phase 2 Solar, LLC. (AES) | Solar & BESS | Stage 2 | O'ahu | 30 | 1.2 | [14 empty] | 240 | [16 empty] | GCOD 9-1-24 | [14 empty] | COD 6-4-25
2018-0431 | Ho‘ohana Solar 1 | 174 Power Global; (Hanwha Energy Corporation; Forest City Sustainable Resources) | Solar & BESS | Stage 1 | O'ahu | 52 | 1.4 | [7 empty] | 3-15-22: Grading Permit & NPDES permit issued, Site Clearing began | [6 empty] | 208 | [16 empty] | GCOD 10-31-24 | COD 11-29-24
2017-0352 | Pu'uloa Energy | Ameresco | Internal Combustion Engines (Biofuel) | Stage 3 | O‘ahu | 99 | [15 empty] | - | [34 empty] | Estimated Completion
2017-0352 | Pu'uloa Solar | Ameresco | Solar & BESS | Stage 3 | O‘ahu | 6 | [15 empty] | TBD | [33 empty] | Estimated Completion
2017-0352 | Base Proposal | Kalaeloa Partners LP | Combustion Turbine (Biofuel) | Stage 3 | O‘ahu | 208 | [15 empty] | - | [40 empty] | Estimated Completion
2017-0352 | Waiau Repower | Hawaiian Electric | Combustion Turbine (Biofuel) | Stage 3 | O‘ahu | 253 | [15 empty] | - | [40 empty] | Estimated Completion
2017-0352 | Mahi Solar & Storage | Longroad Development | Solar & BESS | Stage 3 | O‘ahu | 120 | [15 empty] | TBD | [34 empty] | Estimated Completion
2017-0352 | Makana La | Renew Development Holdlco | Solar & BESS | Stage 3 | O‘ahu | 80 | [15 empty] | TBD | [34 empty] | Estimated Completion
2017-0352 | Par Hawai‘i Renewable Combined Heat & Power | Par Hawai‘i Refining | Combined heat & power (Biofuel) | Stage 3 | O‘ahu | 33.9 | [15 empty] | - | [34 empty] | Estimated Completion
2021-0024 | Maui Utility-Scale Projects
2018-0433 | AES Kuihelani Solar | AES | Solar & BESS | Stage 1 | Maui | 60 | [15 empty] | 240 | [13 empty] | Previous GCOD: 10-27-23 |  |  | GCOD: 5-31-24 | COD Achieved Operations 5-31-24
2021-0026 | Waena Battery Energy Storage System (Approved with Conditions) | Waena Battery Energy Storage System (Approved with Conditions) | Solar & BESS | Stage 2 | Maui | 40 | [15 empty] | 160 | [33 empty] | GCOD: 11-30-26
2020-0132 | Paeahu Solar | Innergex Renewable Energy | Solar & BESS | Stage 1 | Maui | 15 | [15 empty] | 60 | [7 empty] | Terminated
2018-0436 | Kamaole Solar | Kamaole Solar LLC (Potential Renewables) | Solar & BESS | Stage 2 | Maui | 40 | [15 empty] | 160 | [7 empty] | Original GCOD: 4-30-23 |  |  |  | New GCOD: 8-31-23 | [15 empty] | COD 10-31-24
2017-0352 | Kuihelani Phase 2 Solar | AES Corp. | Solar & BESS | Stage 3 | Maui | 40 | [15 empty] | TBD | [35 empty] | Estimated Completion
2017-0352 | Puu Hao Solar | AES Corp | Solar & BESS | Stage 3 | Maui | 20 | [15 empty] | TBD | [34 empty] | Estimated Completion
2017-0352 | Kaheawa Wind 1 | Terraform US | Wind | Stage 3 | Maui | 30 | [15 empty] | - | [33 empty] | Estimated Completion
2017-0352 | Pūlehu Solar & Storage | Longroad Energy | Solar & BESS | Stage 3 | Maui | 20 | [15 empty] | TBD | [34 empty] | Estimated Completion
2017-0352 | Ukiu Energy | Ameresco, Inc. | Internal Combustion (Biofuel) | Stage 3 | Maui | 40 | [15 empty] | TBD | [34 empty] | Estimated Completion
2021-0024 | Hawai'i Utility-Scale Projects
2018-0432 | Hale Kuawehi Solar | Innergex Renewable Energy Inc. | Solar & BESS | Stage 2 | Hawai'i | 30 | 120 | [14 empty] | 120 | [16 empty] | GCOD 10-11-24 | [11 empty] | COD 3-25-25
2020-0127 | Keahole BESS | Hawaiian Electric Company, Capital Improvement Project | Solar & BESS | Stage 2 | Hawai'i | 12 | 12 | [14 empty] | 12
2017-0352 | Keamuku Solar | AES Corp. | Solar & BESS | Stage 3 | Hawai‘i | 86 | [15 empty] | TBD | [37 empty] | Estimated Completion
2017-0352 | Puako Solar | Clearway Energy Group | Solar & BESS | Stage 3 | Hawai‘i | 60 | [15 empty] | TBD | [35 empty] | Estimated Completion
2017-0352 | Kaiwiki Solar | Clearway Energy Group | Solar & BESS | Stage 3 | Hawai‘i | 55 | [15 empty] | TBD | [35 empty] | Estimated Completion
2017-0352 | Hamakua Firm Energy | Pacific Current | Combined Cycle (Biofuel) & BESS | Stage 3 | Hawai‘i | 60 | [15 empty] | TBD | [37 empty] | Estimated Completion
2020-0218 | Kaua'i Utility-Scale Projects
2020-0218 | West Kaua'i Energy Project | KIUC, AES |  | N/A | Kaua'i | 35 | 120 | [14 empty] | 250+ | GCOD: TBD
2015-0389 | Community-Based Renewable Energy (CBRE) - Shared Solar
2015-0389 | Palailai Solar 1 |  |  | Phase 1 | O'ahu | 3 | [15 empty] | 0 |  | Original GCOD 10-29-22 |  |  | New Revised GCOD 1-27-23 | [8 empty] | COD Achieved 10-1-2023
2015-0389 | KHLS |  |  | Phase 1 | O'ahu | 1.72 | [15 empty] | 0 | [6 empty] | GCOD 3-17-23 | [8 empty] | GCOD 3-17-24 | [16 empty] | COD Q4 2025
2015-0389 | Ka Lae (solar) - formerly 'HLCBRE‐0003 Arion South Point' |  |  | Phase 1 | Hawai'i | 0.75 | [15 empty] | 0 | [9 empty] | GCOD: 6-1-23 | [6 empty] | GCOD: 4-1-2024
2015-0389 | Kawela Plantation |  |  | Phase 1 | Moloka'i | 0.25 | [15 empty] | 0 | [13 empty] | GCOD: 10-19-2023 |  |  | GCOD: 4-1-2024
| Phase 2 |  |  | Phase 2 | O'ahu | 105 capacity limit | TBD | [7 empty] | PUC Approved O‘ahu RFP Mar-22 Hawaiian Electric issued RFP Apr-22
2007-0323 | Energy Efficiency - Public Benefits Fund * |  |  |  |  | Estimated Energy Savings
| General Energy Efficiency Programs for Demand Side Management | Hawai‘i Energy |  |  |  | ~ 20 to 22 MW per year | N/A – Energy Efficiency | Ongoing
| Hawai‘i Energy Power Move Program | Hawai‘i Energy |  |  |  | ~2-3 MW per year | N/A – Energy Efficiency | [30 empty] | Application Deadline: 12-30-23
| Power Move Commercial Battery Storage Rebate Pilot | Hawai‘i Energy |  |  |  | ~ 4 MW see Battery Bonus Count | N/A – Energy Efficiency | [26 empty] | Installation by 8-31-23 |  |  |  |  | Application Deadline: 1-31-24
2018-0163 | Microgrid Services Tariff*
[6 empty] | TBD | TBD
2017-0352 | O‘ahu Grid Services RFP *
[6 empty] | 60 | TBD
2014-0135 | Green Infrastructure Loan Program- Green Energy Market Securitization (GEMS) *
TBD
2007-0341 | Demand Side Response - Grid Services Purchase Agreements *
[6 empty] | TBD | TBD

## Sheet1 (hidden)
Project | Guaranteed Commercial Operations Date
AES Kuihelani Solar (Stage 1) | GCOD 10-27-23
AES Waikoloa Solar | 12/26/22 COD (slipped from 11/3/2022)
Barber's Point Solar | Original GCOD 12-29-23 COD 5-2-24
Hale Kuawehi Solar | COD 5/5/23 (slipped from 4/28/23 and 12/2/22)
Ho‘ohana Solar 1 (Stage 1) | GCOD 8-31-23 Estimated COD 12-15-23
Kahana Solar (Stage 2) | Original GCOD: 12-29-23 Anticipated COD 4-17-24
Kamaole Solar (Stage 2) | Original GCOD 07-25-23 Anticipated COD 10-29-24
Kapolei Energy Storage (KES) (Stage 2) | New GCOD 12-30-22 Estimated COD 3-10-23
Keahole Battery Energy Storage | 1-23-24 (slipped from 12-28-23 and 11-28-23)
KHLS Phase 1 | GCOD 12-17-22 COD Aug-23
Kūpono Solar | GCOD 4-9-24
Mahi Solar (Stage 2) | Original GCOD 12-31-23 New Proposed GCOD 3-31-24 (GCOD in recent PPA under review by PUC)
Mililani I Solar (Stage 1) | New GCOD 7-31-22 Estimated COD 7-29-22
Mountain View Solar (Stage 2) | GCOD 5-17-23 Estimated COD 6-6-23
Paeahu Solar Stage 1 (docket suspended) | Suspension lifted 5-11-22 GCOD 4-28-23 COD 9-8-23
Palailai Solar 1 - Phase 1 | New GCOD 1-27-23 COD March 2023
Pulehu Solar (Stage 2) | COD now listed as 10-31-24 Proposed new GCOD 12-31-23 Original GCOD was 4-28-23
Waena Battery Energy Storage System (Awaiting Commission Approval) | 5-28-24 (slipped from 4-26-24, 3-29-24 and 2-29-24 and 1-29-24)
Waiawa Phase 2 Solar (Stage 2) | GCOD 10-30-23
Waiawa Solar (Stage 1) | New GCOD 9-30-22 Estimated COD 11-14-22 (COVID-19 lockdown in Shanghai, China delaying delivery of battery enclosures; could impact COD)
West O‘ahu Solar (Stage 1) | GCOD 9-7-22 Estimated COD 1-20-23 (Extended due to Force Majeure)

## Discretionary Permits Remain (hidden)
Discretionary Permit Outstanding
Project | Developer | State | City and County | Notes
West O‘ahu Solar | AES |  | N/A | not really a discretionary permit, but approval still needed
Mountain View Solar Stage 2 | AES | PUC overhead line review, IRS target 11-15 6e SHPD compliance | CUPminor, Zoning waiver (DPP) | status update states "if applicable" for zoning waiver- it is applicable
Waiawa Phase 2 Solar (Stage 2) | AES | 6e compliance, LUC ammendment | CUPm, Zoning waiver (DPP) | status update states "if applicable" for zoning waiver - it is applicable
Mahi Solar | Longroad Energy |  | CUPminor, Zoning Waiver (DPP)

## TF Project Permit Details (hidden)
Project | Permitting, Approving, or Accepting Agency | Permit or Approval | Discretionary or Ministerial | Application Date or Status | Issuance Status | Permit or Approval Issuance or Target (ETA) Date | Last Updated (HSEO ref)
AES West O‘ahu | AES West O‘ahu Solar (Stage 1) | [5 empty] | 2021-09-24
AES West O‘ahu | PUC | Overhead Line Review | Discretionary | Approved | Approved 3-18-21 | Approved 3-18-21
AES West O‘ahu | DLNR-SHPD | HRS 6E Compliance | Discretionary | Approved | Approved | 2021-01-04
AES West O‘ahu | DPP, OEQC | HRS 343 Compliance (Environmental Assessment) | Discretionary | Approved | Approved | FEA accepted and filed on 7-8-20
AES West O‘ahu | DOH-CWB | NPDES | Ministerial | Approved | Approved | 2021-03-31
AES West O‘ahu | AES West O‘ahu Solar | Special Use Permit | Discretionary | Approved | Approved | Complete 5-13-21, Final approval 6-10-21
AES West O‘ahu | DPP | Conditional Use Permit - Minor | Discretionary | Permit Application Filing milestone was met in August 2020 | Land Use Commission rescheduled hearing from May 26-27 to June 9; impacted ability to move forward with CUP (Minor). Working with DPP to accelerate DPP permits | 2021-08-12
AES West O‘ahu | DLNR - Land Court | Secure Land Rights | Ministerial | Estimate sending easement to land court mid August to early September |  | 2021-10-01
AES West O‘ahu | DOH-IRHB | Noise Permit | Ministerial | Permit Application Filing milestone was met in August 2020 |  | ETA Q3-Q4 2021
AES West O‘ahu | DPP | Grading, Grubbing, and Stockpiling Permit | Ministerial | Permit Application Filing milestone was met in August 2020 | Land Use Commission delayed hearing June 9 (approved); impacted ability to move forward with CUP (Minor). Working with DPP to accelerate DPP permits. | ETA Q4 2021
AES West O‘ahu | DPP | Building and Electrical Permit | Ministerial | Permit Application Filing milestone was met in August 2020 | Land Use Commission rescheduled hearing from May 26-27 to June 9; impacted ability to move forward with CUP (Minor). Working with DPP to accelerate DPP permits | ETA Q4 2021
Kupehau | Kupehau Solar (Stage 2) | [5 empty] | 2021-07-27
Mililani I | Mililani I Solar (Stage 1) | [5 empty] | 2021-07-29
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2021-03-04
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2020-01-23
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2020-01-23
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2017-07-06
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2017-07-06
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2014-10-03
Mililani I | DPP | Zoning Waiver | Ministerial | submitted | Approved | 2014-07-29
Mililani I | DPP | Conditional Use Permit - Minor | Discretionary | submitted | Approved | 2014-07-29
Mililani I | DPP | Conditional Use Permit - Minor (Joint Development) | Discretionary | submitted | Approved | 2010-05-07
Mililani I | DOH-CWB | NPDES | Ministerial | submitted | Approved | 2021-01-19
Mililani I | FAA | FAA Determination of No Hazard | Ministerial | submitted | Completed | Summer-Fall 2019
Mililani I | USACOE | Section 404 Clean Water Act - Nationwide Permit Program | Ministerial | submitted | Completed | Summer-Fall 2019
Mililani I | USFWS, DLNR-DOFAW | Biological Resource Consultation | Ministerial | submitted | Completed | Summer-Fall 2019
Mililani I | DPP | Grading and Grubbing Permit | Ministerial | Submitted Nov 2020 | Approved | 2021-03-12
Mililani I | DPP | Building Permit (PV Project) | Ministerial | Submitted Nov 2020 | Approved | 2021-03-12
Mililani I | DOH-CWB | Section 401 Water Quality Certification | Ministerial | Not Required | Not Required | N-A
Mililani I | USFWS | Section 7-10 Endangered Species Act Consultation | Ministerial | Not Required | Not Required | N-A
Mililani I | DPP | Building Permit (HECO Substation) | Ministerial | N-A | N-A | N-A
Mililani I | DPP | Building Permit (Project Substation) | Ministerial | Received courtesy inspection approval, anticipate full approval by end of July | Courtesy inspection approval received, Pending full approval (anticipated end of July) | 2021-07-30
Waiawa | Waiawa Solar (Stage 1) | [5 empty] | 2021-07-28
Waiawa | USACOE | Section 404 Clean Water Act - Nationwide Permit Program | Ministerial | Not Required | Not Required | N-A
Waiawa | USFWS | Section 7-10 Endangered Species Act Consultation | Ministerial | Not Required | Not Required | N-A
Waiawa | FAA | FAA Determination of No Hazard | Ministerial |  | Completed | Summer-Fall 2019
Waiawa | USFWS, DLNR-DOFAW | Biological Resource Consultation | Ministerial |  | Completed | Summer-Fall 2019
Waiawa | DOH-CWB | Section 401 Water Quality Certification | Ministerial | Not Required | Not Required | N-A
Waiawa | PUC | Overhead Line Review | Discretionary | Approved | Approved | March, 2021
Waiawa | DOH-CWB | NPDES- Construction | Ministerial | Approved | Approved | 2021-01-19
Waiawa | LUC | Motion to Amend for Urban Land Use | Discretionary | Approved | Approved | 2020-02-11
Waiawa | DPP | Zoning Waiver(s) | Discretionary | Approved Approved | Approved Approved | August 13, 2020 March 15, 2021
Waiawa | DPP | Conditional Use Permit - Minor | Discretionary | Approved | Approved | 2021-04-01
Waiawa | DPP | Conditional Use Permit - Minor Modification | Discretionary | Approved | Approved | 2021-03-15
Waiawa | DPP | Grading and Grubbing Permit | Ministerial | Approved | Approved | 2021-04-06
Waiawa | DPP | Building Permit (PV-BESS Project) | Ministerial | Approved | Q2 2021 | 2021-04-19
Waiawa | DPP | Building Permit (Project Substation) | Ministerial | Approved | Q2 2021 | Q2 2021
Waiawa | DOT | Highway Permit | Ministerial | Submitted | Pending | Q2 2021
Waiawa | DPP | Building Permit (Overhead Line) | Ministerial | Target Submission Q2 2021 | Pending | 2021-10-01
AES Mountain View | AES Mountain View Solar (Stage 2) | [5 empty] | 2021-07-28
AES Mountain View | PUC | Overhead Line Review | Discretionary |  | In progress
AES Mountain View | DLNR-SHPD | HRS 6E Compliance | Discretionary |  |  | ETA Q4 2021-Q1 2021
AES Mountain View | DPP | Conditional Use Permit - Minor | Discretionary |  |  | ETA Q4 2021-Q1 2022
AES Mountain View | DPP | Zoning Waiver (if applicable) | Ministerial |  |  | ETA Q4 2021-Q1 2022
AES Mountain View | DOH-CWB | NPDES | Ministerial |  |  | ETA Q1 2022-Q2 2022
AES Mountain View | DOH-IRHB | Noise Permit | Ministerial |  |  | ETA Q4 2021-Q1 2022
AES Mountain View | DPP | Grading, Grubbing, and Stockpiling Permit | Ministerial |  |  | ETA Q1-Q2 2022
AES Mountain View | DPP | Building and Electrical Permit | Ministerial |  |  | ETA Q1-Q2 2022
Ho‘ohana | Ho‘ohana Solar (Stage 1) | [5 empty] | 2021-07-28
Ho‘ohana | DPP | Conditional Use Permit - Minor | Discretionary |  | Approved | 2015-01-01
Ho‘ohana | DLNR-SHPD | HRS 6E Compliance | Discretionary |  | AIS accepted 2-19-15 | AIS accepted 2-19-15
Ho‘ohana | DPP | Grading (Initial Road Construction) | Ministerial |  | Approved | 2019-12-01
Ho‘ohana | DPP | Conditional Use Permit - Minor Modification | Discretionary |  | Approved | 2019-10-18
Ho‘ohana | DPP | Conditional Use Permit - Minor Modification | Discretionary |  | Approved | 2019-10-19
Ho‘ohana | DOH-CWB | NPDES (Initial Road Construction) | Ministerial |  | Approved | 2019-12-01
Ho‘ohana | DPP | Zoning Waiver | Ministerial |  | Approved | 2021-08-01
Ho‘ohana | DPP | Conditional Use Permit - Minor Modification | Discretionary |  | Approved | 2021-08-01
Ho‘ohana | DPP, LUC | Special Use Permit - Amendment- Restatement of State Land Use Boundary Amendment | Discretionary |  | Approved - Decision and Order pending | 2020-10-08
Ho‘ohana | DOT | Road Crossing Agreement | Ministerial |  | Not Applicable
Ho‘ohana | DPP | Building Permit (HECO Switchyard) | Ministerial | Not required per DPP guidance; requesting confirmatory letter from DPP |  | N-A
Ho‘ohana | PUC | 46kV Line Relocation Approval | Discretionary |  | In Progress
Ho‘ohana | DPP | Grading (Solar and Battery Project) | Ministerial | Target submission July 2021 |  | ETA October 2021
Ho‘ohana | DPP | Grading (Project Substation) | Ministerial | Submitted 5-12-2021 |  | ETA October 2021
Ho‘ohana | DPP | Grading (HECO Switchyard) | Ministerial | Initial submission 5-12-2021; some design work refinement continuing |  | ETA October 2021
Ho‘ohana | DOH-CWB | NPDES - Form C (Solar and Battery Project) | Ministerial | Initial submission 3-22-2021; some design work refinement continuing |  | ETA October 2021
Ho‘ohana | DOH-CWB | NPDES - Form C (Project Substation) | Ministerial | Initial submission 5-12-2021; some design work refinement continuing |  | ETA October 2021
Ho‘ohana | DPP | Building Permit (Solar and Battery Project) | Ministerial | Submit June 2021. Project design in progress |  | ETA November 2021
Ho‘ohana | DPP | Building Permit (Project Substation) | Ministerial | Submission 5-12-2021 |  | ETA November 2021
Waiawa | Waiawa Phase 2 Solar | [5 empty] | 2021-07-28
Waiawa | PUC | Overhead Line Review | Discretionary
Waiawa | DOH-US Navy | Zone of Influence Approval (if applicable) | Ministerial |  |  | ETA Q2-Q3 2021
Waiawa | DLNR-SHPD | HRS 6E Compliance | Ministerial | HRS 6E compliance to START 12-18-20 | HRS 6E compliance to targeted to END 4-9-21 | ETA Q2-Q3 2021
Waiawa | LUC | LUC Amendment to Decision and Order |  |  |  | ETA Q3-Q4 2021
Waiawa | DPP | Conditional Use Permit - Minor |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DPP | Conditional Use Permit - Minor (Joint Development) |  |  |  | ETA Q3 2021-Q4 2021
Waiawa | DPP | Conditional Use Permit - Minor Modification |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DPP | Zoning Waiver (if applicable) |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DOH-CWB | NPDES - Form C |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DOH-IRHB | Noise Permit |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DPP | Grading, Grubbing, and Stockpiling Permit |  |  |  | ETA Q1-Q2 2022
Waiawa | DPP | Building and Electrical Permit |  |  |  | ETA Q1-Q2 2022
| Mahi Solar | [5 empty] | 2021-09-10
Mahi | DOT | Permit to Cross Public Highway |  |  | Not Required
Mahi | PUC | Approval of PPA |  | Approved - 12-31-2020 | Approved | 2020-12-31
Mahi | PUC | Overhead Line Review |  | Application filed 4-6-21; stipulated procedural schedule filed on 6-21-21 | In Progress
Mahi | DPP, LUC | Special Use Permit |  | Application submitted on 12-15-2020; Revised and resubmitted March 2021. | Approved | 2021-09-09
Mahi | DLNR-SHPD | HRS 6E Compliance (Plan Approval, Archeological Assessment) |  | SHPD accepted the AIS with the proposed mitigation and monitoring measures. Significant traditional historic properties and wahi pana have been identified in the vicinity, including Pohakea Trail, ali‘i battle sites, a heiau atop Pu‘u Ku‘ua, and Honouliuli National Historic Site, among others. None of these significant historic properties were identified as extending into the Mahi Solar project area. However, two plantation-related sites abut or extend into the project area: the Waiāhole Ditch (Site 50-80-09-2268) and remnants of the Oʻahu Sugar Company Irrigation Infrastructure (Site 50-80-12-7346). The AIS report (Rechtman, September 2021) meets the requirements of HAR 13-276-5. It is accepted. Please submit one hard copy of the AIS, labeled Final, along with a text-searchable pdf copy of the AIS and a copy of this letter to the SHPD Kapolei office, attention Library. Please upload a text-searchable pdf copy of the Final AIS to HICRIS Project No. 2021PR00380 using the Project Supplement option, and a copy to Lehua.K.Soares@hawaii.gov. SHPD hereby notifies the DPP that SUP permit issuance process may continue with the understanding that an AMP meeting the requirements of HAR §13-279-4 prior to project initiation shall be submitted for SHPD review and acceptance prior to project initiation. | Determination received | 2021-09-08
Mahi | DPP | Zoning Waiver |  | Target submission August 2021 (after SUP Approval) |  | ETA 10-27-2021
Mahi | DPP | Conditional Use Permit - Minor for Utility Installation, Type B |  | Target submission August 2021 (after SUP Approval) |  | ETA 10-27-2021
Mahi | DPP | Conditional Use Permit - Minor Joint Development |  |  |  | 2021-02-18
Mahi | DPP | Building Permits |  | Target submission October 2021 |  | ETA February 2022
Mahi | DPP | Grading, Grubbing, Stockpiling Permit |  | Target submission October 2021 |  | ETA February 2022
Mahi | DOH-CWB | NPDES - Form C |  |  |  | ETA February 2022
Mahi | DOH-IRHB | Noise Permit |  |  |  | ETA December 2021
kes | Kapolei Energy Storage (Stage 2) | [5 empty] | 2021-07-29
kes | DPP | Conditional Use Permit - Minor |  | Approved - 10-29-2019 | Approved | Approved 10-28-20
kes | PUC | Overhead Line Review |  | Submitted 4-6-2021 | In progress
kes | DPP | Drainage Plan Approval
kes | DPP | Grading, Grubbing, Stockpiling Permit |  | Anticipated to file the application on 10-12-2021 to third party reviewer |  | Update: ETA 2-9-22, slipped from ETA 12-28-2021 (expected)
kes | DPP | Building and Electrical Permit |  | Anticipated to file the application on 11-12-2021 to third party reviewer |  | Update: 3-12-22, slipped from ETA 1-28-2022 (expected)
kes | DOH- CWB | NPDES - Form C |  | Anticipated to file the application to third party reviewer on 10-12-21 |  | Update: ETA 2-9-22, slipped from ETA 12-28-2021 (expected)
kes | DLNR-SHPD | HRS 6E Compliance |  | no longer on docket update (may need to follow-up).
kes | PUC | Overhead Line Review |  | Notice of approval sent on Sept. 15 2021 | Approved | Approved 09/15/2021
Barbers Point Solar (PPA Not Yet Approved by PUC)
| DHHL | HRS 343 EA |  |  | In progress, pre-assessment consultation
| DOT-HWY | Permit to Perform Work Upon State Highway
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I changed this, since some of these are not "permitting" agencies, but are aproving entities - I think it is a difference worth distinguising to help stakeholders understand different roles.
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a column or way to indicate if a permit or approval is ministerial, discretionary, or unclear?
Note on C49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: do you know if this is the permit to perfom work, or is this for application for occupancy and use? both? I am guessing it is for work?
Note on E71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: do they have a confirmatory letter?

## Permit References and Timelines (hidden)
Jurisdiction | Permitting / Approving Agency | Permit or Approval | Resources |  | Type | Common Rank (1 most common - 5 less common) | Typical Timeline (days) | https://energy.hawaii.gov/renewable-energy-project-permitting-in-the-state-of-Hawai‘i
County | DPP | Conditional Use Permit - Minor | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/ReportsNotices/MonthlyBulletins.aspx | Discretionary | 1 | 45
County | DPP | Grading Permit | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/ReportsNotices/MonthlyBulletins.aspx | Ministerial | 1
County | DPP | Zoning Waiver | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/Calendar.aspx | Ministerial | 1 | 30-90 days | https://energy.hawaii.gov/wp-content/uploads/2015/07/Oahu-Waiver-Permit_March-2015.pdf
County | DPP | Grubbing Permit | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/ReportsNotices/MonthlyBulletins.aspx | Ministerial | 1
County | DPP | Building Permit Project | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/ReportsNotices/MonthlyBulletins.aspx | Ministerial | 1
State | DOH-CWB | NPDES (Initial Road Construction) | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 1
Steate | DOH-CWB | NPDES (Construction) | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 1
State | DOH-CWB | NPDES (Solar and Battery Project) | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 1
State | DOH-IRHB | Noise Permit | ask developer |  | Ministerial | 1
State | LUC (State) | Special Use Permit (Projects >15 acres, LUC makes final decision). | https://luc.hawaii.gov/ |  | Discretionary | 1
County | Planning Commission (County) | Special Use Permit (Projects >15 acres, LUC makes final decision). | https://www.honolulu.gov/dpppd/default.html |  | Discretionary
County | DPP | Trenching Permit | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx |  | Ministerial | 2
State | DOT-HWY | Permit Application to Perform Work Upon State Highways |  |  | Ministerial | 2 | 5-10 days
State | DOT-HWY | Application & Permit for the Occupancy & Use of State Highway Right-of-Way |  |  | Ministerial | 2 | 5-10 days
State | DOH-CWB | NPDES Dewatering | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 2
County | DPP | Conditional Use Permit - Major | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx |  | Discretionary | 3 | 90
Federal | USACOE | Section 404 Clean Water Act - Nationwide Permit Program |  |  | Ministerial | 3
State | DLNR - OCCL | Conservation District Use Permit | https://dlnr.hawaii.gov/occl/current-applications/ |  | Discretionary | 3
State | DBEDT - OP | CZMA Fed Consistency |  |  | Ministerial | 3
State | LUC | District Boundary Amendment | https://luc.hawaii.gov/calendar/ luc.hawaii.gov -> then hit pending dockets -> boundary amendments |  | Discretionary | 3 | 365
Federal | USACE | CWA Section 404 Permit - Individual |  |  | Discretionary | 4
State | DPP | SMA - major | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/Calendar.aspx | Discretionary | 5 | 180
Federal | USACE | Section 9 |  |  | Discretionary | 5
State | PUC | 46kV Line Relocation Approval |  |  | Discretionary - PUC | 1
State | SHPD | HRS 6E, Historic Preservation | https://dlnr.hawaii.gov/shpd/intake-and-determinations/ | see determinations reports | Discretionary | 1
Federal | USFWS | Section 7/10 Endangered Species Act Consultation |  |  | Ministerial | 2
Federal | FAA | FAA Determination of No Hazard |  |  | Ministerial | 2
State | Varies - Accepting Agency | HRS 343 EA | http://oeqc2.doh.hawaii.gov/_layouts/15/start.aspx#/Doc_Library/ |  | Discretionary | 3
State | DOH CWB | CWA Section 401 WQ Certification | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 3
State | DLNR - CWRM | Stream channel Alteration |  |  | Discretionary | 4
State / County | DLNR - CWRM | Stream Diversion |  |  | Discretionary | 4
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I changed this, since some of these are not "permitting" agencies, but are aproving entities - I think it is a difference worth distinguising to help stakeholders understand different roles.
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a column or way to indicate if a permit or approval is ministerial, discretionary, or unclear?

## TMKs (hidden)
Project * | Tax Map Key(s)
AES Mountain View Solar | 185003031; 185003032; 185019034
AES West Oahu Solar Plus Storage | 192002007
Hoohana Solar 1 | 194002052
Kapolei Energy Storage | 191014042
Mahi Solar | 192001001; 192004012; 192004006; 192004003; 192004010
Mililani I Solar | 194005090; 194005092; 194005096; 194005091
Waiawa Phase 2 Solar | 196004024; 196004025; 196004026; 196006036
Waiawa Solar Power | 196004024

## zzz_TF Master Schedule (hidden)
| 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-11-21 | 2021-11-21 | 2021-11-21 | 2021-11-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-02-22 | 2022-02-22 | 2022-02-22 | 2022-02-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-04-22 | 2022-04-22 | 2022-04-22 | 2022-04-22 | 2022-05-22 | 2022-05-22 | 2022-05-22 | 2022-05-22 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | Coal | 2022-09-01 | 2022-09-01 | 2022-09-01 | 2022-09-01 | 2022-10-22 | 2022-10-22 | 2022-10-22 | 2022-10-22 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2023-01-23 | 2023-02-23 | 2023-03-23 | 2023-04-23 | 2023-05-23 | 2023-06-23 | 2023-07-23 | 2023-08-23 | 2023-09-23 | 2023-10-23 | 2023-11-23 | 2023-12-23
AES West O‘ahu Solar (Stage 1) - 2019-0050 | [64 empty] | Plant | GCOD
Environmental Site Studies | DONE | [63 empty] | Shut
Engineering and Design | Engineering (Q3 2020 - Q3 2021); Engineering at 100% design phase | [63 empty] | Down
IRS System Impact Study | DONE
IRS Facility Study | DONE
IRS Amendment | DONE
Transmission Line Approval | DONE
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q3 2020 - Q4 2021) -- LUC hearing on SUP 6/9-6/10; CUP expected Q3 2021
Permitting: Construction (Ministerial) | Permitting (Q3 2020 - Q4 2021)
Procurement | Procurement (Q1 2021 - Q4 2021)
Construction | [20 empty] | Construction (Q4 2021 - Q2 2022)
Hawaiian Electric Work | Hawaiian Electric Work (Q4 2020 - Q2 2022) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [32 empty] | Testing and Commissioning (Q1 2022 - Q3 2022) -- Acceptance Test typically takes 30 business days
Energization | [32 empty] | Testing and Commissioning (Q1 2022 - Q3 2022) -- Energization is a one time event
Commissioning | [32 empty] | Testing and Commissioning (Q1 2022 - Q3 2022) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [32 empty] | Testing and Commissioning (Q1 2022 - Q3 2022) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [65 empty] | GCOD
Mililani I Solar (Stage 1) - 2018-0434 | [73 empty] | GCOD
Environmental Site Studies | DONE
Engineering and Design | Engineering (Q2 2020 - Q3 2021) -- HECO reviewed 90% design; Issued for Construction (IFC); 60% design for substation
IRS System Impact Study | DONE
IRS Facility Study | DONE
IRS Amendment | DONE
Transmission Line Approval | DONE
Permitting: Environmental and Land Use (Discretionary) | DONE
Permitting: Construction (Ministerial) | Permitting (Q4 2020 - Q2 2021) -- final Building Permit (substation) expected June 2021
Procurement | Procurement (Q3 2020 - Q3 2021)
Construction | Construction (Q1 2021 - Q1 2022) -- groundbreaking ceremony April 2021; construction expected May 2021
Hawaiian Electric Work | Hawaiian Electric Work (Q4 2020 - Q4 2021) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [32 empty] | Testing and Commissioning (Q1 2022 - Q4 2022) -- Acceptance Test typically takes 30 business days
Energization | [32 empty] | Testing and Commissioning (Q1 2022 - Q4 2022) -- Energization is a one time event
Commissioning | [32 empty] | Testing and Commissioning (Q1 2022 - Q4 2022) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [32 empty] | Testing and Commissioning (Q1 2022 - Q4 2022) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [57 empty] | Potential GCOD 7/31/22 | [15 empty] | GCOD
Waiawa Solar (Stage 1) - 2018-0435 | [77 empty] | GCOD
Environmental Site Studies | DONE
Engineering and Design | Engineering (Q4 2020 - Q3 2021) -- HECO reviewed 90% substation design; 60% gen-tie design; 90% design under development
IRS System Impact Study | DONE
IRS Facility Study | DONE
IRS Amendment | DONE
Transmission Line Approval | DONE
Permitting: Environmental and Land Use (Discretionary) | DONE
Permitting: Construction (Ministerial) | Permitting (Q4 2020 - Q3 2021) -- substation Building Permit expected July 2021; 46kV OH line Building Permit expected October 2021
Procurement | Procurement (Q3 2020 - 4 2021)
Construction | Construction (Q1 2021 - Q2 2022) -- groundbreaking ceremony April 2021; construction expected May 2021
Hawaiian Electric Work | Hawaiian Electric Work (Q4 2020 - Q4 2021) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [44 empty] | Testing and Commissioning (Q2 2022 - Q4 2022) -- Acceptance Test typically takes 30 business days
Energization | [44 empty] | Testing and Commissioning (Q2 2022 - Q4 2022) -- Energization is a one time event
Commissioning | [44 empty] | Testing and Commissioning (Q2 2022 - Q4 2022) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [44 empty] | Testing and Commissioning (Q2 2022 - Q4 2022) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [63 empty] | Potential GCOD 8/31/22 | [13 empty] | GCOD
Kapolei Energy Storage (Stage 2) - 2020-0136 | [69 empty] | New GCOD - early battery delivery | [10 empty] | New GCOD - NO early battery delivery
Environmental Site Studies
Engineering and Design | Early Engineering Letter Agreement executed; HE reviewed 30% design
IRS System Impact Study | DONE
IRS Facility Study | Revised FS completed May 2021, however, revisions are likely due to KES's new proposed schedule
IRS Amendment | IRS Amendment process scheduled from late May to July 2021
Transmission Line Approval | Application for 138kV OH line filed 4/6/21
Permitting: Environmental and Land Use (Discretionary) | DONE -- KES plans to secure land rights by June 2021
Permitting: Construction (Ministerial) | [16 empty] | Construction Permitting (9/15/21 - 1/7/22)
Procurement | Procurement (3/16/21 - 6/10/22)
Construction | Construction (October 2020 - July 2022)
Hawaiian Electric Work | Hawaiian Electric Work (September 2019 - July 2022)
Acceptance Test | [57 empty] | Acceptance Testing
Control System Acceptance Test | [65 empty] | CSAT
Commercial Operations | [52 empty] | Original GCOD | [16 empty] | New GCOD - early battery delivery | [10 empty] | New GCOD - NO early battery delivery
AES Mountain View Solar (Stage 2) - 2020-0139
Environmental Site Studies |  | Virtual Public Meeting on 5/19
Engineering and Design | Engineering (Q2 2021 - Q2 2022) -- to stay on schedule Early Engineering Agreement must be executed no later than June 2021; AES and HE are discussing Early Engineering (May 2021 Status Report)
IRS System Impact Study | Anticipated to be completed May 2021
IRS Facility Study | Exchanged comments May 2021
IRS Amendment | [8 empty] | Estimated filing of IRS Amendment for Stage 2 projects (2Q/3Q 2021)
Transmission Line Approval | [8 empty] | Estimated filing of OH Line Approval for Stage 2 projects (2Q/3Q 2021)
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q3 2021 - Q2 2022) -- HRS 6E compliance to be completed Q2/Q3 2021; Environmental and Land Use Permitting to be completed by Q1 2022 (May 2021 Status Update)
Permitting: Construction (Ministerial)
Procurement | [8 empty] | Procurement (Q3 2021 - Q2 2022)
Construction | [44 empty] | Construction (Q2 2022 - Q1 2023)
Hawaiian Electric Work - Remote Engineering | [8 empty] | Remote Engineering (Q3 2021 - Q1 2022)
Hawaiian Electric Work - Remote Procurement | [20 empty] | Remote Procurement (Q4 2021 - Q3 2022)
Hawaiian Electric Work - Remote Construction | [56 empty] | Remote Construction (Q3 2022)
Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q2 2023) -- Acceptance Test typically takes 30 business days
Energization | [81 empty] | Testing and Commissioning (Q1 2023 - Q2 2023) -- Energization is a one time event
Commissioning | [81 empty] | Testing and Commissioning (Q1 2023 - Q2 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q2 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [85 empty] | GCOD
Kupehau Solar (Stage 2) - 2020-0138
Environmental Site Studies
Engineering and Design | Engineering (Q2 2020 - Q3 2022) -- Early Engineering Agreement executed; HECO reviewed 30% design
IRS System Impact Study | Anticipated SIS completion date May 2021
IRS Facility Study | Preliminary FS under review by 174PG
IRS Amendment | Anticipated IRS Amendment completion date is confidential (HECO 3/15/21 IR Response)
Transmission Line Approval | To be included with Ho‘ohana Solar 1
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q1 2020 - Q2 2022) -- Environmental and Land Use Permit to be completed March 2022 (May 2021 Status Update)
Permitting: Construction (Ministerial) | Permitting (Q1 2020 - Q2 2022) -- Construction Permitting to be completed May 2022 (May 2021 Status Update)
Procurement | Procurement (Q2 2020 - Q3 2022)
Construction | [32 empty] | Construction (Q1 2022 - Q1 2023)
Hawaiian Electric Work | Hawaiian Electric Work (Q1 2021 - Q1 2023) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Acceptance Test typically takes 30 business days
Energization | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Energization is a one time event
Commissioning | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [87 empty] | New estimated GCOD (7/1/23)
Ho‘ohana Solar 1 (Stage 1) - 2018-0431
Environmental Site Studies | DONE
Engineering and Design | Engineering (Q2 2020 - Q1 2022) -- 60% switchyard design due to HECO 6/3/21; 90% switchyard design due to HECO 10/6/21
IRS System Impact Study | SIS re-study expected to be completed May 2021
IRS Facility Study | DONE
IRS Amendment | DONE
Transmission Line Approval | Application for 138kV Kahe-Hālawa OH line filed 2/26/21; application for 138kV Kahe-Waiau UG line to be filed June 2021; filing for 46kV Wai‘au-Mililani UG/OH line relocation to be filed June 2021
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q1 2020 -Q1 2022) -- CUP-M modification and Zoning Waiver to be submitted June 2021
Permitting: Construction (Ministerial) | Permitting (Q1 2020 -Q1 2022) -- final Building Permit (solar/battery) to be submitted June 2021
Procurement | Procurement (Q2 2021 - Q3 2022)
Construction | [32 empty] | Construction (Q1 2022 - Q1 2023)
Hawaiian Electric Work | Hawaiian Electric Work (Q2 2021 - Q4 2022) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Acceptance Test typically takes 30 business days
Energization | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Energization is a one time event
Commissioning | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [88 empty] | GCOD
Waiawa Phase 2 Solar (Stage 2) - 2020-0137
Environmental Site Studies
Engineering and Design |  |  |  |  | Engineering (Q1 2021 - Q2 2022) -- Engineering and Design must start June 2021 to stay on schedule; AES and HE are discussing Early Engineering; Waiawa Solar (stage 1 ) line runs through Waiawa Phase 2 site; potential delays to GCOD if Wahiawa substation work is not completed on-time (May 2021 Status Report)
IRS System Impact Study | DONE
IRS Facility Study | Final FS was sent to Waiawa on 6/1/2021. Preparing responses to Developer's questions provided on 6/11/2021
IRS Amendment | [8 empty] | Estimated filing of IRS Amendment for Stage 2 projects (2Q/3Q 2021)
Transmission Line Approval | [8 empty] | Estimated filing of OH Line Approval for Stage 2 projects (2Q/3Q 2021)
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q3 2020 - Q2 2022) -- HRS 6E compliance to be completed Q2/Q3 2021
Permitting: Construction (Ministerial)
Procurement | [32 empty] | Assumes Procurement starts after Environmental and Land Use Permitting is complete
Construction | [20 empty] | Construction (Q4 2021 - Q2 2023)
Hawaiian Electric Work - Remote Engineering | [12 empty] | Remote Engineering (Q3 2021 - Q3 2022)
Hawaiian Electric Work - Remote Procurement | [32 empty] | Remote Procurement (Q1 2022 - Q1 2023)
Hawaiian Electric Work - Remote Construction | [81 empty] | Remote Construction (Q1 2023 - Q2 2023)
Acceptance Test | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Acceptance Test typically takes 30 business days
Energization | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Energization is a one time event
Commissioning | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [90 empty] | GCOD
Mahi Solar (Stage 2) - 2020-0140
Environmental Site Studies
Engineering and Design | Engineering (Q2 2021 - Q2 2022) -- Early Engineering Agreement executed 4/15/21
IRS System Impact Study | DONE
IRS Facility Study | Preliminary FS issued to Longroad 2/10/21; review completed; final FS to be completed July 2021
IRS Amendment | [8 empty] | Estimated filing of IRS Amendment for Stage 2 projects (2Q/3Q 2021)
Transmission Line Approval | [8 empty] | Estimated filing of OH Line Approval for Stage 2 projects (2Q/3Q 2021)
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q2 2020 - Q1 2022) -- C&CH Planning Commission to hear SUP on 6/23/21; Longroad planning for SUP approval by August 2021
Permitting: Construction (Ministerial) | [19 empty] | Estimated Construction Permitting starts
Procurement |  |  |  |  | Procurement (Q2 2021 - Q4 2022)
Construction | [32 empty] | Construction (Q1 2022 - Q2 2023)
Hawaiian Electric Work - Remote Engineering | Remote Engineering (Q2 2021 - Q1 2022)
Hawaiian Electric Work - Remote Procurement | [20 empty] | Remote Procurement (Q4 2021 - Q3 2022)
Hawaiian Electric Work - Remote Construction | [56 empty] | Remote Construction (Q3 2022 - Q4 2022)
Acceptance Test | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Acceptance Test typically takes 30 business days
Energization | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Energization is a one time event
Commissioning | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [92 empty] | GCOD
Barbers Point Solar
Kupono Solar*
NEPA Compliance JBPHH

## Permit Details Demo (hidden)
Permitting Agency | Permit or Approval | Required Studies | Status of Required Studies | Permit Number | Application Date or Status | Issuance Status | Permit or Approval Issuance or Target (ETA) Date | Developer | Developer Contact | Project Website | Project Size (ac) + Storage (ac) | Location | Tax Map Key(s) | Project Size (Gross Area in Acres) | County Zoning | State Land Use District(s) (Soil Types) | PUC Docket | PUC Term (Years) | Project Guaranteed Commercial Operations Date
Kupehau Solar | [7 empty] | 174 Power Global |  | Kupehau Solar | 60MW + 240MWh | Kunia | (1)9-2-004:008 | 254 | AG-1 | Agricultural (D, E) | 2020-0138 | 20 | 2022-05-31
PUC | 46kV Line Relocation Approval |  |  |  | Not Required | Will interconnect w/ Ho‘ohana Solar
LUC | Special Use Permit |  |  |  | Not Applicable | Not Applicable
DPP | Grading (Initial Road Construction) |  |  |  | Not Applicable | Not Applicable
DPP | Conditional Use Permit - Minor Amendment |  |  |  | Not Applicable | Not Applicable
DOH-CWB | NPDES (Initial Road Construction) |  |  |  | Not Applicable | Not Applicable
DLNR-SHPD | HRS 6E Compliance | Environmental and Cultural Studies (Biologic Survey and Archeological Inventory Survey) | Target Completion Q1 2021 |  |  |  | ETA Q3 2021
DPP | Conditional Use Permit - Minor |  | Biologic Survey and AIS Pending |  | Target submission June 2021 | Biologic Survey and AIS Pending | ETA September 2021
DPP | Zoning Waiver |  |  |  | Target submission June 2021 |  | ETA September 2021
DPP | Grading (Project Substation) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Grading (HECO Switchyard) |  |  |  | Target submission May 2021 |  | ETA October 2021
DOH-CWB | NPDES (Project Substation) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Building Permit (Project Substation) |  |  |  | Target submission May 2021 |  | ETA November 2021
DPP | Building Permit (HECO Switchyard) |  |  |  | Target submission May 2021 |  | ETA November 2021
DOH-CWB | NPDES (Solar and Battery Project) |  |  |  | Target submission December 2021 |  | ETA March 2022
DPP | Building Permit (Solar and Battery Project) |  |  |  | Target submission December 2021 |  | ETA March 2022
DPP | Grading (Solar and Battery Project) |  |  |  | Target submission December 2021 |  | ETA March 2022
DOT | Road Crossing Agreement |  |  |  | Target submission December 2021 |  | ETA August 2022
AES West O‘ahu Solar | [7 empty] | AES |  | AES West Oahu | 12.5MW + 50MWh | Makakilo | (1)9-2-002:007 | 97 | AG-1 | Agricultural (B,D,E) | 2019-0050 | 25 | 2022-09-07
DLNR-CWRM | Stream Channel Alteration Permit |  |  |  | Not Required | Not Required
DLNR-SHPD | HRS 6E Compliance | Archeological Inventory Study | Submitted to SHPD 2/6/20 | 19-07 | Approved | Approved
DPP, OEQC | HRS 343 Compliance (Environmental Assessment) |  |  |  | Accepted | Accepted | FEA accepted and filed on 07-08-20
PUC | Overhead Line Review |  |  |  |  | Approved 03/18/21
|  | Biological Resource Consultation |  |  | Completed | Completed
|  | Cultural Impact Assessment |  |  | Completed | Completed
DPP, LUC | Special Use Permit |  |  | 2020/SUP-6 SP21-411 |  | Planning Commission approved on 3/17/21 | ETA Q2 2021 (LUC approval)
DOH-CWB | NPDES | [5 empty] | ETA Q2 2021
DPP | Conditional Use Permit - Minor | [5 empty] | ETA Q3 2021
DPP | Zoning Waiver (if applicable) | [5 empty] | ETA Q3 2021
DOH-IRHB | Noise Permit | [5 empty] | ETA Q3 2021
DPP | Grading, Grubbing, and Stockpiling Permit | [5 empty] | ETA Q4 2021
DPP | Building and Electrical Permit | [5 empty] | ETA Q4 2021
Mililani I Solar | [7 empty] | Clearway |  |  | 39MW + 156MWh | Mililani | (1)9-4-005:090 (1)9-4-005:092 (1)9-4-005:096 (1)9-4-005:091 | 144 | AG-1 | Agricultural | 2018-0434 | 20 | 2022-11-01
DPP | Conditional Use Permit - Minor (Modification) | 2021/MOD-8 |  |  |  | Approved | 2021-03-04
DPP | Conditional Use Permit - Minor (Modification) | 2019/MOD-108 |  |  |  | Approved | 2020-01-23
DPP | Conditional Use Permit - Minor (Modification) | 2019/MOD-107 |  |  |  | Approved | 2020-01-23
DPP | Conditional Use Permit - Minor (Modification) | 2017/MOD-46 |  |  |  | Approved | 2017-07-06
DPP | Conditional Use Permit - Minor (Modification) | 2017/MOD-42 |  |  |  | Approved | 2017-07-06
DPP | Conditional Use Permit - Minor (Modification) | 2014/MOD-95 |  |  |  | Approved | 2014-10-03
DPP | Zoning Waiver | 2014/W-14 |  |  |  | Approved | 2014-07-29
DPP | Conditional Use Permit - Minor | 2014/CUP-23 |  |  |  | Approved | 2014-07-29
DPP | Conditional Use Permit - Minor (Joint Development) | 2010/CUP-10, Joint Development |  |  |  | Approved | 2010-05-07
DOH-CWB | NPDES |  |  |  |  | Approved | 2021-01-19
FAA | FAA Determination of No Hazard |  |  |  |  | Completed | Summer/Fall 2019
USACOE | Section 404 Clean Water Act - Nationwide Permit Program |  |  |  |  | Completed | Summer/Fall 2019
USFWS, DLNR-DOFAW | Biological Resource Consultation |  |  |  |  | Completed | Summer/Fall 2019
DPP | Grading and Grubbing Permit |  |  |  | Submitted Nov 2020 | Approved | 2021-03-12
DPP | Building Permit (PV Project) |  |  |  | Submitted Nov 2020 | Approved | 2021-03-12
DOH-CWB | Section 401 Water Quality Certification |  |  |  | Not Required | Not Required | N/A
USFWS | Section 7/10 Endangered Species Act Consultation |  |  |  | Not Required | Not Required | N/A
DPP | Building Permit (HECO Substation) |  |  |  | N/A | N/A | N/A
DPP | Building Permit (Project Substation) |  |  |  | Submitted | Pending | 2021-06-24
Waiawa Solar | [7 empty] | Clearway |  |  | 36MW + 144MWh | Pearl City | (1)9-6-004:024 | 200 | AG-1 | Urban | 2018-0435 | 20 | 2022-12-01
DOH-CWB | Section 401 Water Quality Certification |  |  |  | Not Required | Not Required | N/A
PUC | Overhead Line Review |  |  |  | Approved | Approved | 2021-03-01
USACOE | Section 404 Clean Water Act - Nationwide Permit Program |  |  |  | Not Required | Not Required | N/A
USFWS | Section 7/10 Endangered Species Act Consultation |  |  |  | Not Required | Not Required | N/A
FAA | FAA Determination of No Hazard |  |  |  |  | Completed | Summer/Fall 2019
USFWS, DLNR-DOFAW | Biological Resource Consultation |  |  |  |  | Completed | Summer/Fall 2019
DOH-CWB | NPDES |  |  |  | Approved | Approved | 2021-01-19
LUC | Motion to Amend for Urban Land Use |  |  |  | Approved | Approved | 2020-02-11
DPP | Zoning Waiver(s) |  |  | 2020/W-31 2021/W-8(CK) | Approved Approved | Approved Approved | August 13, 2020 March 15, 2021
DPP | Conditional Use Permit - Minor |  |  | 2020/CUP-2 | Approved | Approved | 2021-04-01
DPP | Conditional Use Permit - Minor Modification |  |  | 2021/MOD-23 | Approved | Approved | 2021-03-15
DPP | Grading and Grubbing Permit |  |  |  | Submitted November 2020 | Approved | 2021-04-06
DOT | Highway Permit |  |  |  | Submitted | Pending | Q2 2021
DPP | Building Permit (PV/BESS Project) |  |  |  | Submitted December 2020 | Pending | Q2 2021
DPP | Building Permit (Overhead Line) |  |  |  | Target Submission Q2 2021 | Pending | 2021-10-01
DPP | Building Permit (Project Substation) |  |  |  | Submitted February 23, 2021 | Pending | Q2 2021
AES Mountain View Solar | [7 empty] | AES |  | Mountain View Solar | 7MW + 35MWh | Wai‘anae | (1)8-5-003:031 (1)8-5-003:032 (1)8-5-019:034 | 100 | AG-1 | Agricultural (C,E) | 2020-0139 | 25 | 2023-05-17
PUC | Overhead Line Review
DLNR-SHPD | HRS 6E Compliance | Environmental and Cultural Studies (Biologic Survey and Archeological Inventory Survey) |  |  |  |  | ETA Q2-Q3 2021
DPP | Conditional Use Permit - Minor |  | Biologic Survey and AIS Pending |  |  |  | ETA Q4 2021-Q1 2022
DPP | Zoning Waiver (if applicable) | [5 empty] | ETA Q4 2021-Q1 2022
DOH-CWB | NPDES | [5 empty] | ETA Q4 2021-Q1 2022
DOH-IRHB | Noise Permit | [5 empty] | ETA Q4 2021-Q1 2022
DPP | Grading, Grubbing, and Stockpiling Permit | [5 empty] | ETA Q1-Q2 2022
DPP | Building and Electrical Permit | [5 empty] | ETA Q1-Q2 2022
Ho‘ohana Solar | [7 empty] | 174 Power Global, Hanwha |  |  | 52MW + 218MWh | Kunia | (1)9-4-002:052 | 160 | AG-1 | Urban | 2018-0431 | 20 | 2023-08-31
DPP | Conditional Use Permit - Minor |  |  | 2014/CUP-76 |  | Approved | 2015-01-01
DPP | Zoning Waiver |  |  | 2014/W-67 |  | Approved | 2015
DLNR-SHPD | HRS 6E Compliance | Archeological Inventory Study | Accepted 2/19/15 | LOG#2014.03535 LOG#2014.04974 Doc#1502SL23 |  | AIS accepted 2/19/15 | AIS accepted 2/19/15
DPP | Grading (Initial Road Construction) |  |  |  |  | Approved | 2019-12-01
DPP | Conditional Use Permit - Minor Modification |  |  | 2019/MOD-94 |  | Approved | 2019-10-18
DPP | Conditional Use Permit - Minor Modification |  |  | 2019/MOD-84 |  | Approved | 2019-10-19
DOH-CWB | NPDES (Initial Road Construction) |  |  |  |  | Approved | 2019-12-01
DPP | Zoning Waiver |  |  | 2020/W-27 |  | Approved | 2020-08-01
DPP | Conditional Use Permit - Minor Modification |  |  | 2020/MOD-38 |  | Approved | 2020-08-01
DPP, LUC | Special Use Permit - Amendment |  |  |  |  | Approved - Decision and Order pending | 2020-10-08
DOT | Road Crossing Agreement |  |  |  |  | Not Applicable
PUC | 46kV Line Relocation Approval |  |  |  |  | In Progress
DPP | Grading (Solar and Battery Project) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Grading (Project Substation) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Grading (HECO Switchyard) |  |  |  | Target submission May 2021 |  | ETA October 2021
DOH-CWB | NPDES (Solar and Battery Project) |  |  |  | Target submission May 2021 |  | ETA October 2021
DOH-CWB | NPDES (Project Substation) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Building Permit (Solar and Battery Project) |  |  |  | Target submission May 2021 |  | ETA November 2021
DPP | Building Permit (Project Substation) |  |  |  | Target submission May 2021 |  | ETA November 2021
DPP | Building Permit (HECO Switchyard) |  |  |  | Target submission May 2021 |  | ETA November 2021
Waiawa Phase 2 Solar | [7 empty] | AES |  | Waiawa Phase 2 Solar | 30MW + 240MWh | Waiawa | (1)9-6-004:024 (1)9-6-004:025 (1)9-6-004:026 (1)9-6-006:036 | 387 | Multiple Zones | Urban | 2020-0137 | 20 | 2023-10-30
PUC | Overhead Line Review |  |  |  |  | In Progress
DOH-US Navy | Zone of Influence Approval (if applicable) | [5 empty] | ETA Q2-Q3 2021
DLNR-SHPD | HRS 6E Compliance | Environmental and Cultural Studies (Biologic Survey and Archeological Inventory Survey) | AIS accepted April 2015 |  | HRS 6E compliance to START 12/18/20 | HRS 6E compliance to targeted to END 4/9/21 | ETA Q2-Q3 2021
LUC | LUC Amendment to Decision and Order | [5 empty] | ETA Q3-Q4 2021
DPP | Conditional Use Permit - Minor |  | Biologic Survey and AIS pending |  |  |  | ETA Q4 2021-Q1 2022
DPP | Conditional Use Permit - Minor (Joint Development) | [5 empty] | ETA Q4 2021-Q1 2022
DPP | Conditional Use Permit - Minor Modification | [5 empty] | ETA Q4 2021-Q1 2022
DPP | Zoning Waiver (if applicable) | [5 empty] | ETA Q4 2021-Q1 2022
DOH-CWB | NPDES | [5 empty] | ETA Q4 2021-Q1 2022
DOH-IRHB | Noise Permit | [5 empty] | ETA Q4 2021-Q1 2022
DPP | Grading, Grubbing, and Stockpiling Permit | [5 empty] | ETA Q1-Q2 2022
DPP | Building and Electrical Permit | [5 empty] | ETA Q1-Q2 2022
Mahi Solar | [7 empty] | Longroad Energy |  | Mahi Solar | 120MW + 480MWh | Kunia | (1)9-2-001:020 (1)9-2-004:012 (1)9-2-004:006 (1)9-2-004:003 (1)9-2-004:010 | 627 | AG-1 | Agricultural (B,C,D,E) | 2020-0140 | 25 | 2023-12-31
DOT | Permit to Cross Public Highway |  |  |  |  | Not Required
PUC | Overhead Line Review |  |  |  |  | In Progress
DPP, LUC | Special Use Permit |  |  | 2020/SUP-7 | Application submitted on 12/15/2020 | Application now being circulated for agency comments (due May 10).
DLNR-SHPD | HRS 6E Compliance (Plan Approval, Archeological Assessment) | Environmental Studies to be Completed in 2021 | Archeological Assessment to be Submitted Q2 2021 |  | Target submission Q2 2021 |  | Need SHPD Concurrence Letter by June 2021 before Planning Commission meeting on SUP
DPP | Zoning Waiver |  |  |  | Target submission August 2021 (after SUP Approval) |  | ETA September 2022
DPP | Conditional Use Permit - Minor |  |  | 2020/CUP-48 | Target submission August 2021 (after SUP Approval) |  | ETA September 2022
DPP | Conditional Use Permit - Minor Joint Development | [5 empty] | 2021-02-18
DPP | Building Permits |  |  |  | Target submission October 2021 |  | ETA March 2022
DPP | Grading Permit |  |  |  | Target submission October 2021 |  | ETA March 2022
DOH-CWB | NPDES | [5 empty] | ETA December 2021
DOH-IRHB | Noise Permit | [5 empty] | ETA December 2021
Grey = Permit or Approval is Not Needed or has Been Approved or Completed
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a column or way to indicate if a permit or approval is ministerial, discretionary, or unclear?