## Details
Program Docket | Project Docket | Project Name | Project Type | Stage | Island | Nameplate Capacity (MW) | Storage Capacity (MWh) | Estimated Utility RPS Percent Contribution | Developer | Notes | Project or Task Update | Project or Task Update | Guaranteed Commercial Operations Date
O'ahu Utility-Scale Projects
2021-0024 | 2018-0434 | Mililani I Solar | Solar | Stage 1 | O'ahu | 39 | 156 | 1.2 | Clearway Energy Group |  | All Construction and Testing Activities Complete - Project Achieved Commercial Operations 7-31-22 |  | COD 7-31-22 |  |  |  | done
| 2018-0435 | Waiawa Solar | Solar | Stage 1 | O'ahu | 36 | 144 | 1.2 | Clearway Energy Group LLC; Global Infrastructure Partners |  | PPA - Amendment Approved 10-6-21 Engineering/Design - Finalized Permits and Land Rights - Complete and Secured Procurement and Delivery - All items delivered | Construction - Complete Hawaiian Telecom Circuit - Completed Testing • Oct-22: Acceptance Testing commenced 10-17-22 and passed 10-18-22. • 11-17-22: CSAT commenced (moved up from Feb-23). In final stages of testing, goal to complete before 12-31-22 | New GCOD 9-30-22 Operational 1-11-23 | no movement since last month. If acceptance testing was pushed up, how could this impact current COD? |  | prior to 12-31-22 | done
| 2020-0136 | Kapolei Energy Storage (KES) | BESS | Stage 2 | O'ahu | 185 | 565 | 0.1 | Plus Power | Delay Notes • Achieved COD 12-18-2023 | PPA - Complete • ESPPA amendment approved April 29, 2021, D&O 37754 • Amendment approved July 19, 2023 • 2nd amendment approved July 19, 2023 Engineering/Design - Complete • Final designs for Storage Facility, Substation, and COIF complete; HECO provided comments. • All final drawings (issued for construction) provided to Hawaiian Electric 11-1-22. Permits - Complete • DPP Permits for BESS, Substation Closed as of 8-17-23 • Grading Permit closed 9/28/2023 Land Rights - Complete | Procurement and Delivery - Complete • Replacement transformer was fully installed and operational in time for the Seller’s Capacity/RTE test on 8/7/2023 • March 2022. AMI meter for station power is still pending. The design was approved by the DPP and Meter has been released. Meter was installed on 8/15/2023. Construction - Complete Testing - Ongoing • Acceptance Testing Completed: 4-26-23 • TBD: CSAT anticipated (delayed). Seller expects to start the official CSAT testing by 12/01/2023 and achieve COD by 12/18/2023 | New GCOD 12-30-22 Operational 12-18-23 | no movement in COD |  | delayed 18 days since last month, permitting and equipment delays Delays in obtaining the Gentile Courtesy inspection resulted in the Gentile pole installation crew being unavailable until the week of 1/9/2023 - pushing out the COD by 13 days. PP is working with Moss/HMS to mitigate this delay to the greatest extent possible. | done
| 2019-0050 | AES West O‘ahu Solar | Solar & BESS | Stage 1 | O'ahu | 12.5 | 50 | 0.4 | AES West O‘ahu Solar, LLC. | Delay Notes • Achieved COD 3-28-2024 | PPA - Amendment Conditionally Approved 5-6-22 Engineering/Design - Complete Permits - Complete Land Rights - Complete | Procurement and Delivery - Complete Construction - Complete Testing - Ongoing | New GCOD 1-20-23 COD Achieved 3-28-24 | no movement in COD |  | no change in COD since prior month | done
| 2022-0007 | Kūpono Solar | PV Solar & BESS | Stage 2 | O'ahu | 42 | 168 | 0.85 | Bright Canyon Energy and Ameresco | Delay Notes • Commercial Operations Date recorded as June 7, 2024 | PPA - Amendment Submitted Overhead Line Approval - Complete Engineering and Design - Complete Permits - Complete | Procurement - Complete Land Rights - Secured Construction - Ongoing Testing - Pending | COD Achieved: 6-7-24 | no movement in COD |  | done | done
| 2020-0139 | Mountain View Solar | Solar & BESS | Stage 2 | O'ahu | 7 | 35 | 0.3 | AES Mountain View Solar, LLC. | Delay Notes • Company provided the official inspection report to Seller on 6-9-25. Seller provided IFCs for Company review on 6-13-25 and Company returned comments, seller resubmitted full packages on 7-8-25. Company approved IFC eith comments to be included in Rev 1. • Continued delay of building and electrical permits and additional durations for acceptance testing. 9 out of 11 building permits are closed. • Seller’s expanded inverter testing and commissioning activities and updated schedule reflective of PPA durations. | PPA - Amendment Approved • The PUC approved the 2nd Amendment to the PPA on 10-30-25. Engineering/Design - Ongoing • Company Seller provided IFCs for company review, Company returned comments, and Seller resubmitted full package, and Company approved sellers resubmitted package. System Impact Study - Ongoing • Additional SIS needed due to equipment changes (i.e. grounding transformer) • Company found the GFL PSCAD model suitable for study on 1-10-25. GFM PSCAD island wide restudy is in progress. Seller responded to restudy model tuning requests for the GFM PSCAD and GFM PSSE models. Seller submitted new models on 7-3-25. Company is reviewing Permits - Ongoing • DPP approved building and electrical permit application on 3-5-25, permit was picked up on 3-13-25. | Land Rights - Complete • Following commissioning, Seller will have COIF surveyed by a surveyor licensed in Hawaii and replace the existing blanket easement with the surveyed COIF easement to remain in place for the life of the Project. Procurement and Delivery - Complete • All deliveries complete. Construction - Ongoing • COIF approximately 98% complete • SOIF approximately 98% complete Testing - Pending • October 2025: Acceptance test scheduled to start. Project missing several key predecessors that are causing a delay in Acceptance Testing. • 1-6-26: CSAT scheduled to start. | GCOD 5-17-2024 Estimated COD 2-4-2026 | shifted 2 days - 12/26 to 12/28 | HICRIS 2022PR00486 | minor 5 day delay since prior month. COD in January 2024 | done
| 2020-0137 | Waiawa Phase 2 Solar | Solar & BESS | Stage 2 | O'ahu | 30 | 240 | 1.2 | Waiawa Phase 2 Solar, LLC. (AES) | Delay Notes • Seller resubmitted full IFDC package on 7-8-25. Company approved IFC package, with comments to be included in Rev 1. • Delay in execution of COIF Grant of Easment. Acceptable land rights have not been delivered to the Company. •DPP building permits were approved 7-24-25. • Updates to testing and commissioning activity durations and deconflicting activities with predecessors to align with PPA requirements. | PPA - Complete • Amendment Approved by PUC 8-1-2023. Engineering/Design - Ongoing • Seller provided an updated Final IFC package on 6-20-25 for Company to review. Company returned comments to Seller. Seller resubmitted full IFC package on 7-8-25 which company is reviewing. • Company and Seller are conducting a partial IRS restudy due to equipment changes. System Impact Study - Ongoing • Additional SIS required due to equipment changes (i.e. collector feeder design, grounding transformer. • GFL PSCAD model found suitable for study and report was issued to Seller on 4-11-25. GFM PSCAD restudy is in progress. Seller is responding to restudy model tuning requests afor the GFM PSCAD and GFM PSSE models. Seller submitted new models on 7-3-25. Company is currently running the study with the updated models. Permits - Ongoing • Seller working to close out grading, grubbing, and stockpiling permit September 2025. | Land Rights - Ongoing • Company, Seller, and Landowner are working on an amendment for the right of entry. • Landowner returned redline to Company on 5-28-2025. Required under the PPA for Asset Transfer. Company returned redlines to the Grant of Easement to Seller and Landowner on 7-16-25. Company received redlines from the landowner and is reviewing. Procurement and Delivery - Ongoing • Pending approval of building permits which have delayed project COD. Construction - Ongoing • SOIF: 99% complete • COIF: 99% complete Testing - Pending • 11-3-25: Acceptance testing scheduled to start • 2-9-26: CSAT schedule to start. | GCOD 9-1-2024 Estimated COD 3-13-2026 | shifted 2 weeks
| 2018-0431 | Ho‘ohana Solar 1 | Solar & BESS | Stage 1 | O'ahu | 52 | 208 | 1.4 | 174 Power Global; (Hanwha Energy Corporation; Forest City Sustainable Resources) | Delay Notes • Delay due to issues that 174PG is currently addressing in its IRS restudy. | PPA Amendment - Complete • The Company and Seller executed a PPA amendment on February 13, 2023 and filed the amendment with the Commission on 2-17-23. The amendment was approved on May 30, 2023. Engineering/Design - Complete • Biweekly meetings with Seller ongoing Permits - Complete • Amended Building Permit for Solar/ Battery approved on 4-30-25. System Impact Study - Ongoing • Company received latest updated single-line diagrams suppororting Seller's proposed solution for review on 10-23-24. Letter Agreement (which allows Seller to complete modeling task within a certain time period following COD) was executed by Seller on 3-12-24 | Procurement and Delivery - Complete Land Rights - Complete Construction - Ongoing • Gen facility: racking at 100% installed and PV at 100% installed. • SOIF - 100% Complete. COIF company local testing in progress, installation of 138kV conductors was completed 11-24-24 Testing - Ongoing • Acceptance Test completed on 11-8-24, and energization (back feed) was completed on 11-24-24 • CSAT re-tests were completed June 13-17, 2025, but the project fell out of monitoring due to incomplete file settings that were corrected on 6-23-25 and retested during the same period. | GCOD 10-31-2024 Estimated COD 6-30-2025 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
2017-0352 | TBD | Pu'uloa Energy | Internal Combustion Engines (Biofuel) | Stage 3 | O‘ahu | 99 | - |  | Ameresco |  | Notes: Project selected for negotiation by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review and Approval |  | Estimated Completion: 2027
| TBD | Pu'uloa Solar | Solar & BESS | Stage 3 | O‘ahu | 6 | 30 |  | Ameresco |  | Notes: Project selected for negotiation by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review and Approval |  | Estimated Completion: 2026
| TBD | Base Proposal | Combustion Turbine (Biofuel) | Stage 3 | O‘ahu | 208 | - |  | Kalaeloa Partners LP |  | Notes: Project selected for negotiation by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review and Approval |  | Estimated Completion: 2033
| TBD | Waiau Repower | Combustion Turbine (Biofuel) | Stage 3 | O‘ahu | 253 | - |  | Hawaiian Electric |  | Notes: Project selected for negotiation by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review and Approval |  | Estimated Completion: 2033
| TBD | Mahi Solar & Storage | Solar & BESS | Stage 3 | O‘ahu | 120 | 480 |  | Longroad Development |  | Notes: Project selected for negotiation by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review and Approval |  | Estimated Completion: 2027
| TBD | Makana La | Solar & BESS | Stage 3 | O‘ahu | 80 | 480 |  | Clearway Energy Group | Notes: Project withdrew October 7, 2024 |  |  | Project withdrew October 7, 2024
| TBD | Par Hawai‘i Renewable Combined Heat & Power | Combined heat & power (biofuel) | Stage 3 | O‘ahu | 33.9 | - |  | Par Hawai‘i Refining | Notes: Project withdrew November 1, 2024 |  |  | Project withdrew November 1, 2024
| Sum all O‘ahu Projects |  |  |  |  | 723 | 785
Maui Utility-Scale Projects
2021-0024 | 2018-0436 | AES Kuihelani Solar | Solar & BESS | Stage 1 | Maui | 60 | 240 | 1.9 | AES | Delay Notes • Commercial Operations Date recorded as May 31, 2024) | Overhead Line - Approved PPA amendment - Complete Engineering and Design - Complete Permits - Complete Land Rights - Complete | Procurement - Complete Construction - Complete Testing - Complete | COD Achieved: 5-31-24 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
| 2020-0132 | Waena Battery Energy Storage System (Reapproved by PUC with Conditions) | BESS | Stage 2 | Maui | 40 | 160 | 0.2 | Hawaiian Electric Company, Capital Improvement Project | Delay Notes • Circuit breaker lead time increased to 80 weeks. | Engineering/Design - Ongoing • COIF: 60% review completed. COIF - Transmission line: 90% design complete • 60% design drawing comments are complete for Plant and substation work. 90% design drawings complete for physicals and controls for plant and substation work. Permits - Ongoing • Remaining permits anticipated by 3-1-26. System Impact Study - Ongoing • On 11-29-21, an updated SIS was submitted to the Hawaiian Electric Development Team for verification if the system is capable of the new changes. Restudy required due to change in equipment, still working on getting info to SIS team due to some design changes in the system. | Land Rights - Complete • Rights of entry and easements are secured because the land is company-owned Procurement and Delivery - Ongoing • The earliest arrival date for equipment is on 6-17-25. Construction - Pending • Has not started. Earliest start date projected to be 4-30-26. EPC contracts executed Testing - Pending • Has not been scheduled to start | GCOD 4-30-2027 Estimated COD 4-30-2027 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
| 2018-0433 | Paeahu Solar | Solar & BESS | Stage 1 | Maui | 15 | 60 | 0.5 | Innergex Renewable Energy | Delay Notes • Project delays for re-approval process of CUP/H2 Permits led to mediation meetings, with a hearing concluding January 9, 2023. The Hearings Officer final report, along with the re-approval of the CUP/PH2 • Permit is currently delayed, pending updates from hearing officer. • Project requires PUC approval of the Overhead Line to proceed with project financing. • Projected has been delayed by FM Events requiring: Alternative Sourced PV BESS Inverter & potential delays due to BESS equipment supply shipping. • On September 29, 2023 & October 16, Company sent notice of missed construction financing milestones and assessment of daily delay damages. Company requested a new unit Price & GCOD. • Parties have met and are working diligently towards a new unit price and schedule. | Overhead Line Approval - Ongoing • On July 22, 2022, the Consumer Advocate filed a response to the Company’s July 8 Response to Order 38446, explaining it does not object to addressing Issue 3 of the proceeding at this time. • 5-23-22 Innergex provided letter to MECO, provided reasoning not all information is available to update the Interconnection Requirements Study (IRS). OH line approval should not be delayed pending execution of updated IRS Amendment. • Seller is anxiously awaiting a procedural schedule PPA amendments - Ongoing • If PUC Approval order Date Occurs 180 days after execution, the seller and HECO are entitled to an extension of the GCOD. • Paeahu PPA – PUC issued D&O No. 37340 on October 5, 2020 and 37553 on January 14, 2021 approving the project and denying a subsequent motion for reconsideration filed by Pono Power Coalition (“PPC”), respectively. • PPC filed a timely appeal to the Hawaii Supreme Court (“HSC”) related to the Paeahu PPA and procedural steps were completed throughout 2021. The HSC issued its Opinion of the Court on March 2, 2022 stating the PUC lawfully approved the PPA and affirmed the Approval Order and the Recon Order. The HSC entered judgment on April 1, 2022. • The Paeahu PPA notes if the PUC Approval Order Date occurs more than 180 days after the Execution date, the Seller and Company will be entitled to an extension of the Guaranteed Project Milestone Date. Parties agree that July 1, 2022 is the Effective Date of the PPA. Land Rights - ongoing Easement update required for overhead line extension, pending IFC of Seller transmission line, estimated Q4 2023 | Permits (Critical Path) - Ongoing • Noise permit was extended on July 18, 2022, and valid until July 13, 2023. • County Special Use Permit (CUP) - Approved 5-25-21, appealed by Pono Power Coalition, mediation was 5-3-22 to 5-27-22. A settlement was not reached and will proceed to a contested case, evidentiary hearing to commence 11-28-22. • Approvals at county level would not be granted until after the re-approval of the CUP/PH2 permit. The Hearing Officer final report is delayed and expected by end of Q3 2023. Engineering and Design - Ongoing • May-22: MECO pricing update identified the cost has more than doubled since May-2020 • 90% design complete step-up substation, generation facility, SOIF transmission line. Procurement -TBD • The Seller provided the Company with a BESS and PV inverter solution for the Hale Kuawehi Project on July 15, 2022. The Seller noted that the Paeahu solution will be very similar. The Seller anticipates design updates and preliminary system model updates. An interconnection restudy may be required. Construction - TBD Testing - TBD | Project Terminated | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
2017-0352 | TBD | Kuihelani Phase 2 Solar | Solar & BESS | Stage 3 | Maui | 40 | TBD |  | AES Corp. |  | Notes: Project selected for negotiation by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  | Estimated Completion: 2027
| TBD | Puu Hao Solar | Solar & BESS | Stage 3 | Maui | 20 | TBD |  | AES Corp | Notes: Project withdrew May 24, 2024 |  |  | Project withdrew May 24, 2024
| TBD | Kaheawa Wind 1 | Wind | Stage 3 | Maui | 30 | - |  | Terraform US |  | Notes: Project selected for negotiation by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  | Estimated Completion: 2026
| TBD | Pūlehu Solar & Storage | Solar & BESS | Stage 3 | Maui | 20 | 80 |  | Longroad Energy |  | Notes: Project selected for negotiation by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  | Estimated Completion: 2027
| TBD | Ukiu Energy | Internal Combustion (biofuel) | Stage 3 | Maui | 40 | TBD |  | Ameresco, Inc. |  | Notes: Project selected for negotiation by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  | Estimated Completion: 2027
| 2021-0026 | Kamaole Solar | Solar & BESS | Stage 2 | Maui | 40 | 160 | 1.4 | Kamaole Solar LLC (Potential Renewables) | PPA Declared Null & Void March 2023 Due to Rising Costs | PPA Status • PPPA Declared Null and VOID Overhead Line Approval - Engineering and Design • Q3-22: remote work scheduled to start • 30% design complete for step up substation, 10% for COIF and COIF Transmission Line Land Rights Easement for COIF anticipated May 2023. | Permits • Nov-22: Anticipated approval date of SHPD approval letter. Archeological Inventory Survey ongoing, sites were larger than anticipated, impacting anticipated approval date and SUP and County permitting timelines (HRS) • Jun-22 : Estimated issue date of noise permit • Jan-23: Estimated approval date of EA exemption (HDOT, Maui County) • Jun-23: anticipated approval date of County Special Use Permit (slipped from Jan-23), as well as building permit • Jul-23: anticipated approval date of grading and grubbing and electrical permits Land Rights • May-23: estimated receipt of COIF/SOIF easement, impacted by delay in substation engineering Procurement and Delivery • All equipment dates pending resolutions to supply chain volatility • Orders placed for most equipment Sep-Nov-22, estimated arrival dates Q1-Q3 2023. Construction • Q2-23: generation facility and SOIF construction scheduled to start • Q3-23: COIF transmission line construction scheduled to start Testing • Sep-24: Acceptance test • Dec-24: CSAT | GCOD 8-31-23 Estimated COD 10-31-24 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
| Sum All Maui Projects |  |  |  | Maui | 185 | 240 | 2.1
Hawai'i Utility-Scale Projects
2021-0024 | 2018-0432 | Hale Kuawehi Solar | Solar & BESS | Stage 2 | Hawai'i | 30 | 120 | 0.8 | Innergex Renewable Energy Inc. | Delay Notes: • Project reached commercial operations on 3-25-2025 | PPA Amendment - Complete Engineering & Design - Complete • Company will amend SIS report, to correct an error, and align with the PPA ride-through requirements, which will not cause a delay to COD. • All designs are complete, however typical and minor constructability updates may be required and are anticipated to be captured in final documentation. • System impact Study restudy updates complete and will not cause delay to COD. System Impact Study - Complete • Seller provided feedback on October 9, which was reviewed by Company. On October 29, 2024 Company sent restudy report to Seller. • Company is currently revising report to reflect minor changes requested by Seller. Permits - Complete • All permits required to construct and operate the facility are in hand • October 2024, all county building permits provided to the company | Procurement and Delivery - Complete • All PV modules were received in December 2023, but Seller discovered a high number of broken modules. Delivery of 31 replacement modules received in December 2024. Construction - Complete • All facility construction is complete. • Work on COIF construction was completed 2-3-25. Testing - Complete • Acceptance Testing estimated Start: 11-18-2024, completed: 11-20-2024. • Company provided results 12-9-2024 indicating acceptance testing was passed. • CSAT is expected to start 2-28-2025. | GCOD 10-11-2024 COD: 3-25-2025 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
| 2020-0127 | Keahole | BESS | Stage 2 | Hawai'i | 12 | 12 | N/A | Hawaiian Electric Company, Capital Improvement Project | Delay Notes • No change in status, but project schedule is still being impacted by: • Pending decision by the Commission on the amended application (submitted May 5, 2023) • Work is on hold and schedule to be re‐evaluated pending a PUC Approval Order for the Project | • Work is on hold and schedule to be re‐evaluated pending a PUC Approval Order for the Project | Decision and Order 39066 approved new Procedural schedule which ends in August 2023. Updated dates are based on the new procedural schedule. Amended application submitted to the Commission on May 5, 2023. | GCOD: 12-30-25 COD: 12-30-25
2017-0352 | TBD | Keamuku Solar | Solar & BESS | Stage 3 | Hawai‘i | 86 | 344 |  | AES Corp. |  | Notes: Project selected for negotiation by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  | Estimated Completion: 2030
| TBD | Puako Solar | Solar & BESS | Stage 3 | Hawai‘i | 60 | 240 |  | Clearway Energy Group | Notes: Project withdrew on October 7, 2024 |  |  | Project withdrew October 7, 2024
| TBD | Kaiwiki Solar | Solar & BESS | Stage 3 | Hawai‘i | 55 | 220 |  | Clearway Energy Group | Notes: Project withdrew on October 7, 2024 |  |  | Project withdrew October 7, 2024
| TBD | Hamakua Firm Energy | Combined Cycle (Biofuel) & BESS | Stage 3 | Hawai‘i | 60 | 30 |  | Currently Pacific Current pending Kalaeloa Partners LP |  | Notes: Project selected for negotiation by Hawaiian Electric December 18, 2023 Contracts will be submitted to PUC for Review & Approval |  | Estimated Completion: 2030
| Sum All Hawai'i Projects |  |  |  | Hawai'i | 146 | 374 | 0.8
Kaua'i Utility-Scale Projects
2020-0218 | 2020-0218 | West Kaua'I Energy Project | Solar, BESS, & Pumped Hydro | N/A | Kaua'i | 35 |  | 15 | KIUC, AES | From quarterly report filed Aug 1, 2024: "At the current time, KIUC and AES are focusing on ... a solar and battery only option..."
| TBD | Mana Solar & Storage | Solar & BESS | N/A | Kaua'i | 35 | 140 |  | AES Corp. |  | Notes: Project selected by KIUC
| TBD | Kaawanui Solar & Storage | Solar & BESS | N/A | Kaua'i | 43 | 172 |  | AES Corp. |  | Notes: Project selected by KIUC
| Sum All Kaua'i Projects |  |  |  |  | 78 | 312 | 15
Community-Based Renewable Energy (CBRE) - Shared Solar
2015-0389 | 2015-0389 | Palailai Solar 1 - Phase 1 |  | CBRE Phase 1 | O'ahu | 3 | 0 |  |  | Delay Notes: • COD Achieved October 10, 2023 | Engineering & Design - Complete Permits Complete Procurement - Complete | Construction - Complete Testing- Complete • Acceptance Test: Completed 8-24-23 • CSAT Test: Oct-23 CBRE Contract - Complete | New GCOD 1-27-23 *to be 7-28-23 Achieved: COD October 2023 | no movement since last month
| 2015-0389 | Ka Lae (solar) - formerly 'HLCBRE‐0003 Arion South Point' | Solar & BESS | CBRE Phase 1 | Hawai'i | 0.75 | 0 |  |  | Delay Notes: • Achieved COD on April1, 2024 | PPA • N/A Land rights Permits - Complete • All required permits for construction have been received from the Dept. of Public Works. Engineering/Design - Complete • Inverter change from Delta to Chint Power Systems inverters is required. Company confirmed Sellers's PCSAD model passed the check out on 01/16/24. | Procurement and Delivery - Complete Construction -Complete Testing | GCOD: 3-29-23 Achieved COD: 4-1-2024 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
| 2015-0389 | Kawela Plantation | Solar & BESS | CBRE Phase 1 | Moloka'i | 0.25 | 0 |  |  | Delay Notes: • Achieved COD on April1, 2024 | PPA - N/A Engineering/Design - Complete • Complete Overhead Line Approval - N/A | Permits - Complete Procurement and Delivery - Complete Construction - Complete Testing | GCOD: 10-19-2023 Achieved COD: 4-1-2024 | no movement in COD |  | Note for Hawaiian Electric and Larry - looks like they have a lot of permitting information in the engineering and design sections.
| 2015-0389 | KHLS - Phase 1 |  | CBRE Phase 1 | O'ahu | 1.72 | 0 |  |  | Delay Notes: • Seller and Company executed a Letter Agreement to reinstate the KHLS CBRE Phase 1 project effective 03-26-24. Commercial Operations deadline for the project is 5-1-25. Primary driver for the schedule change is the progress on the closeout of the Engineering phase. Seller provided revised project schedule 8-11-25. • Facility construction is completed for the Generating Facility and partial SOIF, until the approval of the IFC Design set. IFC Design set approved by company on 6-3-25. Seller is currently in process of remobilization. | Engineering/Design - Ongoing • Seller completed revisions on 90% Rev 1, and submitted IFC design set review was completed by the Company on 5-20-25 and is being routed for approvals. IFC Design set approved by company on 6-3-25. • Engineering design and review phases completed on 5-20-25. Permits - Complete • All permits approved. System Impact Study - Ongoing • Company provided Seller additional comments regarding inverter models. Seller working to address comments and resubmit. Land Rights - Ongoing • Seller is coordinating easements with HDOT, the City and County of Honolulu, and DHHL on the MV overhead route to the POI • provided additional redlines prior to execution and license is currently being re-reviewed for finalization by DHHL. • Company received signed ROE from Seller on 12-17-24, Right of Entry fully executed 12-19-24. | Procurement • All equipment received. • Company is working with Seller to finalize outstanding RFIs regarding remaining Company Owned Interconnection Facilities items that have not yet been procured. Construction- Ongoing • SOIF: Completed • COIF: Estimated completion Q3 2025. • Seller and Company are currently looking at impact revised schedule will have on construction related timelines. Seller provided updated schedule on 4-28-25, and a revised schedule on 8-11-25. Seller submitted RFI regarding the corrections required for the Microstation Drawings. Testing - Pending • Q4 2025: Acceptance Test Anticipated • Q1 2026: CSAT Test Anticipated | GCOD 3-17-2023 COD Q2 2026 | one month slip since last month

## Calendar
PUC Docket Number and Link | PUC Approved Project | Developer | Technology | Stage | Island | Nameplate Capacity (MW) | Estimated Utility RPS Percent Contribution | 2021-07-21 | 2021-09-21 | 2021-10-21 | 2021-11-21 | 2021-12-21 | 2021-01-22 | 2021-02-22 | 2021-03-22 | 2021-04-22 | 2021-05-22 | 2021-06-22 | July 2022 | Aug 2022 | Coal Plant Retirement 9-1-2022 | Storage Capacity (MWh) | Up to Oct, 2022 | Oct 2022 | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | June 2023 | July 2023 | August 2023 | Sept 2023 | Oct 2023 | Nov 2023 | 2023 | 2024 | 2024 (if delayed) | Jan 2025 | Feb 2025 | Mar 2025 | April 2025 | May 2025 | June 2025 | July 2025 | Aug 2025 | Sept 2025 | Oct 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Q3 / Q4 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034
2021-0024 | O'ahu Utility-Scale Projects
2018-0434 | Mililani I Solar (Stage 1) | Clearway Energy Group LLC; Global Infrastructure Partners |  |  |  | 39 | 1.2 | [11 empty] | Accelerated GCOD 7-31-22 PROJECT ENERGIZED!
2018-0435 | Waiawa Phase 1 Solar | Clearway Energy Group LLC; Global Infrastructure Partners |  | Stage 1 | O'ahu | 36 | 1.2 | [6 empty] | • Equipment delivery ongoing |  | • Shanghai shutdown impacting delivery of BESS components |  | Telecom poles building permit: Approved 6-28-22 |  |  |  | 0 | Accelerated GCOD 9-30-22 |  | Original COD 12-1-23 |  | Operational 1-11-23
2020-0136 | Kapolei Energy Storage (KES) | Plus Power | BESS | Stage 2 | O'ahu | 185 | 0.1 | [7 empty] | Mar-22: Grading permits received Site mobilization started |  | May-22 Building permits expected (DPP & AES) - Delayed |  |  |  |  | 565 |  |  |  | GCOD 12-30-22 | [11 empty] | Online December 2023
2019-0050 | AES West O‘ahu Solar | AES West O‘ahu Solar, LLC. | Solar & BESS | Stage 1 | O'ahu | 12.5 | 0.4 | [7 empty] | •Mar- 22: Noise Permit Received | • Apr-22: Grading Permit approved | • May-22: Building and Electrical Permit (DPP & AES) • May-22: Construction anticipated to start |  |  |  |  | 50 |  |  |  |  | New GCOD 1-20-23 | [11 empty] | COD Achieved Operations 3-28-24
2022-0007 | Kūpono Solar | Bright Canyon Energy and Ameresco | Solar & BESS | Stage 2 | O'ahu | 42 | 0.85 | [14 empty] | 168 | [16 empty] | GCOD 5-13-24 | COD Achieved Operations 6-7-24
2020-0139 | Mountain View Solar | AES Mountain View Solar, LLC. | Solar & BESS | Stage 2 | O'ahu | 7 | 0.3 | [14 empty] | 35 | [8 empty] | GCOD 5-17-23 | [7 empty] | GCOD 5-17-24 | [16 empty] | COD 2-4-26
2020-0137 | Waiawa Phase 2 Solar | Waiawa Phase 2 Solar, LLC. (AES) | Solar & BESS | Stage 2 | O'ahu | 30 | 1.2 | [14 empty] | 240 | [16 empty] | GCOD 9-1-24 | [16 empty] | COD 3-13-26
2018-0431 | Ho‘ohana Solar 1 | 174 Power Global; (Hanwha Energy Corporation; Forest City Sustainable Resources) | Solar & BESS | Stage 1 | O'ahu | 52 | 1.4 | [7 empty] | 3-15-22: Grading Permit & NPDES permit issued, Site Clearing began | [6 empty] | 208 | [16 empty] | GCOD 10-31-24 | [14 empty] | COD 6-30-25
2017-0352 | Pu'uloa Energy | Ameresco | Internal Combustion Engines (Biofuel) | Stage 3 | O‘ahu | 99 | [15 empty] | - | [34 empty] | Estimated Completion
2017-0352 | Pu'uloa Solar | Ameresco | Solar & BESS | Stage 3 | O‘ahu | 6 | [15 empty] | TBD | [33 empty] | Estimated Completion
2017-0352 | Base Proposal | Kalaeloa Partners LP | Combustion Turbine (Biofuel) | Stage 3 | O‘ahu | 208 | [15 empty] | - | [40 empty] | Estimated Completion
2017-0352 | Waiau Repower | Hawaiian Electric | Combustion Turbine (Biofuel) | Stage 3 | O‘ahu | 253 | [15 empty] | - | [40 empty] | Estimated Completion
2017-0352 | Mahi Solar & Storage | Longroad Development | Solar & BESS | Stage 3 | O‘ahu | 120 | [15 empty] | TBD | [34 empty] | Estimated Completion
2017-0352 | Makana La | Renew Development Holdlco | Solar & BESS | Stage 3 | O‘ahu | 80 | [15 empty] | TBD | [34 empty] | Estimated Completion
2017-0352 | Par Hawai‘i Renewable Combined Heat & Power | Par Hawai‘i Refining | Combined heat & power (Biofuel) | Stage 3 | O‘ahu | 33.9 | [15 empty] | - | [34 empty] | Estimated Completion
2021-0024 | Maui Utility-Scale Projects
2018-0433 | AES Kuihelani Solar | AES | Solar & BESS | Stage 1 | Maui | 60 | [15 empty] | 240 | [13 empty] | Previous GCOD: 10-27-23 |  |  | GCOD: 5-31-24 | COD Achieved Operations 5-31-24
2021-0026 | Waena Battery Energy Storage System (Approved with Conditions) | Waena Battery Energy Storage System (Approved with Conditions) | Solar & BESS | Stage 2 | Maui | 40 | [15 empty] | 160 | [34 empty] | GCOD 4-30-27
2020-0132 | Paeahu Solar | Innergex Renewable Energy | Solar & BESS | Stage 1 | Maui | 15 | [15 empty] | 60 | [7 empty] | Terminated
2018-0436 | Kamaole Solar | Kamaole Solar LLC (Potential Renewables) | Solar & BESS | Stage 2 | Maui | 40 | [15 empty] | 160 | [7 empty] | Original GCOD: 4-30-23 |  |  |  | New GCOD: 8-31-23 | [15 empty] | COD 10-31-24
2017-0352 | Kuihelani Phase 2 Solar | AES Corp. | Solar & BESS | Stage 3 | Maui | 40 | [15 empty] | TBD | [35 empty] | Estimated Completion
2017-0352 | Puu Hao Solar | AES Corp | Solar & BESS | Stage 3 | Maui | 20 | [15 empty] | TBD | [34 empty] | Estimated Completion
2017-0352 | Kaheawa Wind 1 | Terraform US | Wind | Stage 3 | Maui | 30 | [15 empty] | - | [33 empty] | Estimated Completion
2017-0352 | Pūlehu Solar & Storage | Longroad Energy | Solar & BESS | Stage 3 | Maui | 20 | [15 empty] | TBD | [34 empty] | Estimated Completion
2017-0352 | Ukiu Energy | Ameresco, Inc. | Internal Combustion (Biofuel) | Stage 3 | Maui | 40 | [15 empty] | TBD | [34 empty] | Estimated Completion
2021-0024 | Hawai'i Utility-Scale Projects
2018-0432 | Hale Kuawehi Solar | Innergex Renewable Energy Inc. | Solar & BESS | Stage 2 | Hawai'i | 30 | 120 | [14 empty] | 120 | [16 empty] | GCOD 10-11-24 | [11 empty] | COD 3-25-25
2020-0127 | Keahole BESS | Hawaiian Electric Company, Capital Improvement Project | Solar & BESS | Stage 2 | Hawai'i | 12 | 12 | [14 empty] | 12
2017-0352 | Keamuku Solar | AES Corp. | Solar & BESS | Stage 3 | Hawai‘i | 86 | [15 empty] | TBD | [37 empty] | Estimated Completion
2017-0352 | Puako Solar | Clearway Energy Group | Solar & BESS | Stage 3 | Hawai‘i | 60 | [15 empty] | TBD | [35 empty] | Estimated Completion
2017-0352 | Kaiwiki Solar | Clearway Energy Group | Solar & BESS | Stage 3 | Hawai‘i | 55 | [15 empty] | TBD | [35 empty] | Estimated Completion
2017-0352 | Hamakua Firm Energy | Pacific Current | Combined Cycle (Biofuel) & BESS | Stage 3 | Hawai‘i | 60 | [15 empty] | TBD | [37 empty] | Estimated Completion
2020-0218 | Kaua'i Utility-Scale Projects
2015-0389 | Community-Based Renewable Energy (CBRE) - Shared Solar
2015-0389 | Palailai Solar 1 |  |  | Phase 1 | O'ahu | 3 | [15 empty] | 0 |  | Original GCOD 10-29-22 |  |  | New Revised GCOD 1-27-23 | [8 empty] | COD Achieved 10-1-2023
2015-0389 | KHLS |  |  | Phase 1 | O'ahu | 1.72 | [15 empty] | 0 | [6 empty] | GCOD 3-17-23 | [8 empty] | GCOD 3-17-23 | [17 empty] | COD Q2 2026
2015-0389 | Ka Lae (solar) - formerly 'HLCBRE‐0003 Arion South Point' |  |  | Phase 1 | Hawai'i | 0.75 | [15 empty] | 0 | [9 empty] | GCOD: 6-1-23 | [6 empty] | GCOD: 4-1-2024
2015-0389 | Kawela Plantation |  |  | Phase 1 | Moloka'i | 0.25 | [15 empty] | 0 | [13 empty] | GCOD: 10-19-2023 |  |  | GCOD: 4-1-2024
| Phase 2 |  |  | Phase 2 | O'ahu | 105 capacity limit | TBD | [7 empty] | PUC Approved O‘ahu RFP Mar-22 Hawaiian Electric issued RFP Apr-22
2007-0323 | Energy Efficiency - Public Benefits Fund * |  |  |  |  | Estimated Energy Savings
| General Energy Efficiency Programs for Demand Side Management | Hawai‘i Energy |  |  |  | ~ 20 to 22 MW per year | N/A – Energy Efficiency | Ongoing
| Hawai‘i Energy Power Move Program | Hawai‘i Energy |  |  |  | ~2-3 MW per year | N/A – Energy Efficiency | [30 empty] | Application Deadline: 12-30-23
| Power Move Commercial Battery Storage Rebate Pilot | Hawai‘i Energy |  |  |  | ~ 4 MW see Battery Bonus Count | N/A – Energy Efficiency | [26 empty] | Installation by 8-31-23 |  |  |  |  | Application Deadline: 1-31-24
2018-0163 | Microgrid Services Tariff*
[6 empty] | TBD | TBD
2017-0352 | O‘ahu Grid Services RFP *
[6 empty] | 60 | TBD
2014-0135 | Green Infrastructure Loan Program- Green Energy Market Securitization (GEMS) *
TBD
2007-0341 | Demand Side Response - Grid Services Purchase Agreements *
[6 empty] | TBD | TBD

## Sheet1 (hidden)
Project | Guaranteed Commercial Operations Date
AES Kuihelani Solar (Stage 1) | GCOD 10-27-23
AES Waikoloa Solar | 12/26/22 COD (slipped from 11/3/2022)
Barber's Point Solar | Original GCOD 12-29-23 COD 5-2-24
Hale Kuawehi Solar | COD 5/5/23 (slipped from 4/28/23 and 12/2/22)
Ho‘ohana Solar 1 (Stage 1) | GCOD 8-31-23 Estimated COD 12-15-23
Kahana Solar (Stage 2) | Original GCOD: 12-29-23 Anticipated COD 4-17-24
Kamaole Solar (Stage 2) | Original GCOD 07-25-23 Anticipated COD 10-29-24
Kapolei Energy Storage (KES) (Stage 2) | New GCOD 12-30-22 Estimated COD 3-10-23
Keahole Battery Energy Storage | 1-23-24 (slipped from 12-28-23 and 11-28-23)
KHLS Phase 1 | GCOD 12-17-22 COD Aug-23
Kūpono Solar | GCOD 4-9-24
Mahi Solar (Stage 2) | Original GCOD 12-31-23 New Proposed GCOD 3-31-24 (GCOD in recent PPA under review by PUC)
Mililani I Solar (Stage 1) | New GCOD 7-31-22 Estimated COD 7-29-22
Mountain View Solar (Stage 2) | GCOD 5-17-23 Estimated COD 6-6-23
Paeahu Solar Stage 1 (docket suspended) | Suspension lifted 5-11-22 GCOD 4-28-23 COD 9-8-23
Palailai Solar 1 - Phase 1 | New GCOD 1-27-23 COD March 2023
Pulehu Solar (Stage 2) | COD now listed as 10-31-24 Proposed new GCOD 12-31-23 Original GCOD was 4-28-23
Waena Battery Energy Storage System (Awaiting Commission Approval) | 5-28-24 (slipped from 4-26-24, 3-29-24 and 2-29-24 and 1-29-24)
Waiawa Phase 2 Solar (Stage 2) | GCOD 10-30-23
Waiawa Solar (Stage 1) | New GCOD 9-30-22 Estimated COD 11-14-22 (COVID-19 lockdown in Shanghai, China delaying delivery of battery enclosures; could impact COD)
West O‘ahu Solar (Stage 1) | GCOD 9-7-22 Estimated COD 1-20-23 (Extended due to Force Majeure)

## Discretionary Permits Remain (hidden)
Discretionary Permit Outstanding
Project | Developer | State | City and County | Notes
West O‘ahu Solar | AES |  | N/A | not really a discretionary permit, but approval still needed
Mountain View Solar Stage 2 | AES | PUC overhead line review, IRS target 11-15 6e SHPD compliance | CUPminor, Zoning waiver (DPP) | status update states "if applicable" for zoning waiver- it is applicable
Waiawa Phase 2 Solar (Stage 2) | AES | 6e compliance, LUC ammendment | CUPm, Zoning waiver (DPP) | status update states "if applicable" for zoning waiver - it is applicable
Mahi Solar | Longroad Energy |  | CUPminor, Zoning Waiver (DPP)

## TF Project Permit Details (hidden)
Project | Permitting, Approving, or Accepting Agency | Permit or Approval | Discretionary or Ministerial | Application Date or Status | Issuance Status | Permit or Approval Issuance or Target (ETA) Date | Last Updated (HSEO ref)
AES West O‘ahu | AES West O‘ahu Solar (Stage 1) | [5 empty] | 2021-09-24
AES West O‘ahu | PUC | Overhead Line Review | Discretionary | Approved | Approved 3-18-21 | Approved 3-18-21
AES West O‘ahu | DLNR-SHPD | HRS 6E Compliance | Discretionary | Approved | Approved | 2021-01-04
AES West O‘ahu | DPP, OEQC | HRS 343 Compliance (Environmental Assessment) | Discretionary | Approved | Approved | FEA accepted and filed on 7-8-20
AES West O‘ahu | DOH-CWB | NPDES | Ministerial | Approved | Approved | 2021-03-31
AES West O‘ahu | AES West O‘ahu Solar | Special Use Permit | Discretionary | Approved | Approved | Complete 5-13-21, Final approval 6-10-21
AES West O‘ahu | DPP | Conditional Use Permit - Minor | Discretionary | Permit Application Filing milestone was met in August 2020 | Land Use Commission rescheduled hearing from May 26-27 to June 9; impacted ability to move forward with CUP (Minor). Working with DPP to accelerate DPP permits | 2021-08-12
AES West O‘ahu | DLNR - Land Court | Secure Land Rights | Ministerial | Estimate sending easement to land court mid August to early September |  | 2021-10-01
AES West O‘ahu | DOH-IRHB | Noise Permit | Ministerial | Permit Application Filing milestone was met in August 2020 |  | ETA Q3-Q4 2021
AES West O‘ahu | DPP | Grading, Grubbing, and Stockpiling Permit | Ministerial | Permit Application Filing milestone was met in August 2020 | Land Use Commission delayed hearing June 9 (approved); impacted ability to move forward with CUP (Minor). Working with DPP to accelerate DPP permits. | ETA Q4 2021
AES West O‘ahu | DPP | Building and Electrical Permit | Ministerial | Permit Application Filing milestone was met in August 2020 | Land Use Commission rescheduled hearing from May 26-27 to June 9; impacted ability to move forward with CUP (Minor). Working with DPP to accelerate DPP permits | ETA Q4 2021
Kupehau | Kupehau Solar (Stage 2) | [5 empty] | 2021-07-27
Mililani I | Mililani I Solar (Stage 1) | [5 empty] | 2021-07-29
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2021-03-04
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2020-01-23
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2020-01-23
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2017-07-06
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2017-07-06
Mililani I | DPP | Conditional Use Permit - Minor (Modification) | Discretionary | submitted | Approved | 2014-10-03
Mililani I | DPP | Zoning Waiver | Ministerial | submitted | Approved | 2014-07-29
Mililani I | DPP | Conditional Use Permit - Minor | Discretionary | submitted | Approved | 2014-07-29
Mililani I | DPP | Conditional Use Permit - Minor (Joint Development) | Discretionary | submitted | Approved | 2010-05-07
Mililani I | DOH-CWB | NPDES | Ministerial | submitted | Approved | 2021-01-19
Mililani I | FAA | FAA Determination of No Hazard | Ministerial | submitted | Completed | Summer-Fall 2019
Mililani I | USACOE | Section 404 Clean Water Act - Nationwide Permit Program | Ministerial | submitted | Completed | Summer-Fall 2019
Mililani I | USFWS, DLNR-DOFAW | Biological Resource Consultation | Ministerial | submitted | Completed | Summer-Fall 2019
Mililani I | DPP | Grading and Grubbing Permit | Ministerial | Submitted Nov 2020 | Approved | 2021-03-12
Mililani I | DPP | Building Permit (PV Project) | Ministerial | Submitted Nov 2020 | Approved | 2021-03-12
Mililani I | DOH-CWB | Section 401 Water Quality Certification | Ministerial | Not Required | Not Required | N-A
Mililani I | USFWS | Section 7-10 Endangered Species Act Consultation | Ministerial | Not Required | Not Required | N-A
Mililani I | DPP | Building Permit (HECO Substation) | Ministerial | N-A | N-A | N-A
Mililani I | DPP | Building Permit (Project Substation) | Ministerial | Received courtesy inspection approval, anticipate full approval by end of July | Courtesy inspection approval received, Pending full approval (anticipated end of July) | 2021-07-30
Waiawa | Waiawa Solar (Stage 1) | [5 empty] | 2021-07-28
Waiawa | USACOE | Section 404 Clean Water Act - Nationwide Permit Program | Ministerial | Not Required | Not Required | N-A
Waiawa | USFWS | Section 7-10 Endangered Species Act Consultation | Ministerial | Not Required | Not Required | N-A
Waiawa | FAA | FAA Determination of No Hazard | Ministerial |  | Completed | Summer-Fall 2019
Waiawa | USFWS, DLNR-DOFAW | Biological Resource Consultation | Ministerial |  | Completed | Summer-Fall 2019
Waiawa | DOH-CWB | Section 401 Water Quality Certification | Ministerial | Not Required | Not Required | N-A
Waiawa | PUC | Overhead Line Review | Discretionary | Approved | Approved | March, 2021
Waiawa | DOH-CWB | NPDES- Construction | Ministerial | Approved | Approved | 2021-01-19
Waiawa | LUC | Motion to Amend for Urban Land Use | Discretionary | Approved | Approved | 2020-02-11
Waiawa | DPP | Zoning Waiver(s) | Discretionary | Approved Approved | Approved Approved | August 13, 2020 March 15, 2021
Waiawa | DPP | Conditional Use Permit - Minor | Discretionary | Approved | Approved | 2021-04-01
Waiawa | DPP | Conditional Use Permit - Minor Modification | Discretionary | Approved | Approved | 2021-03-15
Waiawa | DPP | Grading and Grubbing Permit | Ministerial | Approved | Approved | 2021-04-06
Waiawa | DPP | Building Permit (PV-BESS Project) | Ministerial | Approved | Q2 2021 | 2021-04-19
Waiawa | DPP | Building Permit (Project Substation) | Ministerial | Approved | Q2 2021 | Q2 2021
Waiawa | DOT | Highway Permit | Ministerial | Submitted | Pending | Q2 2021
Waiawa | DPP | Building Permit (Overhead Line) | Ministerial | Target Submission Q2 2021 | Pending | 2021-10-01
AES Mountain View | AES Mountain View Solar (Stage 2) | [5 empty] | 2021-07-28
AES Mountain View | PUC | Overhead Line Review | Discretionary |  | In progress
AES Mountain View | DLNR-SHPD | HRS 6E Compliance | Discretionary |  |  | ETA Q4 2021-Q1 2021
AES Mountain View | DPP | Conditional Use Permit - Minor | Discretionary |  |  | ETA Q4 2021-Q1 2022
AES Mountain View | DPP | Zoning Waiver (if applicable) | Ministerial |  |  | ETA Q4 2021-Q1 2022
AES Mountain View | DOH-CWB | NPDES | Ministerial |  |  | ETA Q1 2022-Q2 2022
AES Mountain View | DOH-IRHB | Noise Permit | Ministerial |  |  | ETA Q4 2021-Q1 2022
AES Mountain View | DPP | Grading, Grubbing, and Stockpiling Permit | Ministerial |  |  | ETA Q1-Q2 2022
AES Mountain View | DPP | Building and Electrical Permit | Ministerial |  |  | ETA Q1-Q2 2022
Ho‘ohana | Ho‘ohana Solar (Stage 1) | [5 empty] | 2021-07-28
Ho‘ohana | DPP | Conditional Use Permit - Minor | Discretionary |  | Approved | 2015-01-01
Ho‘ohana | DLNR-SHPD | HRS 6E Compliance | Discretionary |  | AIS accepted 2-19-15 | AIS accepted 2-19-15
Ho‘ohana | DPP | Grading (Initial Road Construction) | Ministerial |  | Approved | 2019-12-01
Ho‘ohana | DPP | Conditional Use Permit - Minor Modification | Discretionary |  | Approved | 2019-10-18
Ho‘ohana | DPP | Conditional Use Permit - Minor Modification | Discretionary |  | Approved | 2019-10-19
Ho‘ohana | DOH-CWB | NPDES (Initial Road Construction) | Ministerial |  | Approved | 2019-12-01
Ho‘ohana | DPP | Zoning Waiver | Ministerial |  | Approved | 2021-08-01
Ho‘ohana | DPP | Conditional Use Permit - Minor Modification | Discretionary |  | Approved | 2021-08-01
Ho‘ohana | DPP, LUC | Special Use Permit - Amendment- Restatement of State Land Use Boundary Amendment | Discretionary |  | Approved - Decision and Order pending | 2020-10-08
Ho‘ohana | DOT | Road Crossing Agreement | Ministerial |  | Not Applicable
Ho‘ohana | DPP | Building Permit (HECO Switchyard) | Ministerial | Not required per DPP guidance; requesting confirmatory letter from DPP |  | N-A
Ho‘ohana | PUC | 46kV Line Relocation Approval | Discretionary |  | In Progress
Ho‘ohana | DPP | Grading (Solar and Battery Project) | Ministerial | Target submission July 2021 |  | ETA October 2021
Ho‘ohana | DPP | Grading (Project Substation) | Ministerial | Submitted 5-12-2021 |  | ETA October 2021
Ho‘ohana | DPP | Grading (HECO Switchyard) | Ministerial | Initial submission 5-12-2021; some design work refinement continuing |  | ETA October 2021
Ho‘ohana | DOH-CWB | NPDES - Form C (Solar and Battery Project) | Ministerial | Initial submission 3-22-2021; some design work refinement continuing |  | ETA October 2021
Ho‘ohana | DOH-CWB | NPDES - Form C (Project Substation) | Ministerial | Initial submission 5-12-2021; some design work refinement continuing |  | ETA October 2021
Ho‘ohana | DPP | Building Permit (Solar and Battery Project) | Ministerial | Submit June 2021. Project design in progress |  | ETA November 2021
Ho‘ohana | DPP | Building Permit (Project Substation) | Ministerial | Submission 5-12-2021 |  | ETA November 2021
Waiawa | Waiawa Phase 2 Solar | [5 empty] | 2021-07-28
Waiawa | PUC | Overhead Line Review | Discretionary
Waiawa | DOH-US Navy | Zone of Influence Approval (if applicable) | Ministerial |  |  | ETA Q2-Q3 2021
Waiawa | DLNR-SHPD | HRS 6E Compliance | Ministerial | HRS 6E compliance to START 12-18-20 | HRS 6E compliance to targeted to END 4-9-21 | ETA Q2-Q3 2021
Waiawa | LUC | LUC Amendment to Decision and Order |  |  |  | ETA Q3-Q4 2021
Waiawa | DPP | Conditional Use Permit - Minor |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DPP | Conditional Use Permit - Minor (Joint Development) |  |  |  | ETA Q3 2021-Q4 2021
Waiawa | DPP | Conditional Use Permit - Minor Modification |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DPP | Zoning Waiver (if applicable) |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DOH-CWB | NPDES - Form C |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DOH-IRHB | Noise Permit |  |  |  | ETA Q4 2021-Q1 2022
Waiawa | DPP | Grading, Grubbing, and Stockpiling Permit |  |  |  | ETA Q1-Q2 2022
Waiawa | DPP | Building and Electrical Permit |  |  |  | ETA Q1-Q2 2022
| Mahi Solar | [5 empty] | 2021-09-10
Mahi | DOT | Permit to Cross Public Highway |  |  | Not Required
Mahi | PUC | Approval of PPA |  | Approved - 12-31-2020 | Approved | 2020-12-31
Mahi | PUC | Overhead Line Review |  | Application filed 4-6-21; stipulated procedural schedule filed on 6-21-21 | In Progress
Mahi | DPP, LUC | Special Use Permit |  | Application submitted on 12-15-2020; Revised and resubmitted March 2021. | Approved | 2021-09-09
Mahi | DLNR-SHPD | HRS 6E Compliance (Plan Approval, Archeological Assessment) |  | SHPD accepted the AIS with the proposed mitigation and monitoring measures. Significant traditional historic properties and wahi pana have been identified in the vicinity, including Pohakea Trail, ali‘i battle sites, a heiau atop Pu‘u Ku‘ua, and Honouliuli National Historic Site, among others. None of these significant historic properties were identified as extending into the Mahi Solar project area. However, two plantation-related sites abut or extend into the project area: the Waiāhole Ditch (Site 50-80-09-2268) and remnants of the Oʻahu Sugar Company Irrigation Infrastructure (Site 50-80-12-7346). The AIS report (Rechtman, September 2021) meets the requirements of HAR 13-276-5. It is accepted. Please submit one hard copy of the AIS, labeled Final, along with a text-searchable pdf copy of the AIS and a copy of this letter to the SHPD Kapolei office, attention Library. Please upload a text-searchable pdf copy of the Final AIS to HICRIS Project No. 2021PR00380 using the Project Supplement option, and a copy to Lehua.K.Soares@hawaii.gov. SHPD hereby notifies the DPP that SUP permit issuance process may continue with the understanding that an AMP meeting the requirements of HAR §13-279-4 prior to project initiation shall be submitted for SHPD review and acceptance prior to project initiation. | Determination received | 2021-09-08
Mahi | DPP | Zoning Waiver |  | Target submission August 2021 (after SUP Approval) |  | ETA 10-27-2021
Mahi | DPP | Conditional Use Permit - Minor for Utility Installation, Type B |  | Target submission August 2021 (after SUP Approval) |  | ETA 10-27-2021
Mahi | DPP | Conditional Use Permit - Minor Joint Development |  |  |  | 2021-02-18
Mahi | DPP | Building Permits |  | Target submission October 2021 |  | ETA February 2022
Mahi | DPP | Grading, Grubbing, Stockpiling Permit |  | Target submission October 2021 |  | ETA February 2022
Mahi | DOH-CWB | NPDES - Form C |  |  |  | ETA February 2022
Mahi | DOH-IRHB | Noise Permit |  |  |  | ETA December 2021
kes | Kapolei Energy Storage (Stage 2) | [5 empty] | 2021-07-29
kes | DPP | Conditional Use Permit - Minor |  | Approved - 10-29-2019 | Approved | Approved 10-28-20
kes | PUC | Overhead Line Review |  | Submitted 4-6-2021 | In progress
kes | DPP | Drainage Plan Approval
kes | DPP | Grading, Grubbing, Stockpiling Permit |  | Anticipated to file the application on 10-12-2021 to third party reviewer |  | Update: ETA 2-9-22, slipped from ETA 12-28-2021 (expected)
kes | DPP | Building and Electrical Permit |  | Anticipated to file the application on 11-12-2021 to third party reviewer |  | Update: 3-12-22, slipped from ETA 1-28-2022 (expected)
kes | DOH- CWB | NPDES - Form C |  | Anticipated to file the application to third party reviewer on 10-12-21 |  | Update: ETA 2-9-22, slipped from ETA 12-28-2021 (expected)
kes | DLNR-SHPD | HRS 6E Compliance |  | no longer on docket update (may need to follow-up).
kes | PUC | Overhead Line Review |  | Notice of approval sent on Sept. 15 2021 | Approved | Approved 09/15/2021
Barbers Point Solar (PPA Not Yet Approved by PUC)
| DHHL | HRS 343 EA |  |  | In progress, pre-assessment consultation
| DOT-HWY | Permit to Perform Work Upon State Highway
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I changed this, since some of these are not "permitting" agencies, but are aproving entities - I think it is a difference worth distinguising to help stakeholders understand different roles.
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a column or way to indicate if a permit or approval is ministerial, discretionary, or unclear?
Note on C49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: do you know if this is the permit to perfom work, or is this for application for occupancy and use? both? I am guessing it is for work?
Note on E71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: do they have a confirmatory letter?

## Permit References and Timelines (hidden)
Jurisdiction | Permitting / Approving Agency | Permit or Approval | Resources |  | Type | Common Rank (1 most common - 5 less common) | Typical Timeline (days) | https://energy.hawaii.gov/renewable-energy-project-permitting-in-the-state-of-Hawai‘i
County | DPP | Conditional Use Permit - Minor | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/ReportsNotices/MonthlyBulletins.aspx | Discretionary | 1 | 45
County | DPP | Grading Permit | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/ReportsNotices/MonthlyBulletins.aspx | Ministerial | 1
County | DPP | Zoning Waiver | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/Calendar.aspx | Ministerial | 1 | 30-90 days | https://energy.hawaii.gov/wp-content/uploads/2015/07/Oahu-Waiver-Permit_March-2015.pdf
County | DPP | Grubbing Permit | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/ReportsNotices/MonthlyBulletins.aspx | Ministerial | 1
County | DPP | Building Permit Project | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/ReportsNotices/MonthlyBulletins.aspx | Ministerial | 1
State | DOH-CWB | NPDES (Initial Road Construction) | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 1
Steate | DOH-CWB | NPDES (Construction) | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 1
State | DOH-CWB | NPDES (Solar and Battery Project) | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 1
State | DOH-IRHB | Noise Permit | ask developer |  | Ministerial | 1
State | LUC (State) | Special Use Permit (Projects >15 acres, LUC makes final decision). | https://luc.hawaii.gov/ |  | Discretionary | 1
County | Planning Commission (County) | Special Use Permit (Projects >15 acres, LUC makes final decision). | https://www.honolulu.gov/dpppd/default.html |  | Discretionary
County | DPP | Trenching Permit | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx |  | Ministerial | 2
State | DOT-HWY | Permit Application to Perform Work Upon State Highways |  |  | Ministerial | 2 | 5-10 days
State | DOT-HWY | Application & Permit for the Occupancy & Use of State Highway Right-of-Way |  |  | Ministerial | 2 | 5-10 days
State | DOH-CWB | NPDES Dewatering | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 2
County | DPP | Conditional Use Permit - Major | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx |  | Discretionary | 3 | 90
Federal | USACOE | Section 404 Clean Water Act - Nationwide Permit Program |  |  | Ministerial | 3
State | DLNR - OCCL | Conservation District Use Permit | https://dlnr.hawaii.gov/occl/current-applications/ |  | Discretionary | 3
State | DBEDT - OP | CZMA Fed Consistency |  |  | Ministerial | 3
State | LUC | District Boundary Amendment | https://luc.hawaii.gov/calendar/ luc.hawaii.gov -> then hit pending dockets -> boundary amendments |  | Discretionary | 3 | 365
Federal | USACE | CWA Section 404 Permit - Individual |  |  | Discretionary | 4
State | DPP | SMA - major | http://www.honoluludpp.org/ReportsNotices/DailyBulletins.aspx | http://www.honoluludpp.org/Calendar.aspx | Discretionary | 5 | 180
Federal | USACE | Section 9 |  |  | Discretionary | 5
State | PUC | 46kV Line Relocation Approval |  |  | Discretionary - PUC | 1
State | SHPD | HRS 6E, Historic Preservation | https://dlnr.hawaii.gov/shpd/intake-and-determinations/ | see determinations reports | Discretionary | 1
Federal | USFWS | Section 7/10 Endangered Species Act Consultation |  |  | Ministerial | 2
Federal | FAA | FAA Determination of No Hazard |  |  | Ministerial | 2
State | Varies - Accepting Agency | HRS 343 EA | http://oeqc2.doh.hawaii.gov/_layouts/15/start.aspx#/Doc_Library/ |  | Discretionary | 3
State | DOH CWB | CWA Section 401 WQ Certification | http://eha-web.doh.hawaii.gov/wpc-viewer/ |  | Ministerial | 3
State | DLNR - CWRM | Stream channel Alteration |  |  | Discretionary | 4
State / County | DLNR - CWRM | Stream Diversion |  |  | Discretionary | 4
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I changed this, since some of these are not "permitting" agencies, but are aproving entities - I think it is a difference worth distinguising to help stakeholders understand different roles.
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a column or way to indicate if a permit or approval is ministerial, discretionary, or unclear?

## TMKs (hidden)
Project * | Tax Map Key(s)
AES Mountain View Solar | 185003031; 185003032; 185019034
AES West Oahu Solar Plus Storage | 192002007
Hoohana Solar 1 | 194002052
Kapolei Energy Storage | 191014042
Mahi Solar | 192001001; 192004012; 192004006; 192004003; 192004010
Mililani I Solar | 194005090; 194005092; 194005096; 194005091
Waiawa Phase 2 Solar | 196004024; 196004025; 196004026; 196006036
Waiawa Solar Power | 196004024

## zzz_TF Master Schedule (hidden)
| 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-05-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-07-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-09-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-11-21 | 2021-11-21 | 2021-11-21 | 2021-11-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2021-12-21 | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-02-22 | 2022-02-22 | 2022-02-22 | 2022-02-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-03-22 | 2022-04-22 | 2022-04-22 | 2022-04-22 | 2022-04-22 | 2022-05-22 | 2022-05-22 | 2022-05-22 | 2022-05-22 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | Coal | 2022-09-01 | 2022-09-01 | 2022-09-01 | 2022-09-01 | 2022-10-22 | 2022-10-22 | 2022-10-22 | 2022-10-22 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2023-01-23 | 2023-02-23 | 2023-03-23 | 2023-04-23 | 2023-05-23 | 2023-06-23 | 2023-07-23 | 2023-08-23 | 2023-09-23 | 2023-10-23 | 2023-11-23 | 2023-12-23
AES West O‘ahu Solar (Stage 1) - 2019-0050 | [64 empty] | Plant | GCOD
Environmental Site Studies | DONE | [63 empty] | Shut
Engineering and Design | Engineering (Q3 2020 - Q3 2021); Engineering at 100% design phase | [63 empty] | Down
IRS System Impact Study | DONE
IRS Facility Study | DONE
IRS Amendment | DONE
Transmission Line Approval | DONE
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q3 2020 - Q4 2021) -- LUC hearing on SUP 6/9-6/10; CUP expected Q3 2021
Permitting: Construction (Ministerial) | Permitting (Q3 2020 - Q4 2021)
Procurement | Procurement (Q1 2021 - Q4 2021)
Construction | [20 empty] | Construction (Q4 2021 - Q2 2022)
Hawaiian Electric Work | Hawaiian Electric Work (Q4 2020 - Q2 2022) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [32 empty] | Testing and Commissioning (Q1 2022 - Q3 2022) -- Acceptance Test typically takes 30 business days
Energization | [32 empty] | Testing and Commissioning (Q1 2022 - Q3 2022) -- Energization is a one time event
Commissioning | [32 empty] | Testing and Commissioning (Q1 2022 - Q3 2022) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [32 empty] | Testing and Commissioning (Q1 2022 - Q3 2022) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [65 empty] | GCOD
Mililani I Solar (Stage 1) - 2018-0434 | [73 empty] | GCOD
Environmental Site Studies | DONE
Engineering and Design | Engineering (Q2 2020 - Q3 2021) -- HECO reviewed 90% design; Issued for Construction (IFC); 60% design for substation
IRS System Impact Study | DONE
IRS Facility Study | DONE
IRS Amendment | DONE
Transmission Line Approval | DONE
Permitting: Environmental and Land Use (Discretionary) | DONE
Permitting: Construction (Ministerial) | Permitting (Q4 2020 - Q2 2021) -- final Building Permit (substation) expected June 2021
Procurement | Procurement (Q3 2020 - Q3 2021)
Construction | Construction (Q1 2021 - Q1 2022) -- groundbreaking ceremony April 2021; construction expected May 2021
Hawaiian Electric Work | Hawaiian Electric Work (Q4 2020 - Q4 2021) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [32 empty] | Testing and Commissioning (Q1 2022 - Q4 2022) -- Acceptance Test typically takes 30 business days
Energization | [32 empty] | Testing and Commissioning (Q1 2022 - Q4 2022) -- Energization is a one time event
Commissioning | [32 empty] | Testing and Commissioning (Q1 2022 - Q4 2022) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [32 empty] | Testing and Commissioning (Q1 2022 - Q4 2022) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [57 empty] | Potential GCOD 7/31/22 | [15 empty] | GCOD
Waiawa Solar (Stage 1) - 2018-0435 | [77 empty] | GCOD
Environmental Site Studies | DONE
Engineering and Design | Engineering (Q4 2020 - Q3 2021) -- HECO reviewed 90% substation design; 60% gen-tie design; 90% design under development
IRS System Impact Study | DONE
IRS Facility Study | DONE
IRS Amendment | DONE
Transmission Line Approval | DONE
Permitting: Environmental and Land Use (Discretionary) | DONE
Permitting: Construction (Ministerial) | Permitting (Q4 2020 - Q3 2021) -- substation Building Permit expected July 2021; 46kV OH line Building Permit expected October 2021
Procurement | Procurement (Q3 2020 - 4 2021)
Construction | Construction (Q1 2021 - Q2 2022) -- groundbreaking ceremony April 2021; construction expected May 2021
Hawaiian Electric Work | Hawaiian Electric Work (Q4 2020 - Q4 2021) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [44 empty] | Testing and Commissioning (Q2 2022 - Q4 2022) -- Acceptance Test typically takes 30 business days
Energization | [44 empty] | Testing and Commissioning (Q2 2022 - Q4 2022) -- Energization is a one time event
Commissioning | [44 empty] | Testing and Commissioning (Q2 2022 - Q4 2022) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [44 empty] | Testing and Commissioning (Q2 2022 - Q4 2022) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [63 empty] | Potential GCOD 8/31/22 | [13 empty] | GCOD
Kapolei Energy Storage (Stage 2) - 2020-0136 | [69 empty] | New GCOD - early battery delivery | [10 empty] | New GCOD - NO early battery delivery
Environmental Site Studies
Engineering and Design | Early Engineering Letter Agreement executed; HE reviewed 30% design
IRS System Impact Study | DONE
IRS Facility Study | Revised FS completed May 2021, however, revisions are likely due to KES's new proposed schedule
IRS Amendment | IRS Amendment process scheduled from late May to July 2021
Transmission Line Approval | Application for 138kV OH line filed 4/6/21
Permitting: Environmental and Land Use (Discretionary) | DONE -- KES plans to secure land rights by June 2021
Permitting: Construction (Ministerial) | [16 empty] | Construction Permitting (9/15/21 - 1/7/22)
Procurement | Procurement (3/16/21 - 6/10/22)
Construction | Construction (October 2020 - July 2022)
Hawaiian Electric Work | Hawaiian Electric Work (September 2019 - July 2022)
Acceptance Test | [57 empty] | Acceptance Testing
Control System Acceptance Test | [65 empty] | CSAT
Commercial Operations | [52 empty] | Original GCOD | [16 empty] | New GCOD - early battery delivery | [10 empty] | New GCOD - NO early battery delivery
AES Mountain View Solar (Stage 2) - 2020-0139
Environmental Site Studies |  | Virtual Public Meeting on 5/19
Engineering and Design | Engineering (Q2 2021 - Q2 2022) -- to stay on schedule Early Engineering Agreement must be executed no later than June 2021; AES and HE are discussing Early Engineering (May 2021 Status Report)
IRS System Impact Study | Anticipated to be completed May 2021
IRS Facility Study | Exchanged comments May 2021
IRS Amendment | [8 empty] | Estimated filing of IRS Amendment for Stage 2 projects (2Q/3Q 2021)
Transmission Line Approval | [8 empty] | Estimated filing of OH Line Approval for Stage 2 projects (2Q/3Q 2021)
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q3 2021 - Q2 2022) -- HRS 6E compliance to be completed Q2/Q3 2021; Environmental and Land Use Permitting to be completed by Q1 2022 (May 2021 Status Update)
Permitting: Construction (Ministerial)
Procurement | [8 empty] | Procurement (Q3 2021 - Q2 2022)
Construction | [44 empty] | Construction (Q2 2022 - Q1 2023)
Hawaiian Electric Work - Remote Engineering | [8 empty] | Remote Engineering (Q3 2021 - Q1 2022)
Hawaiian Electric Work - Remote Procurement | [20 empty] | Remote Procurement (Q4 2021 - Q3 2022)
Hawaiian Electric Work - Remote Construction | [56 empty] | Remote Construction (Q3 2022)
Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q2 2023) -- Acceptance Test typically takes 30 business days
Energization | [81 empty] | Testing and Commissioning (Q1 2023 - Q2 2023) -- Energization is a one time event
Commissioning | [81 empty] | Testing and Commissioning (Q1 2023 - Q2 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q2 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [85 empty] | GCOD
Kupehau Solar (Stage 2) - 2020-0138
Environmental Site Studies
Engineering and Design | Engineering (Q2 2020 - Q3 2022) -- Early Engineering Agreement executed; HECO reviewed 30% design
IRS System Impact Study | Anticipated SIS completion date May 2021
IRS Facility Study | Preliminary FS under review by 174PG
IRS Amendment | Anticipated IRS Amendment completion date is confidential (HECO 3/15/21 IR Response)
Transmission Line Approval | To be included with Ho‘ohana Solar 1
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q1 2020 - Q2 2022) -- Environmental and Land Use Permit to be completed March 2022 (May 2021 Status Update)
Permitting: Construction (Ministerial) | Permitting (Q1 2020 - Q2 2022) -- Construction Permitting to be completed May 2022 (May 2021 Status Update)
Procurement | Procurement (Q2 2020 - Q3 2022)
Construction | [32 empty] | Construction (Q1 2022 - Q1 2023)
Hawaiian Electric Work | Hawaiian Electric Work (Q1 2021 - Q1 2023) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Acceptance Test typically takes 30 business days
Energization | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Energization is a one time event
Commissioning | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [87 empty] | New estimated GCOD (7/1/23)
Ho‘ohana Solar 1 (Stage 1) - 2018-0431
Environmental Site Studies | DONE
Engineering and Design | Engineering (Q2 2020 - Q1 2022) -- 60% switchyard design due to HECO 6/3/21; 90% switchyard design due to HECO 10/6/21
IRS System Impact Study | SIS re-study expected to be completed May 2021
IRS Facility Study | DONE
IRS Amendment | DONE
Transmission Line Approval | Application for 138kV Kahe-Hālawa OH line filed 2/26/21; application for 138kV Kahe-Waiau UG line to be filed June 2021; filing for 46kV Wai‘au-Mililani UG/OH line relocation to be filed June 2021
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q1 2020 -Q1 2022) -- CUP-M modification and Zoning Waiver to be submitted June 2021
Permitting: Construction (Ministerial) | Permitting (Q1 2020 -Q1 2022) -- final Building Permit (solar/battery) to be submitted June 2021
Procurement | Procurement (Q2 2021 - Q3 2022)
Construction | [32 empty] | Construction (Q1 2022 - Q1 2023)
Hawaiian Electric Work | Hawaiian Electric Work (Q2 2021 - Q4 2022) -- engineering, design, procurement, construction of interconnection facilities
Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Acceptance Test typically takes 30 business days
Energization | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Energization is a one time event
Commissioning | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [81 empty] | Testing and Commissioning (Q1 2023 - Q3 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [88 empty] | GCOD
Waiawa Phase 2 Solar (Stage 2) - 2020-0137
Environmental Site Studies
Engineering and Design |  |  |  |  | Engineering (Q1 2021 - Q2 2022) -- Engineering and Design must start June 2021 to stay on schedule; AES and HE are discussing Early Engineering; Waiawa Solar (stage 1 ) line runs through Waiawa Phase 2 site; potential delays to GCOD if Wahiawa substation work is not completed on-time (May 2021 Status Report)
IRS System Impact Study | DONE
IRS Facility Study | Final FS was sent to Waiawa on 6/1/2021. Preparing responses to Developer's questions provided on 6/11/2021
IRS Amendment | [8 empty] | Estimated filing of IRS Amendment for Stage 2 projects (2Q/3Q 2021)
Transmission Line Approval | [8 empty] | Estimated filing of OH Line Approval for Stage 2 projects (2Q/3Q 2021)
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q3 2020 - Q2 2022) -- HRS 6E compliance to be completed Q2/Q3 2021
Permitting: Construction (Ministerial)
Procurement | [32 empty] | Assumes Procurement starts after Environmental and Land Use Permitting is complete
Construction | [20 empty] | Construction (Q4 2021 - Q2 2023)
Hawaiian Electric Work - Remote Engineering | [12 empty] | Remote Engineering (Q3 2021 - Q3 2022)
Hawaiian Electric Work - Remote Procurement | [32 empty] | Remote Procurement (Q1 2022 - Q1 2023)
Hawaiian Electric Work - Remote Construction | [81 empty] | Remote Construction (Q1 2023 - Q2 2023)
Acceptance Test | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Acceptance Test typically takes 30 business days
Energization | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Energization is a one time event
Commissioning | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [90 empty] | GCOD
Mahi Solar (Stage 2) - 2020-0140
Environmental Site Studies
Engineering and Design | Engineering (Q2 2021 - Q2 2022) -- Early Engineering Agreement executed 4/15/21
IRS System Impact Study | DONE
IRS Facility Study | Preliminary FS issued to Longroad 2/10/21; review completed; final FS to be completed July 2021
IRS Amendment | [8 empty] | Estimated filing of IRS Amendment for Stage 2 projects (2Q/3Q 2021)
Transmission Line Approval | [8 empty] | Estimated filing of OH Line Approval for Stage 2 projects (2Q/3Q 2021)
Permitting: Environmental and Land Use (Discretionary) | Permitting (Q2 2020 - Q1 2022) -- C&CH Planning Commission to hear SUP on 6/23/21; Longroad planning for SUP approval by August 2021
Permitting: Construction (Ministerial) | [19 empty] | Estimated Construction Permitting starts
Procurement |  |  |  |  | Procurement (Q2 2021 - Q4 2022)
Construction | [32 empty] | Construction (Q1 2022 - Q2 2023)
Hawaiian Electric Work - Remote Engineering | Remote Engineering (Q2 2021 - Q1 2022)
Hawaiian Electric Work - Remote Procurement | [20 empty] | Remote Procurement (Q4 2021 - Q3 2022)
Hawaiian Electric Work - Remote Construction | [56 empty] | Remote Construction (Q3 2022 - Q4 2022)
Acceptance Test | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Acceptance Test typically takes 30 business days
Energization | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Energization is a one time event
Commissioning | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- Commissioning includes Acceptance Test and CSAT
Control System Acceptance Test | [84 empty] | Testing and Commissioning (Q2 2023 - Q4 2023) -- CSAT tests operation of entire system; requires adequate solar resource
Commercial Operations | [92 empty] | GCOD
Barbers Point Solar
Kupono Solar*
NEPA Compliance JBPHH

## Permit Details Demo (hidden)
Permitting Agency | Permit or Approval | Required Studies | Status of Required Studies | Permit Number | Application Date or Status | Issuance Status | Permit or Approval Issuance or Target (ETA) Date | Developer | Developer Contact | Project Website | Project Size (ac) + Storage (ac) | Location | Tax Map Key(s) | Project Size (Gross Area in Acres) | County Zoning | State Land Use District(s) (Soil Types) | PUC Docket | PUC Term (Years) | Project Guaranteed Commercial Operations Date
Kupehau Solar | [7 empty] | 174 Power Global |  | Kupehau Solar | 60MW + 240MWh | Kunia | (1)9-2-004:008 | 254 | AG-1 | Agricultural (D, E) | 2020-0138 | 20 | 2022-05-31
PUC | 46kV Line Relocation Approval |  |  |  | Not Required | Will interconnect w/ Ho‘ohana Solar
LUC | Special Use Permit |  |  |  | Not Applicable | Not Applicable
DPP | Grading (Initial Road Construction) |  |  |  | Not Applicable | Not Applicable
DPP | Conditional Use Permit - Minor Amendment |  |  |  | Not Applicable | Not Applicable
DOH-CWB | NPDES (Initial Road Construction) |  |  |  | Not Applicable | Not Applicable
DLNR-SHPD | HRS 6E Compliance | Environmental and Cultural Studies (Biologic Survey and Archeological Inventory Survey) | Target Completion Q1 2021 |  |  |  | ETA Q3 2021
DPP | Conditional Use Permit - Minor |  | Biologic Survey and AIS Pending |  | Target submission June 2021 | Biologic Survey and AIS Pending | ETA September 2021
DPP | Zoning Waiver |  |  |  | Target submission June 2021 |  | ETA September 2021
DPP | Grading (Project Substation) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Grading (HECO Switchyard) |  |  |  | Target submission May 2021 |  | ETA October 2021
DOH-CWB | NPDES (Project Substation) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Building Permit (Project Substation) |  |  |  | Target submission May 2021 |  | ETA November 2021
DPP | Building Permit (HECO Switchyard) |  |  |  | Target submission May 2021 |  | ETA November 2021
DOH-CWB | NPDES (Solar and Battery Project) |  |  |  | Target submission December 2021 |  | ETA March 2022
DPP | Building Permit (Solar and Battery Project) |  |  |  | Target submission December 2021 |  | ETA March 2022
DPP | Grading (Solar and Battery Project) |  |  |  | Target submission December 2021 |  | ETA March 2022
DOT | Road Crossing Agreement |  |  |  | Target submission December 2021 |  | ETA August 2022
AES West O‘ahu Solar | [7 empty] | AES |  | AES West Oahu | 12.5MW + 50MWh | Makakilo | (1)9-2-002:007 | 97 | AG-1 | Agricultural (B,D,E) | 2019-0050 | 25 | 2022-09-07
DLNR-CWRM | Stream Channel Alteration Permit |  |  |  | Not Required | Not Required
DLNR-SHPD | HRS 6E Compliance | Archeological Inventory Study | Submitted to SHPD 2/6/20 | 19-07 | Approved | Approved
DPP, OEQC | HRS 343 Compliance (Environmental Assessment) |  |  |  | Accepted | Accepted | FEA accepted and filed on 07-08-20
PUC | Overhead Line Review |  |  |  |  | Approved 03/18/21
|  | Biological Resource Consultation |  |  | Completed | Completed
|  | Cultural Impact Assessment |  |  | Completed | Completed
DPP, LUC | Special Use Permit |  |  | 2020/SUP-6 SP21-411 |  | Planning Commission approved on 3/17/21 | ETA Q2 2021 (LUC approval)
DOH-CWB | NPDES | [5 empty] | ETA Q2 2021
DPP | Conditional Use Permit - Minor | [5 empty] | ETA Q3 2021
DPP | Zoning Waiver (if applicable) | [5 empty] | ETA Q3 2021
DOH-IRHB | Noise Permit | [5 empty] | ETA Q3 2021
DPP | Grading, Grubbing, and Stockpiling Permit | [5 empty] | ETA Q4 2021
DPP | Building and Electrical Permit | [5 empty] | ETA Q4 2021
Mililani I Solar | [7 empty] | Clearway |  |  | 39MW + 156MWh | Mililani | (1)9-4-005:090 (1)9-4-005:092 (1)9-4-005:096 (1)9-4-005:091 | 144 | AG-1 | Agricultural | 2018-0434 | 20 | 2022-11-01
DPP | Conditional Use Permit - Minor (Modification) | 2021/MOD-8 |  |  |  | Approved | 2021-03-04
DPP | Conditional Use Permit - Minor (Modification) | 2019/MOD-108 |  |  |  | Approved | 2020-01-23
DPP | Conditional Use Permit - Minor (Modification) | 2019/MOD-107 |  |  |  | Approved | 2020-01-23
DPP | Conditional Use Permit - Minor (Modification) | 2017/MOD-46 |  |  |  | Approved | 2017-07-06
DPP | Conditional Use Permit - Minor (Modification) | 2017/MOD-42 |  |  |  | Approved | 2017-07-06
DPP | Conditional Use Permit - Minor (Modification) | 2014/MOD-95 |  |  |  | Approved | 2014-10-03
DPP | Zoning Waiver | 2014/W-14 |  |  |  | Approved | 2014-07-29
DPP | Conditional Use Permit - Minor | 2014/CUP-23 |  |  |  | Approved | 2014-07-29
DPP | Conditional Use Permit - Minor (Joint Development) | 2010/CUP-10, Joint Development |  |  |  | Approved | 2010-05-07
DOH-CWB | NPDES |  |  |  |  | Approved | 2021-01-19
FAA | FAA Determination of No Hazard |  |  |  |  | Completed | Summer/Fall 2019
USACOE | Section 404 Clean Water Act - Nationwide Permit Program |  |  |  |  | Completed | Summer/Fall 2019
USFWS, DLNR-DOFAW | Biological Resource Consultation |  |  |  |  | Completed | Summer/Fall 2019
DPP | Grading and Grubbing Permit |  |  |  | Submitted Nov 2020 | Approved | 2021-03-12
DPP | Building Permit (PV Project) |  |  |  | Submitted Nov 2020 | Approved | 2021-03-12
DOH-CWB | Section 401 Water Quality Certification |  |  |  | Not Required | Not Required | N/A
USFWS | Section 7/10 Endangered Species Act Consultation |  |  |  | Not Required | Not Required | N/A
DPP | Building Permit (HECO Substation) |  |  |  | N/A | N/A | N/A
DPP | Building Permit (Project Substation) |  |  |  | Submitted | Pending | 2021-06-24
Waiawa Solar | [7 empty] | Clearway |  |  | 36MW + 144MWh | Pearl City | (1)9-6-004:024 | 200 | AG-1 | Urban | 2018-0435 | 20 | 2022-12-01
DOH-CWB | Section 401 Water Quality Certification |  |  |  | Not Required | Not Required | N/A
PUC | Overhead Line Review |  |  |  | Approved | Approved | 2021-03-01
USACOE | Section 404 Clean Water Act - Nationwide Permit Program |  |  |  | Not Required | Not Required | N/A
USFWS | Section 7/10 Endangered Species Act Consultation |  |  |  | Not Required | Not Required | N/A
FAA | FAA Determination of No Hazard |  |  |  |  | Completed | Summer/Fall 2019
USFWS, DLNR-DOFAW | Biological Resource Consultation |  |  |  |  | Completed | Summer/Fall 2019
DOH-CWB | NPDES |  |  |  | Approved | Approved | 2021-01-19
LUC | Motion to Amend for Urban Land Use |  |  |  | Approved | Approved | 2020-02-11
DPP | Zoning Waiver(s) |  |  | 2020/W-31 2021/W-8(CK) | Approved Approved | Approved Approved | August 13, 2020 March 15, 2021
DPP | Conditional Use Permit - Minor |  |  | 2020/CUP-2 | Approved | Approved | 2021-04-01
DPP | Conditional Use Permit - Minor Modification |  |  | 2021/MOD-23 | Approved | Approved | 2021-03-15
DPP | Grading and Grubbing Permit |  |  |  | Submitted November 2020 | Approved | 2021-04-06
DOT | Highway Permit |  |  |  | Submitted | Pending | Q2 2021
DPP | Building Permit (PV/BESS Project) |  |  |  | Submitted December 2020 | Pending | Q2 2021
DPP | Building Permit (Overhead Line) |  |  |  | Target Submission Q2 2021 | Pending | 2021-10-01
DPP | Building Permit (Project Substation) |  |  |  | Submitted February 23, 2021 | Pending | Q2 2021
AES Mountain View Solar | [7 empty] | AES |  | Mountain View Solar | 7MW + 35MWh | Wai‘anae | (1)8-5-003:031 (1)8-5-003:032 (1)8-5-019:034 | 100 | AG-1 | Agricultural (C,E) | 2020-0139 | 25 | 2023-05-17
PUC | Overhead Line Review
DLNR-SHPD | HRS 6E Compliance | Environmental and Cultural Studies (Biologic Survey and Archeological Inventory Survey) |  |  |  |  | ETA Q2-Q3 2021
DPP | Conditional Use Permit - Minor |  | Biologic Survey and AIS Pending |  |  |  | ETA Q4 2021-Q1 2022
DPP | Zoning Waiver (if applicable) | [5 empty] | ETA Q4 2021-Q1 2022
DOH-CWB | NPDES | [5 empty] | ETA Q4 2021-Q1 2022
DOH-IRHB | Noise Permit | [5 empty] | ETA Q4 2021-Q1 2022
DPP | Grading, Grubbing, and Stockpiling Permit | [5 empty] | ETA Q1-Q2 2022
DPP | Building and Electrical Permit | [5 empty] | ETA Q1-Q2 2022
Ho‘ohana Solar | [7 empty] | 174 Power Global, Hanwha |  |  | 52MW + 218MWh | Kunia | (1)9-4-002:052 | 160 | AG-1 | Urban | 2018-0431 | 20 | 2023-08-31
DPP | Conditional Use Permit - Minor |  |  | 2014/CUP-76 |  | Approved | 2015-01-01
DPP | Zoning Waiver |  |  | 2014/W-67 |  | Approved | 2015
DLNR-SHPD | HRS 6E Compliance | Archeological Inventory Study | Accepted 2/19/15 | LOG#2014.03535 LOG#2014.04974 Doc#1502SL23 |  | AIS accepted 2/19/15 | AIS accepted 2/19/15
DPP | Grading (Initial Road Construction) |  |  |  |  | Approved | 2019-12-01
DPP | Conditional Use Permit - Minor Modification |  |  | 2019/MOD-94 |  | Approved | 2019-10-18
DPP | Conditional Use Permit - Minor Modification |  |  | 2019/MOD-84 |  | Approved | 2019-10-19
DOH-CWB | NPDES (Initial Road Construction) |  |  |  |  | Approved | 2019-12-01
DPP | Zoning Waiver |  |  | 2020/W-27 |  | Approved | 2020-08-01
DPP | Conditional Use Permit - Minor Modification |  |  | 2020/MOD-38 |  | Approved | 2020-08-01
DPP, LUC | Special Use Permit - Amendment |  |  |  |  | Approved - Decision and Order pending | 2020-10-08
DOT | Road Crossing Agreement |  |  |  |  | Not Applicable
PUC | 46kV Line Relocation Approval |  |  |  |  | In Progress
DPP | Grading (Solar and Battery Project) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Grading (Project Substation) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Grading (HECO Switchyard) |  |  |  | Target submission May 2021 |  | ETA October 2021
DOH-CWB | NPDES (Solar and Battery Project) |  |  |  | Target submission May 2021 |  | ETA October 2021
DOH-CWB | NPDES (Project Substation) |  |  |  | Target submission May 2021 |  | ETA October 2021
DPP | Building Permit (Solar and Battery Project) |  |  |  | Target submission May 2021 |  | ETA November 2021
DPP | Building Permit (Project Substation) |  |  |  | Target submission May 2021 |  | ETA November 2021
DPP | Building Permit (HECO Switchyard) |  |  |  | Target submission May 2021 |  | ETA November 2021
Waiawa Phase 2 Solar | [7 empty] | AES |  | Waiawa Phase 2 Solar | 30MW + 240MWh | Waiawa | (1)9-6-004:024 (1)9-6-004:025 (1)9-6-004:026 (1)9-6-006:036 | 387 | Multiple Zones | Urban | 2020-0137 | 20 | 2023-10-30
PUC | Overhead Line Review |  |  |  |  | In Progress
DOH-US Navy | Zone of Influence Approval (if applicable) | [5 empty] | ETA Q2-Q3 2021
DLNR-SHPD | HRS 6E Compliance | Environmental and Cultural Studies (Biologic Survey and Archeological Inventory Survey) | AIS accepted April 2015 |  | HRS 6E compliance to START 12/18/20 | HRS 6E compliance to targeted to END 4/9/21 | ETA Q2-Q3 2021
LUC | LUC Amendment to Decision and Order | [5 empty] | ETA Q3-Q4 2021
DPP | Conditional Use Permit - Minor |  | Biologic Survey and AIS pending |  |  |  | ETA Q4 2021-Q1 2022
DPP | Conditional Use Permit - Minor (Joint Development) | [5 empty] | ETA Q4 2021-Q1 2022
DPP | Conditional Use Permit - Minor Modification | [5 empty] | ETA Q4 2021-Q1 2022
DPP | Zoning Waiver (if applicable) | [5 empty] | ETA Q4 2021-Q1 2022
DOH-CWB | NPDES | [5 empty] | ETA Q4 2021-Q1 2022
DOH-IRHB | Noise Permit | [5 empty] | ETA Q4 2021-Q1 2022
DPP | Grading, Grubbing, and Stockpiling Permit | [5 empty] | ETA Q1-Q2 2022
DPP | Building and Electrical Permit | [5 empty] | ETA Q1-Q2 2022
Mahi Solar | [7 empty] | Longroad Energy |  | Mahi Solar | 120MW + 480MWh | Kunia | (1)9-2-001:020 (1)9-2-004:012 (1)9-2-004:006 (1)9-2-004:003 (1)9-2-004:010 | 627 | AG-1 | Agricultural (B,C,D,E) | 2020-0140 | 25 | 2023-12-31
DOT | Permit to Cross Public Highway |  |  |  |  | Not Required
PUC | Overhead Line Review |  |  |  |  | In Progress
DPP, LUC | Special Use Permit |  |  | 2020/SUP-7 | Application submitted on 12/15/2020 | Application now being circulated for agency comments (due May 10).
DLNR-SHPD | HRS 6E Compliance (Plan Approval, Archeological Assessment) | Environmental Studies to be Completed in 2021 | Archeological Assessment to be Submitted Q2 2021 |  | Target submission Q2 2021 |  | Need SHPD Concurrence Letter by June 2021 before Planning Commission meeting on SUP
DPP | Zoning Waiver |  |  |  | Target submission August 2021 (after SUP Approval) |  | ETA September 2022
DPP | Conditional Use Permit - Minor |  |  | 2020/CUP-48 | Target submission August 2021 (after SUP Approval) |  | ETA September 2022
DPP | Conditional Use Permit - Minor Joint Development | [5 empty] | 2021-02-18
DPP | Building Permits |  |  |  | Target submission October 2021 |  | ETA March 2022
DPP | Grading Permit |  |  |  | Target submission October 2021 |  | ETA March 2022
DOH-CWB | NPDES | [5 empty] | ETA December 2021
DOH-IRHB | Noise Permit | [5 empty] | ETA December 2021
Grey = Permit or Approval is Not Needed or has Been Approved or Completed
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is there a column or way to indicate if a permit or approval is ministerial, discretionary, or unclear?